## How to read
Section | Plain English
What this file is | The desktop's living audit + findings ledger — maintained exactly like the phone's master file: every doc-vs-code audit gets a tab, every walk finding gets a row with a verified root cause and a status, every decision gets logged the day it's made.
Standing rules carried over | Mock-first (mockups/desktop/, never overwrite, supersede with v2) · same-day changelog · full-surface done with coverage lines · builds only on your literal word.

## Findings
# | Your finding | Verified root cause | Fix + coverage | Status

## Decisions log
Date | Decision | Decided by
2026-08-03 | Desktop workstream STARTED on the founder's word ("start immediately"), on the recommended path: web app first → installable wrap; big-screen redesign of the five surfaces; same gates as the phone. | Founder
2026-08-03 | Structure created: MK-desktop-PRD-v1 (derived row-by-row from the app PRD with SAME/DIFFERENT verdicts) · MK-desktop-UX-design-v1 (same derivation from the app UX file + desktop-new rules) · this audit file · mockups/desktop/. | Founder-directed
2026-08-03 | One-brain rule affirmed: desktop consumes the SAME engines, store, and navigation map as the phone — no forked math, ever; the sameness contract now spans devices. | Standing (from the app PRD)
2026-08-03 | PHASE 1 STARTED on founder's word ("start building desktop application"). Scaffolding only — no user-facing design before the mock gates. | Founder
2026-08-03 | Phase 1 milestone: the web build EXPORTS — react-native-web installed; web platform on (metro, single-page); browser dialogs stand in for phone alerts via a web-only module shim (styled sheets come with the design phase); sign-in persistence uses the browser's own storage on web; the notifications side effect is guarded; fonts fall back to the system face. Phone side verified untouched: full suite green. | Build log
2026-08-03 | Desktop mock v1 DELIVERED (mockups/desktop/shell-home-plan-desktop-v1): the sidebar shell + Home + Plan at full width — AWAITING founder verdict. Phase 2 builds nothing until it. | Awaiting founder
2026-08-03 | Folder consolidation (founder): everything desktop moved under finwise/desktop/ — docs/, mockups/, platform/ (web shims). Shared engines stay in src/ per the one-brain rule. | Founder
2026-08-03 | Desktop mock v1 APPROVED (founder: "I like it"). Phase 2 build began. | Founder
2026-08-03 | Phase 2 milestone: the SIDEBAR SHELL is built — web-only branch in the tabs layout renders DesktopSidebar (same TAB_META map, lens order preserved, long-tail + Hide balances + Sign out in the foot); the bottom bar untouched on phones. Web export green; phone suite green. NEXT: Home and Plan two-column layouts to the approved windows. | Build log
2026-08-03 | ALL THREE DESKTOP DOCS APPROVED by the founder ("consider docs approved") — the derived PRD (180 criteria + NFR verdicts + desktop-only requirements), the UX design file (derived rules + 9 desktop-new), and this audit structure. The build proceeds against them as the approved spec. | Founder
2026-08-04 | Phase 2 milestone: PLAN TWO-COLUMN INTERIOR BUILT to the approved shell mock — verdict + next-decision + ranked decisions LEFT (1.15) ¦ INLINE sandbox + saved scenarios + revert + sharpen meter RIGHT (0.85). The sandbox is new: dials (retire age / save / spend; retired: spend / plan-to age) re-run the SAME simulate() the verdict uses, patched only on moved dials so at rest sandbox % = hub % exactly; "Use as my plan" previews the exact numbers then writes through the one shared adoptPlan (revert card appears). Phone untouched (12/12 v9 pins green). 6 new desktop pins; suite 1,394 green; tsc clean; web export green. NEXT: Home two-column (glance LEFT ¦ what-needs-you + investments table RIGHT).