## How to read
What this is | The item-by-item walk you asked for on 2026-07-28: every fix proposed for Build 46, one row each, with exactly what you see today and exactly what changes. Nothing in this sheet is built until you approve its row.
How to respond | Column H on "The walk" tab is a dropdown: APPROVE FOR BUILD 46 · CHANGE — see my comment · SKIP FOR NOW. Add anything in Your comments (column I). Send the file back or just tell me row numbers.
What APPROVE means | The fix is coded with a pinning test, rides Build 46, and (per your new standing rule) gets a same-day changelog row in the design doc. Rows with a look change conform to mocks you have ALREADY approved — no new design appears anywhere in this batch.
What is NOT here | Anything needing a new picture stays at the mock gate (PARKED): the richer adoption sheet, source chips, staleness stamps, cushion card, will-it-last detail, and the rest of Group C — those arrive as mock batches, first batch coming next.
Decisions already made | The "Decided today" tab logs the 10 decisions you gave on 2026-07-28, so there is one written record.

## The walk
# | The fix | Today — what you see | After — exactly what changes | Where you will see it | Look change? | Mock status | Approve? | Your comments | Outcome (my status — kept current)
ACCURACY — the wrong-number class (your non-negotiable)
1 | Social Security odds use the reduced check | Your statement says $2,600/mo at 67. You adopt claim-at-62 → the real check is ~$1,820. The SS screen shows "74% chance" for that choice — but Home and Plan quietly keep computing with the full $2,600 and show ~79%. | Every screen says the same 74%. The adopted plan feeds the age-adjusted check into the odds everywhere. An agreement test pins Home, Plan hub, and the SS screen to one number. | Home · Plan hub · SS timing | NO | No mock needed — numbers, not layout | APPROVE FOR BUILD 46 — given verbally, 2026-07-29 ("build all 16") |  | BUILT — odds read the claim-age-adjusted check everywhere (hub = SS screen, agreement-pinned; the legacy cockpit fixed too)
2 | Unpriced holding stops showing $0 | A holding with no live price (your LCTX) shows "LCTX … $0" on the Invest list — as if it were worthless. | The row shows what you paid — "LCTX … $1,132" with the small words "what you paid" beneath. Same honest treatment its own detail page already uses. | Invest list | TINY | Matches the detail page’s approved treatment; say "show me" for a drawn row first | APPROVE FOR BUILD 46 — given verbally, 2026-07-29 ("build all 16") |  | BUILT — unpriced rows show what you paid, in words; no weight % (0% would be wrong)
3 | Insights pop-up respects hide-balances | Eye ON (balances hidden): the card says "••••" — but tap it and the pop-up reads "You can still contribute $9,200 this year" in plain dollars. | The pop-up masks like every other surface: "•••• this year". | Home insights pop-up | NO | No mock needed | APPROVE FOR BUILD 46 — given verbally, 2026-07-29 ("build all 16") |  | BUILT — the pop-up masks its title and body like every surface
TRUST — drift traps (nothing visibly broken yet)
4 | Bond/CD/alternative sales get an activity record | Sell your $10,000 CD → the balance drops but the account’s Activity shows nothing. A month later there is no way to see where $10,000 went. | A SELL row appears in Activity, exactly like stock sales already do. No layout change — rows simply start appearing in the existing, approved list. | Bond/Alt editors · Account detail | NO | Activity list already in your approved account-detail FINAL mock | APPROVE FOR BUILD 46 — given verbally, 2026-07-29 ("build all 16") |  | BUILT — bond/alternative partial sales write a SELL activity row; the ledger (not a silent patch) lowers the value
5 | One shared market-average formula | Home and Invest both say "the market: up 8.2%" from two identical copies of the formula. Edit one copy someday and the screens silently disagree. | The copies merge into one shared calculation; an agreement test pins both screens to it. Invisible today — protection for tomorrow. | Home · Invest | NO | No mock needed | APPROVE FOR BUILD 46 — given verbally, 2026-07-29 ("build all 16") |  | BUILT — one shared market-average formula behind Home and Invest, source-pinned
6 | Stock-vesting money lands in the right months | You add $24,000/yr vesting in March + September. Cash flow correctly shows $12,000 in Mar and Sep — the income engine’s year view still parks all $24,000 in December. | The December lump moves to the months it really lands; the two views agree. | Income detail vs Cash flow | NO | No mock needed | APPROVE FOR BUILD 46 — given verbally, 2026-07-29 ("build all 16") |  | BUILT — equity lands in its vest months on the income year view too; one shared placement rule, agreement-pinned
ALREADY-APPROVED PICTURES — building what your final mocks show
7 | "Your path ahead" row on Net worth | Under the trend chart today: nothing. | One calm line from your approved networth-v7 FINAL mock: "Your path ahead (from your Plan): on course for ~$310,000 by 67 ›". Building = making the app match the picture you approved. | Net worth | YES — to the approved picture | Drawn in networth-v7 FINAL (open it — you are looking at it) | APPROVE FOR BUILD 46 — given verbally, 2026-07-29 ("build all 16") |  | BUILT — the path-ahead row renders per your v7 mock; the projection number appears only when the plan is computable
8 | Net-worth grouping toggle | Only the by-class view exists. | Above the list, from the same approved mock: [By class] [By institution] [By type]. Tap "By institution" → your two E*TRADE entries roll up under one E*TRADE header. | Net worth | YES — to the approved picture | Drawn in networth-v7 FINAL | APPROVE FOR BUILD 46 — given verbally, 2026-07-29 ("build all 16") |  | BUILT — By class / By institution / By type pills; institution and type views roll whole accounts under one header
9 | Dollar-first "what needs you" line | "42% of your investable money is in one account." | "$71,000 (42%) sits in one account" — dollars first, as your approved Home mock shows. | Home | TINY | Drawn in home-v2 (approved) | APPROVE FOR BUILD 46 — given verbally, 2026-07-29 ("build all 16") |  | BUILT — dollar-first wording on cash-drag and account-concentration; the instruction became a fact
WORDS & POLISH — layouts identical
10 | Acronyms spelled out | "12.99% APR" · "YTM 4.1%" · glossary title "RMD". | "12.99% yearly interest (APR)" · "Yield to maturity: 4.1%" · "Required withdrawals (RMD)". Your standing no-acronyms rule, applied to the strays. | Budget · Bonds · glossary | TINY | Words only | APPROVE FOR BUILD 46 — given verbally, 2026-07-29 ("build all 16") |  | BUILT — yearly interest (APR), Yield to maturity, Required withdrawals (RMD)
11 | Your nest-egg explanation, letter for letter | The info-dot text drifted to wonkier phrasing than the copy you approved. | Your exact approved words restored: "…The amount shown represents the incremental wealth… An estimate, not a promise." | Look-ahead info dot | TINY | Your copy IS the approval | APPROVE FOR BUILD 46 — given verbally, 2026-07-29 ("build all 16") |  | NO CODE CHANGE NEEDED — git shows the shipped text IS your approved 2026-07-19 copy; the DESIGN DOC was stale and now carries it. Paste your original if you remember it differently.
12 | One consistent voice | Ten "estimate" chip variants; three different "trying it out" banners; Debts empty line and the old budget landing drifted from the approved sentences. | One approved wording for each. Same layouts. | Various | TINY | Approved sentences exist | APPROVE FOR BUILD 46 — given verbally, 2026-07-29 ("build all 16") |  | BUILT — one shared estimate tag component + one trying-it-out sentence on all three scenario surfaces + the approved Debts first-open line
13 | Tap targets to the 44-point rule | Some rows and links are 32–40pt tall — fingers miss them. | The same rows, a touch taller. Nothing moves or changes words. A ratchet test keeps it from regressing. | NW rows · sheet links | TINY | Spacing only | APPROVE FOR BUILD 46 — given verbally, 2026-07-29 ("build all 16") |  | BUILT — flagged rows and links raised to 44pt; a ratchet test keeps any sub-44 from returning on those surfaces
14 | Paycheck card wording | "This year $71,600" · button "See all 12 months". | "~$71,600" (it is an estimate) · "See July’s paycheck" (says what it does). | Home paycheck card | TINY | Doc-specified words | APPROVE FOR BUILD 46 — given verbally, 2026-07-29 ("build all 16") |  | BUILT — "This year ~$…" and "See July’s paycheck →" (names the current month)
15 | Masked money spoken as "hidden" | A screen reader reads "••••" aloud as dots. | It says "hidden". Spoken only; nothing visual. | App-wide | NO | No mock needed | APPROVE FOR BUILD 46 — given verbally, 2026-07-29 ("build all 16") |  | BUILT as a CLASS — spoken labels across 16 files now say "hidden"; a guard test blocks the dot characters from ever re-entering a spoken label
FROM TODAY’S DECISIONS — copy alignment
16 | Disconnect promise: one wording everywhere (your "offer the choice" decision) | The consent screen says "we delete the connection’s data" while Settings actually asks keep-or-remove — two different promises. | One promise, stated wherever disconnect appears: "Disconnect any time — you choose: keep your numbers as a by-hand account, or delete the connection’s data." (Exact copy — edit it in the comment if you want different words.) | Consent · Settings | TINY | Words only; behavior already matches | APPROVE FOR BUILD 46 — given verbally, 2026-07-29 ("build all 16") |  | BUILT — one promise in consent and Settings: you choose, keep as by-hand or delete

## Decided today (2026-07-28)
# | Decision | Your call | What happens next
1 | Build-46 fix batch | Walk me item-by-item | This workbook ("The walk" tab). Only rows you approve are built.
2 | Empty-state odds strip on Home | Sample gauge wins | The locked "Sample: 84% to age 92" gauge is the approved empty state (as built today); the 3-questions-invite mock is retired. Changelog row added.
3 | Disconnect promise | Offer the choice | Keep-as-manual or delete, user picks. Copy alignment = row 16 of the walk; the future account-page disconnect door (parked) will use the same promise.
4 | Emergency cushion card on Net worth | Build it | Goes into the first mock batch: full Net worth screen with the card drawn, both data states. Built only after you approve the picture.
5 | 17-point money floor vs dense tables | Keep approved compact sizes | Long-open question CLOSED. Dense tables stay as approved in v7; the 17pt floor keeps applying to heroes and standalone money. No change.
6 | Legacy modules in v1 (Estate, Insurance, Tax organizer, Job safety, Credit) | Keep in v1 | They stay reachable and remain rows in your 97-row launch sign-off walk — each must pass it.
7 | Chart color palettes | Adopt the validated colorblind-safe palettes | I deliver recolored mocks of every affected chart (one batch); nothing changes until you approve the pictures.
8 | Price provider (Tiingo ruled out) | I research + shortlist | One-page comparison of licensed providers (coverage, dividends/total-return, price, license terms) with a recommendation, for your approval.
9 | Group C — 23 approved-but-never-built items | Mock in batches | Parked items arrive as small mock batches; each approved picture joins the next build; each rejected one gets a doc changelog row. The already-drawn items are rows 7-9 of the walk.
10 | Doc-vs-code drift root cause | Same-day changelog rule ADOPTED | Every approval you give = a dated row in the design doc’s Changelog the same day. Written into the repo’s standing orders; today’s decisions are already logged there.