## How to read
Section | Plain English
What this file is | The desktop's living audit + findings ledger — maintained exactly like the phone's master file: every doc-vs-code audit gets a tab, every walk finding gets a row with a verified root cause and a status, every decision gets logged the day it's made.
Standing rules carried over | Mock-first (mockups/desktop/, never overwrite, supersede with v2) · same-day changelog · full-surface done with coverage lines · builds only on your literal word.

## Findings
# | Your finding | Verified root cause | Fix + coverage | Status

## Decisions log
Date | Decision | Decided by
2026-08-03 | Desktop workstream STARTED on the founder's word ("start immediately"), on the recommended path: web app first → installable wrap; big-screen redesign of the five surfaces; same gates as the phone. | Founder
2026-08-03 | Structure created: MK-desktop-PRD-v1 (derived row-by-row from the app PRD with SAME/DIFFERENT verdicts) · MK-desktop-UX-design-v1 (same derivation from the app UX file + desktop-new rules) · this audit file · mockups/desktop/. | Founder-directed
2026-08-03 | One-brain rule affirmed: desktop consumes the SAME engines, store, and navigation map as the phone — no forked math, ever; the sameness contract now spans devices. | Standing (from the app PRD)
2026-08-03 | PHASE 1 STARTED on founder's word ("start building desktop application"). Scaffolding only — no user-facing design before the mock gates. | Founder
2026-08-03 | Phase 1 milestone: the web build EXPORTS — react-native-web installed; web platform on (metro, single-page); browser dialogs stand in for phone alerts via a web-only module shim (styled sheets come with the design phase); sign-in persistence uses the browser's own storage on web; the notifications side effect is guarded; fonts fall back to the system face. Phone side verified untouched: full suite green. | Build log
2026-08-03 | Desktop mock v1 DELIVERED (mockups/desktop/shell-home-plan-desktop-v1): the sidebar shell + Home + Plan at full width — AWAITING founder verdict. Phase 2 builds nothing until it. | Awaiting founder