## Read me
WHAT THIS IS | The eight steps to a launch-ready build for Net worth, Cash flow and Performance — all three, complete. Your words, 2026-09-30: "No, I want complete launch ready build. Fast does not mean incomplete and crappy work."
EVERY STATUS IS COUNTED, NOT TYPED | Each time this runs it counts off the live files: the master calculation file, the decision log, the figure register, the five gates. No step can say DONE unless its own numbers say so. A plan that reports its own progress from memory is the thing this project keeps being burnt by.
IT IS REBUILT, NEVER EDITED | Generated by build-launch-readiness.py. A hand edit dies on the next build. Re-run it and it is current.
THE TWO STEPS THAT ARE YOURS | Step 6 — answer the open questions, on the launch answer list. Step 7 — read every row and mark it VERIFIED, in column AM of the master file. Nobody can do step 7 for you: a test proves a figure is what the code gives, never that it is the figure you wanted.
THE ORDER MATTERS IN ONE PLACE | Do not verify the cashflow tab until step 1 says DONE. Until then 19 of its rows are hand-typed, so their formulas may not be what the app does. Net worth and Performance are printed from the code today and safe to read now.

## The eight steps
Step | What has to happen | Owner | Status | Where it stands — counted, not typed | What it blocks | Where the work is done
1 | Cash flow pass 1 — every figure printed from the code, none worked out on a screen, and every figure on a cash-flow screen printed through its identifier | Claude | NOT DONE | 34 of 53 printed from the code · 19 still hand-typed (MK-CF-M-006, MK-CF-M-029, MK-CF-M-007, MK-CF-M-008…) · 1 still worked out on a screen (MK-CF-M-020) · 157 places across 12 cash-flow screens still print a figure with NO identifier (worst: CashFlowScreen.tsx 43, BudgetScreen.tsx 30, BillCalendarScreen.tsx 22) | A hand-typed row can drift from what the app does, with nothing to notice. A figure worked out on a screen has no row, no example and nothing able to check it. And a figure printed without its identifier cannot be traced from the screen to its formula, which is the master key his objective 4 asks for. THREE GENERATIONS OF THE SAME FIGURE currently sit on the cashflow tab — the pre-four-tab rows and two declared sets, with MK-CF-M-002 and MK-CF-M-049 carrying the IDENTICAL label — so the dead ones are retired first, pointing at what replaced them, before anything new is declared. | MoneyKeel/functions/cashflow/ · the master file, cashflow tab · the twelve cash-flow screens
2 | Cash flow pass 2 — a worked example on every figure, run through the real door on every build | Claude | NOT DONE | 29 of 53 carry an example a test RUNS | A figure with no worked example has nothing that re-runs it, so its row on the master file is a claim. | MoneyKeel/functions/cashflow/ · src/__tests__/worked_examples.test.ts
3 | Cash flow pass 3 — every figure shown on two screens proved to agree | Claude | NOT DONE | not started — this is the pass that found B-112 (Home 3.57% against Performance 3.69%), B-117 (the emergency-fund warning suppressed) and B-118 | A wrong number in a finance app loses trust irrecoverably, and the two screens a person moves between in one tap are where it shows. | src/__tests__/guard_d3_screens_agree.test.tsx
4 | Pass 4 on all three modules — a test that NAMES each decision and re-runs it | Claude | NOT DONE | Net worth 53 of 78 · Cash flow 25 of 42 · Performance 23 of 33 — 101 decisions have nothing that re-runs them | A decision could be broken today and nothing would go red. This is the pass that found B-116 (interest on a hand-entered CD booked under Stocks / Funds). | the decision log · one test per decision, named by its identifier
5 | Rebuild and re-verify everything — master, decision log, answer list, every gate, the full suite | Claude | NOT DONE | formula-agreement FAIL · rulings-in-file PASS · rulings-sync PASS · changelog-anchored PASS · read-from-approved PASS | The file-and-code rule: neither changes alone, and done means "file and code are both updated and they match 100%". | Calculation Module code/scripts/build-all.sh
6 | Answer the open questions | FOUNDER | NOT DONE | Net worth 13 on figures + 5 on decisions · Cash flow 0 on figures + 2 on decisions · Performance 0 on figures + 4 on decisions — 24 open | Those figures stay DRAFT: they are declared and printed, and nothing moves behind their doors until you rule. | moneykeel_calc_plan_launch-answer-list_v01.xlsx — tabs Net worth · Cash flow · Performance, column "YOUR ANSWER"
7 | Read every row and mark it VERIFIED, or say what is wrong | FOUNDER | NOT DONE | Net worth 0 of 48 · Cash flow 0 of 53 · Performance 0 of 11 — 112 rows still unread | THE HARD GATE. A test proves a figure is what the code gives; only your mark proves it is the figure you wanted. Every row carries a worked example — a real household with real numbers — so a row can be checked in a minute. | moneykeel_calc_master_calculation-master_v01.xlsx — tabs networth, cashflow, performance · COLUMN AM "ROW VERIFIED — founder, date and how"
8 | Pre-build checklist presented, and your explicit "cut the build" | Claude to present · FOUNDER to say | NOT DONE | blocked until steps 1 to 7 are DONE | Standing order since 2026-07-14: go on a plan, silence or enthusiasm is NOT build approval. Only the literal ask counts. | the checklist in chat, then EAS