## How to read
MoneyKeel — Build analysis · code vs approved documents · 2026-07-24
What this is | You asked: read the ACTUAL code — no assumptions — and compare it against the detailed design doc, the strategy & objective doc, the PRD, and the UX design doc, and list every difference. One tab per document. Every row cites the real code file so nothing here is an opinion.
How rows were made | Five independent read-only audits (one per document area) checked ~700 documented claims against source files. Every difference they flagged was then re-verified by hand before it entered this workbook. Matches are counted but not listed — only differences and unverifiable rows appear.
The classification column | CODE GAP = the doc is approved and the code differs → a fix candidate for you to prioritize. DOC STALE = you approved a later change (cited) and the doc was never updated → doc edit, not a code fix. OPEN DECISION = a decision you have not made yet — nothing is "wrong" until you decide. FOUNDER-GATED = waits on an external you hold (bank connection keys, price provider). DELIBERATE = a deviation made on purpose with the reasoning written in the code and previously surfaced.
Build status column (added 2026-07-28, extended to every tab 2026-07-29) | Your one-master-file request: EVERY tab now carries a Build status column (H on Examples & mock map, G on the five document tabs). It says for each row: PROPOSED for Build 46 (with its row in the walk workbook) · PARKED at the mock gate · NEXT WALK ROUND (no picture needed, proposed after this batch) · DECIDED (your call, dated) · OPEN (a pick still yours to make) · DOC REFRESH (paper edit only, nothing to build) · DELIVERED · NO ACTION (deliberate, founder-known deviation) · DEVICE CHECK · POST-LAUNCH. Rows that map to an action item cite it, so the tabs can never disagree. As items build I update the cells to "BUILT — Build N" the same day. This file is the master monitor; build46-item-walk-v1-2026-07-28.xlsx is just the approval form for the current batch.
Build 46 — findings tab (added 2026-07-29) | Your device-walk findings for Build 46 live HERE (one master file, your standing rule) — numbered rows with what you saw, the verified root cause, the fix and its status. I add rows as your findings arrive and update statuses the same day fixes build. The old separate feedback workbook is retired; future builds get their own findings tab the same way.

## Built — Aug 11
Area | What was asked for / what was wrong | What is built | Where it came from | Status
— NET WORTH · the Quiet Instrument rebuild —
Net worth · the whole screen | Claude Design "Quiet Instrument" handoff + the founder's 11 hero corrections | Flat continuous ledger; one shared right edge for every number; hero title carries only the info dot then the date; the trend line under the hero deleted; change line reads "Change in net worth +$X · Return on cash + investments +Y%", green at zero and up, amber only on a fall; since-line plain weight with the year. | Handoff + NW-screen.docx, 2026-08-10 | BUILT — in build 52
Net worth · the six decisions | Founder decisions on the audit workbook | Composition bar replaces the donut; What you owe gains its own bar; the cushion gains a progress bar; categories read biggest-first; the cash-flow row deleted; grouping buttons on day one. | Audit workbook "Round 2", 2026-08-11 | BUILT — in build 52
All screens · section banners | Square corners, applied everywhere | SectionBand corners squared — one component, so every banded screen changed at once. Hero and retirement plan wear the same full-width banner as WHAT YOU OWN. | Founder, 2026-08-11 | BUILT — in build 52
All screens · the money column | One size, totals bold, genuinely right-aligned | Every money figure 15pt, totals bold. AND the column was really bent: band totals sat 8 points right of row values because a row puts a gap before its arrow and a band did not. One constant now; the test MEASURES both edges instead of asserting a margin. | Founder, 2026-08-11 | BUILT — in build 52
All screens · account naming | THE naming rule | Taxable = institution + last four ("Vanguard -5738"); no digits = institution + account word; tax-advantaged = institution + wrapper + last four; duplicates get · 1 / · 2. Only real digits qualify. Recorded in the PRD (Amendments + Sameness contract). | Founder rule, 2026-08-11 | BUILT — after build 52
— CONNECTIONS · honesty —
Net worth · "Sync now" | The button did not sync — it opened a page that cannot sync | It runs the sync in place, shows "Syncing…", and reports the real count. Saying "Updated" when nothing refreshed is gone. | Founder device finding, 2026-08-11 | BUILT — after build 52
Net worth · dead connections | No way to re-log-in, and a dead link looked identical to a healthy one | Per-account sync failures are recorded; the row reads "We couldn't reach Vanguard -5738" with a RECONNECT button. An account marked connected with NO connection at the provider is recorded too, instead of ageing silently. | Founder device finding, 2026-08-11 | BUILT — after build 52
Everywhere · two dead routes | Buttons that led to screens which do not exist | First-day "Connect a brokerage" and the fix-it sheet's "Update the value" both fixed; a new guard walks every pushed route and fails on any that names no screen. | Found during the rebuild audit | BUILT — in build 52
— CLASSIFICATION · cash means cash —
Assets · the cash-only rule | Applied in the migration but NOT where data arrives | The name/ticker rule is applied at classification, so a holding synced after the migration cannot land back in Cash. Known money-market tickers (VMFXX, SPAXX, SWVXX…) are recognised when a broker sends only a symbol. | Founder correction, 2026-08-11 | BUILT — after build 52
Assets · the unexplained leftover | Counted as MORE of the biggest holding | A positive leftover is CASH — it is money the broker's total includes but its holdings do not itemise. A negative leftover stays a pricing artifact. This was the chain that turned a $500 deposit into "more CDs". | Founder question, 2026-08-11 | BUILT — after build 52
Transactions · a deposit | Had nowhere to land, so it only inflated the total | A deposit into an account that itemises holdings opens the cash sleeve and lands there; the total rises by the same amount. The sheet says so: "Lands as cash in this account." | Founder finding, 2026-08-11 | BUILT — after build 52
— THE RETIREMENT PLAN —
Net worth + Plan · the verdict | Went silent below 80% odds — a bare "See your plan" | It speaks for every computable plan and tells the truth about the ending: "to spare" only when there is something spare, otherwise "running short around age 84". The word now carries its number, in ONE wording used on Home, Net worth and Plan: "<word> — xx% odds of lasting to age abc". | Founder finding + rule, 2026-08-11 | BUILT — after build 52
Plan · the three questions | A line naming one missing answer landed on a hub, then on a 7-item checklist | NEW /plan-answers: asks what the odds are missing, prefilled with what we hold, ?focus= opens at one, shows the odds on the same screen, returns you where you came from. Home, Net worth and Plan all open it. The app had NO screen capturing age at all before this. | Founder finding, 2026-08-11 | BUILT — after build 52
Plan · what counts toward retirement | Cash and all property were excluded by default | Everything counts except the home you live in and the car you drive; a rental and a second car count. Changeable per account on the answers screen, and the person's choice always beats the default. | Founder rule, 2026-08-11 | BUILT — after build 52
Plan · the odds model | "Where do the assumptions come from?" | Volatility is MEASURED per asset class from the same long-run series as the returns (was return × 1.7). The info dot explains the whole method in plain English with every number and where to change it, and it SCROLLS — the text was previously unreadable past the fold. The full model is recorded in the PRD ("Retirement odds — assumptions", 45 rows). | Founder questions, 2026-08-11 | BUILT — after build 52
— ACCOUNT DETAIL + PERFORMANCE —
Account detail · income | Untickered income was pinned onto every holding | A holding claims income only when the source names it — no CD shows "dividends" any more. Untickered income is still counted at the account level. The activity list is newest-first, so income is no longer hidden past the cut. | Founder finding, 2026-08-11 | BUILT — after build 52
Account detail · whose fact is a row | Broker records and your own looked identical | Your rows wear "you entered this" and a pencil; broker rows read "from Vanguard" and are read-only. A correction reverses the old amount and records the new one through the one engine. The door names the date the list stops at. | Performance handoff, 2026-08-11 | BUILT — after build 52
Performance · the walks | Per-account walks skipped accounts with no itemised holdings | Every account with value gets its walk, so the parts sum to the all-accounts walk — which is titled "· ALL ACCOUNTS" as the handoff names it. | Performance handoff, 2026-08-11 | BUILT — after build 52
Performance · still open | Two items deliberately not built | Category rows tapping through to a category-detail screen (a new screen). The handoff's "/yr" stated-yield treatment for bonds and cash (a CALCULATION change — the founder's instruction was to take the UX, not the calculations). | Performance handoff, 2026-08-11 | OPEN — founder's call

## SUMMARY — read me first
# | Where (doc tab · row) | The document says | The code actually does (file evidence) | Classification | What it means for you / recommended action
1 | THE ONE-PARAGRAPH VERDICT | You asked what differs between the documents and the code. | The money math and the approved core surfaces are overwhelmingly faithful (about 640 of ~740 checked claims agree once verified). The single biggest pattern is the DOCUMENTS trailing your own later approvals — the PRD alone understates 73 built capabilities. The genuine code-side list is short but real: one accuracy bug in the flagship odds figure, a handful of honesty/consistency gaps, and a set of approved-but-unbuilt elements you should triage. | — | Read the five document tabs for the full evidence; below is the ranked action view.
2 | FIX BEFORE BUILD 46 (accuracy class) | — | 1) Social Security adoption feeds UN-REDUCED benefit into the odds (PRD tab #2 — verified twice). 2) Unpriced holding shows $0 on the invest list (Invest tab #2). 3) Insight sheet title/body escape hide-balances (PRD tab #6). | CODE GAP | All three are small fixes in the accuracy/honesty class you've declared non-negotiable. Say the word and they go into the Build-46 batch with pins.
3 | FIX SOON (trust & audit trail) | — | 4) Bond/alternative sales bypass the transaction ledger — balances change with no record (two auditors + hand-check). 5) Market-comparison math duplicated inline on two screens — one edit breaks one-number silently. 6) Equity-comp months disagree between engines. 7) The plan-adoption sheet is thinner than its approved contract (no will-it-last shift, no where-you'll-see-it, louder confirm button). | CODE GAP | None visibly broken today; every one is a drift trap. Recommend the ledger fix and the shared-helper extraction next, the adoption sheet when you prioritize it.
4 | APPROVED BUT NEVER BUILT (your triage list) | — | "Your path ahead" row on Net worth (approved in doc AND final mock) · where-the-return-came-from breakdown on Invest · source chips + grouping toggle on Net worth member rows · per-number staleness stamps · loading/offline states · pull-to-refresh · SS claim-now for ages 67-69 · goals starter examples · Roth banner/save/action-item · cash look-back comparison · matured-bond payoff banner · reduce-motion accessibility · richer merge matching · disconnect on account page. | CODE GAP | Mark each: Build-46 / post-launch / drop-and-doc. The sign-off walk is the natural place to decide.
5 | SMALL COPY & POLISH SWEEP | — | Bare acronyms (APR, YTM, RMD title) — also your own standing rule · your verbatim nest-egg info-dot copy drifted wonkier · empty-state copy drifts (Invest, Debts) · dollar-first what-needs-you items shipped percent-only · estimate chip in ~10 local variants · "trying it out" banner in 3 wordings · tap targets under spec in places. | CODE GAP | One combined sweep, mostly one-liners; I can batch it into Build 46.
6 | YOUR OPEN DECISIONS (nothing is "wrong" until you decide) | — | 17pt money floor vs dense tables · sample-gauge vs 3-questions empty strip (your two approvals conflict by date) · emergency-cushion card (doc yes, final mock dropped it) · disconnect promise: keep data vs delete data · legacy modules (estate/insurance/tax organizer) in v1 or hidden · price provider (the market hook rides an unofficial free feed) · status + allocation color palettes (validated set vs shipped set). | OPEN DECISION | Seven decisions, each unblocking a batch of rows above.
7 | DOCUMENTS TO REFRESH (code is right, paper is stale) | — | PRD capability/gap notes (73 rows) · screen-inventory build statuses (9 rows) · Plaid→SnapTrade throughout · +Expense-on-Home reversal · first-run redesign · 3-day stale rule · invest-v7 table replacing bars · top-bar chip removal · winners-table doc rows superseded by your Jul-19 mock approvals. | DOC STALE | One documentation pass restores the docs as the source of truth.
8 | THE PROCESS ROOT CAUSE | Why do the docs and app keep diverging? | At least six founder-approved changes live only as code comments or workbook rows — the design doc's own Changelog tab has 4 entries while the July marathon made dozens of approved changes. | — | Standing fix I propose: every approval you give gets a Changelog row in the design doc THE SAME DAY, alongside the mock. Then this audit never finds a stale-doc pile again.
9 | COVERAGE & METHOD | — | Five independent read-only audits over ~740 documented claims (PRD 310 rows · detailed design 290 · UX 62 · strategy 15 · lineage 98). Every reported difference was re-verified by hand before entering this workbook; four auditor claims FAILED verification and were corrected or dropped (masking works everywhere — it lives in the money formatter; the bank connection is live; Disconnect exists in Settings; three refuted rows are marked in their tabs). | — | What a code audit cannot prove (large-text survival, thumb reach, browser-handoff connection states) is flagged for your device walk.
2026-08-11 | Built — Aug 11 (this file) | The Net worth Quiet-Instrument rebuild, the founder's device findings from builds 51 and 52, and the Performance/account-detail handoff. | See the "Built — Aug 11" tab: 18 items with what was wrong, what is built and where it came from. | BUILT (build 52 + after) | Two Performance items remain open by the founder's own instruction — a category-detail screen, and the "/yr" stated-yield treatment (a calculation change).

## Build 46 — findings
# | What you saw | Verified root cause | The fix | Status
1 | Q: does import bring in dividends & interest? | Not a bug — answered: connected accounts import dividends/interest/coupons into the account Activity, the income surfaces and the tax estimate; Invest returns stay price-only until the price provider lands; the file import brings holdings only. | No fix needed. The "Dividends & interest" line on Cash flow This-month is audit item 27 (parked, mock on request). | ANSWERED
2 | Look-ahead sliders still frozen on Build 46 (second failed fix) | TWO device-only causes my simulated-touch tests could not see: (a) the screen's scroll view NATIVELY cancels the drag after a few points — refusing the termination request does not stop iOS; (b) the mid-drag touch coordinate is read relative to whatever sits under the finger and goes stale off the strip. | Slider rebuilt: claims the touch at capture, the scroll view is disabled while a finger is down (new handshake, pinned), and every move is driven by page-absolute coordinates anchored at touch-down. 11 pins incl. the scroll-stand-down behavior. RIDES BUILD 47 — device verification is yours; I will not call it fixed until your thumb says so. | FIX BUILT — verify on 47
3 | Add investment: picking Bonds / Crypto / Private equity / Hedge funds never changes the form; an added option landed under Stocks/ETFs | The sheet offers all 8 investment types as chips but the chips only switch the BENCHMARK — the form is ticker/shares/cost for everything. Verified root cause of the option case: this sheet always creates a ticker POSITION, and positions can only render in the equities bucket (options/alternatives are value-based ACCOUNTS in our model, added on their own editors with the right forms). Per the master file this screen is "complete" — the docs never asked it to adapt, which is exactly the gap your walk found: a document blind spot, not code drift. | PROPOSED: the type chips become a router — Stocks/ETFs keep the ticker form; Fixed income routes to the bond editor (face/coupon/maturity); Options/Crypto/Private equity/Hedge funds/Gold route to the alternatives editor pre-set to that type. Sheet change → per your mock-first rule I mock it before building (joining the mock batch under review). | BUILT + v2 mock delivered on your revision ask (real editors, separate fields, real Record sheet) — mockups/build47-batch1/invest-add-record-router-v2-2026-07-31.html · confirm the picture, adjust on your word · verify on 47
4 | Record-a-transaction: the account picker shows "E*Trade savings" three times + "E*Trade brokerage" once — you only uploaded one account | VERIFIED: your statement upload deliberately splits by type — LCTX became a brokerage account, and every CASH-type line on the file (money market / sweep / CD-like rows) became its OWN small account, each filed under Cash with institution E*Trade. Three cash lines → three accounts. The picker then names chips its own local way (institution first; on a name collision it appends the TYPE) instead of the shared account-naming helper the rest of the app uses — three accounts sharing institution AND type = three IDENTICAL chips. A one-concept-one-helper violation (same class as your B43 finding 9). | Fix (a): the picker adopts the shared account naming — you would see the real names (e.g. the fund name, "· 1 / · 2") instead of three clones. Proposed as Build-47 walk row 22 (conforms to the approved naming system, no new design). Check (b) FOR YOU: those three accounts may DOUBLE-COUNT money your live E*TRADE connection already reports — open Net worth → the Cash class (or the new By-institution pill) and look at their names and amounts; if they duplicate connected money, they should be deleted. Tell me what you see and I will guide or script the cleanup. | FIXED — Build-47 payload: the picker uses the shared account naming (walk row 22) · verify on 47
5 | NW → Cash shows "E*Trade Key bank CD", "E*Trade VMFXX", "E*Trade cash" — leftovers from the statement upload, alongside the SAME money inside the connected accounts | RESOLVED BY YOUR CHECK (2026-07-29): totals MATCH the broker — NO double-count. The three imported accounts (KeyBank CD, VMFXX, cash) carry money the live connection's reported balances do NOT include — the import complements the connection. KEEP all three. Design lesson captured: the future duplicate-matching fix must ASK, never auto-absorb — auto-merging here would have silently deleted real money. | No cleanup. Still queued from this finding: walk row 22 (the picker's identical "E*Trade savings" chips → shared naming) and walk row 23 (confirm before Remove). The richer duplicate-matching fix (walk row 19 scope) is now specced as ask-first. | RESOLVED — keep accounts
6 | Invest → Record a transaction only supports stocks/ETFs and cash actions (Buy / Sell / Deposit / Withdraw / Transfer / Dividend) — nothing for bonds or alternatives | VERIFIED: deliberate in the code ("cash actions apply to equity + cash accounts — never bond or alternative accounts, those aren't traded here") — bonds and alternatives transact inside their OWN screens (the Bonds and Alternatives editors, which since Build 46 write real Sell rows to the ledger). But the central Record sheet gives NO door or pointer to those flows: a bond/CD holder standing on Invest has no path from here. Same document blind spot as finding 3 — the docs designed separate flows and never asked the central sheet to route to them. | ONE fix for findings 3 + 6 together: a router. On the Add sheet, type chips route to the right editor (finding 3); on the Record sheet, a "Bond / CD / alternative" path routes to that account's own record flow. Both are the same drawing — ONE mock covering both sheets joins the batch you're reviewing. | BUILT + v2 mock delivered on your revision ask (real editors, separate fields, real Record sheet) — mockups/build47-batch1/invest-add-record-router-v2-2026-07-31.html · confirm the picture, adjust on your word · verify on 47
7 | Cash flow THIS MONTH: "In (take-home) $8,600 − Out (bills) $0 = Planned surplus $9,172" — the equation is false on its face; and the Income tab source says salary steady $5,000 | VERIFIED root cause of the false equation: the In and Out lines read the month grid, but the surplus line read a DIFFERENT engine (the plan-level savings-capacity helper) whose income basis can legitimately differ — the card printed two engines with an equals sign between them. Exactly the "two savings-capacity helpers" drift the audit flagged (Strategy tab #7), now caught making the app contradict itself on one card. | FIXED same hour: the surplus row is now COMPUTED as In − Out from the same month cell — the equals sign is earned by construction, pinned by a test that renders the card and checks the arithmetic to the dollar. Rides Build 47. The engine-level consolidation (one capacity helper) remains walk row 7. STILL OPEN: why In shows $8,600 when your only listed source is $5,000 steady — answering needs one fact from your screen (see chat). | FIXED (card) — verify on 47
8 | Income tab says "Salary — steady $5,000, take-home · monthly" but the This-month In line says $8,600 — and Salary is the ONLY source | VERIFIED: the Salary row printed the raw per-period entry and HARDCODED the words "take-home · monthly" no matter what the stored fields say. Your stored salary is almost certainly a per-period, before-tax figure (e.g. $5,000 every 2 weeks before tax ≈ $10,833/mo gross ≈ $8,600/mo after tax) — so the In line was HONEST and the sources row was the wrong number. The income pop-up always writes monthly take-home, so this salary was captured through an older path (or an earlier cloud profile) with different units. | FIXED same hour: the row now names the entered form truthfully and bridges to the SAME monthly take-home the In line uses ("before tax · every 2 weeks · ≈ $8,600/mo take-home") — pinned with a cross-tab reconciliation test. Rides Build 47. FOR YOU: confirm the stored form matches reality — if your true pay IS $5,000/mo take-home, open ＋ Set up income, re-save steady $5,000, and every number follows; if it is $5,000 per paycheck before tax, the app was right all along and now says so. | FIXED (display) — your data check
9 | Income tab note reads "Opens the steady-or-varies question. Rich editors (equity comp, rental) live in the income manager" — what does it mean, and where are these editors? Both paths show only one number | THREE verified problems in one note: (a) it is written in my internal jargon — "steady-or-varies question", "rich editors", "income manager" are code words, not app words (the menu calls that screen just "Income"); (b) it points somewhere without taking you there — no link; (c) the REAL bug: on the Income screen, the stock-vesting and rental editors open ONLY by tapping an existing "Equity comp" or "Rental property" row — and those rows render only when the amount is already above zero. Anyone who skipped them at onboarding has NO path to ever add them. That is why you saw one number and no doors. | Queued as two walk rows with exact before→after: row 24 — the note becomes plain English with a real door ("Pay from stock vesting or a rental? They have their own screen — open Income ›"); row 25 — the Income screen gains an "＋ Add an income source" path (bonus, stock vesting, rental, self-employment) so the editors are reachable for everyone, not just onboarding completers. | FIXED — Build-47 payload: plain-English note + working Income door (row 24) and the add-any-source path (row 25) · verify on 47
10 | Receipt scan reads the ACME receipt as $8.99 or $9.99 — the real bill was $4.99 | VERIFIED from your photo — three traps on one slip: (a) the true total prints as "**** BALANCE", and bare "balance" was not a total keyword (only "balance due"); (b) the savings section prints a decoy "Total 4.00" (your coupons, not your bill); (c) whenever OCR mangles the keywords, the fallback took the LARGEST safe number — the $8.99 list price. $9.99 = OCR digit noise on the same wrong pick. Same parser class as your Build-44 cash-tendered finding. | FIXED same hour in BOTH parsers (the Build-44 lesson): ranked totals — the BALANCE/amount-due class beats a bare "total"; once a savings/points section starts, bare "Total" lines stop counting; discount lines (negative) are never charges; and a payment ECHO (an amount matching what you actually paid — $4.99 on three lines) beats the largest-number fallback, so even a keyword-mangled scan lands on $4.99. Your receipt is the pinned fixture, plus a mangled-keyword variant. Rides Build 47. | FIXED — verify on 47

## Build 47 — findings
# | What you saw | Verified root cause | The fix | Status
1 | Equity-based compensation — no place to enter the stock or options symbol | VERIFIED: the equity editor captured shares, price and vest dates but never the SYMBOL — every price was hand-typed and could go stale, and the app had no way to know which company the award is in. | FIXED same hour: a "Company stock symbol (optional)" field on the editor; with a known live price, new rows start at it (editable, never forced) and the editor shows "NVDA: $423 (live)". Full automatic re-marking of grants joins the price-provider work. Rides Build 48. | FIXED — verify on 48
2 | The equity editor has no complete / done button | VERIFIED — subtle: a Done EXISTS but only as small text in the modal's top bar; from the bottom of a long vesting form with the keyboard up it is invisible. The editor came from onboarding, where the shell provided the Continue button — inside the Income screen's modal, nothing replaced it. | FIXED same hour: a full-width 48pt Done button at the BOTTOM of the form (where the work ends), with the honest note "Your changes save as you type — Done just closes." The top-bar Done stays. | FIXED — verify on 48
3 | Connected Vanguard: the class row shows Brokerage $132k, but the account page hero reads $0 and the By-institution total for Vanguard is $0. Also: tapping the Stocks/ETFs row opens the FULL account, not just the stocks | VERIFIED root cause of the $0s: Vanguard's connection reports no usable account TOTAL while the positions carry the real value — and the authority rule stored "total ?? 0". The class row looked right because portions compute from positions; everything reading the stored balance (detail hero, By-institution sums) read $0. The full-account page on tap is BY DESIGN — the account's own page with the WHAT'S-INSIDE by-type breakdown; with the hero fixed it reads correctly. | FIXED same hour: the authority rule gains an honesty fallback — when the reported total is missing or zero but the account demonstrably holds value, the balance derives from holdings (live marks, cost basis when unpriced) + options + the cash sleeve. Non-USD accounts never derive (currency guard held). A genuinely empty account stays zero; a real broker total still wins. Your Vanguard heals on its next sync (pull down on Home). Rides Build 48. If you still want tap-on-class to land on a stocks-only view rather than the account page, say so — logged as an open question. | FIXED — pull to heal · verify on 48
4 | Invest → holding detail → delete holding: an error screen shows — but the holding did get deleted | VERIFIED: the deletion itself was always correct. Deleting re-renders the page BEFORE the back-navigation finishes, so the "This holding isn't here any more" fallback flashed mid-exit and read as an error. | FIXED same hour: the delete path now exits silently — the page renders nothing during the leave, then you land back on Invest with the holding gone. The not-found screen still exists for its real case (opening a link to a holding deleted elsewhere). Rides Build 48. | FIXED — verify on 48
5 | A CD shows under Stocks/ETFs on the Invest screen | VERIFIED: only the explicit bond type code mapped to Bonds & CDs — Vanguard's brokered CD arrives without it and fell through to equities (the same positions-default class as your option finding). | FIXED same hour: fixed-income SHAPES are recognized by description too — CDs, certificates of deposit, Treasuries/T-bills, and coupon-with-maturity patterns land in Bonds & CDs (the bucket your E*TRADE CDs always used). Ticker look-alikes (MCD) are not fooled — pinned both ways. Your Vanguard heals on its next sync. Rides Build 48. | FIXED — pull to heal · verify on 48
6 | Holding-detail hero: current design disliked — should be price on top, then graph, then value / change since purchase $ and % / quantity / price, in a table | Design direction, not a bug — your spec recorded verbatim. | BUILT 2026-08-01 (founder "holding screen - approved."): the whole page now follows your order — CURRENT PRICE hero (with up/down $ and % vs the prior close, honest "last market day" wording when prices are stale), price graph with the same period chips as Invest (they drive the graph AND the market compare), then your position as a table (Current value · Change since purchase $ and % · Quantity · Price paid average). Every other section speaks the same table grammar: market compare (window words match the math — "since purchase" only when true), lots + Total paid row, Dividends & Realized in one card (zeros said plainly), sold-today tax at your own rate with the estimate sentence. Unpriced holdings (your LCTX): honest basis hero, "live pricing arrives with the price provider", sub-$2 averages keep 3 decimals ($1.132, masked when hidden), no invented sections. Edit moved to ✎ top-right. Coverage: 2 of 2 mock states built (priced + unpriced) + closed/masked/deleted states kept. 6 old pins superseded + 2 new; suite 1358 green. Rides Build 48. | BUILT — verify on 48
7 | Tapping the Stocks/ETFs slice of a mixed account should land on a stocks-only view — "that's the design and how E*TRADE worked" | HONEST CORRECTION, verified in code and docs: it never worked that way — every slice tap opened the FULL account page, for E*TRADE too; the approved docs specify the account page. The what's-inside-by-type breakdown at the top made it FEEL class-focused. Your expectation is now the direction. | APPROVED + BUILT same day: tapping a class slice of a SPLIT account opens the class-only view (portion hero, that class's holdings, "See the whole account ›" one tap up; account taps elsewhere unchanged). Pinned. Rides Build 48. | BUILT — verify on 48
8 | Holding detail → the history list shows sell price as an integer, not cents; and the button says History while the sheet says Activity | VERIFIED both: (a) the activity sheet's "@ price" line used the whole-dollar formatter — the Build-44 cents-precision rule (prices always show cents) was applied to the detail page but this sheet was missed; (b) two words for one concept — the account page and this sheet both say Activity, the button drifted to History. | FIXED same hour: prices in the activity sheet are cents-precise ($250.10, never $250), and the button now says Activity — one concept, one word, pinned. Rides Build 48. | FIXED — verify on 48
9 | Winners & Laggards: LCTX says "since you bought" but the other stocks don't — is it because they were bought over a year ago? | EXACTLY RIGHT — not a bug, the capped-returns honesty rule you approved in July: a holding bought more recently than the selected window is measured from YOUR purchase date and labeled; holdings held longer show the plain window return. The market comparison always uses the same dates as your side. | No change — answered. The ⓘ on "How these numbers work" carries your approved explanation. | ANSWERED
10 | Cash-flow Income tab: two add-income entries and a sentence explaining what a button will ask — "app is explaining something not relevant on that screen" | RIGHT — and the critique lands on my own day-old fix: I made the explanation plainer when the answer was to DELETE the explanation and merge the entries. Screens offer actions; they don't narrate them. | FIXED same hour: ONE "＋ Add income ›" entry, zero explanatory sentences — the chooser (Salary / Stock vesting / Rental / Self-employment) carries the meaning, and each choice deep-links straight into its editor. Rides Build 48. | FIXED — verify on 48
11 | Cash-flow Debts: asks min payment + due day — no mortgage end year, no actual-monthly-payment; and a personal loan due IN FULL in 5 months cannot be entered at all | VERIFIED, three layers: (a) the Cash-flow Debts editor asks fewer fields than the Net-worth debt editor (two editors drifted — the min-AND-you-pay fields exist only on Net worth); (b) NO editor captures an installment end date — the credit-card framing was applied to mortgages; (c) the due-in-full structure does not exist in the model — your 5-month balloon loan is unrepresentable, and the closest fit misstates reality as a monthly minimum. | BUILT same day (founder "approved."): ONE DebtEditorSheet now serves Net worth AND Cash flow (drifted forms deleted). Installment: real monthly payment ↔ paid-off-by, either computed from the other (a payment that only covers interest warns "never pays off"). Cards: unchanged fields. Due in full: amount + due date → ONE dated big-ticket in that month's cash flow, on the bill calendar, in "Later" if beyond the window; no monthly payment counted in DTI or cash flow, balance still counts against net worth; debt-free date = the later of plan vs lump. Coverage: 6 of 6 debt surfaces (two editors→one, cash-flow grid, bill calendar, payoff plan, DTI/monthly rollups). 20 new pins, suite 1331→1351 green. Rides Build 48. | FIXED — verify on 48
12 | Scenario analysis (Retirement) — the sliders not working on device | VERIFIED — the same class as the Build-46 What-if slider: the retirement screen had its OWN private copy of the drag code, written before the device lessons (the page's scroll steals the drag mid-gesture; the touch anchor goes stale). Tests pass because simulated touches never involve the phone's native scroll — exactly how this shipped twice. | FIXED same hour, as a class: ONE shared drag engine now exists (capture the touch, refuse hand-off, stop the page scrolling during the drag, anchor from the finger's absolute position) and BOTH sliders ride it — a guard test fails the build if any screen ever writes its own drag code again. Scenario sliders also became VoiceOver-adjustable (swipe up/down to step). Rides Build 48. | FIXED — verify on 48
13 | Retirement "Where you stand" — left box reads "IF YOU NEVER SAVE AGAIN / KEEP SAVING / on today's $162K" | RIGHT — three fragments that contradict each other. The box answers a real question (could today's money ALONE, with zero new saving, grow enough to retire on?) but the words never said it: when the answer is "no", the header said never-save-again while the verdict said keep-saving, with "on today's $162K" dangling. | FIXED same hour: each state is now one sentence. Coasting works → "Retire 68 — today's $162K alone gets there by 68". Doesn't → "Keep saving — today's $162K alone doesn't get there, even by 80". "at 5.0%/yr" became "growing at 5.0%/yr". Layout untouched. Both states pinned. Rides Build 48. | FIXED — verify on 48
14 | Invest + Net worth "by type": cash and cash equivalents is called "Savings" — call it what it is: "Cash and cash equivalents" | VERIFIED on Net worth: the By-type view grouped accounts by their account-type word, so your E*TRADE sweep account (holding the CD, the money-market fund, and cash) sat under a "Savings" header. On Invest: the code has no "Savings" group header — its type labels for cash already say "Cash", and cash accounts don't join the invest list. What you likely saw there is the account's own broker-given NAME ("E*TRADE Savings") on a row — we show broker names verbatim. If it was somewhere else, point me at it. | FIXED same hour on Net worth: in the By-type view, ALL cash-bucket account types (checking, savings, high-yield, money market, CD, cash management) now merge under ONE group: "Cash and cash equivalents" (your words), with the summed total; each account row underneath keeps its own name and source chip. One label constant in the assets domain so no screen can drift. Old "Checking-header" pin superseded, new pin added. Rides Build 48. | FIXED — verify on 48

## Examples & mock map
# | Gap (source tab) | A concrete example — before → after | Screen(s) | In a final approved mock? | Look change? | What you would actually see · my commitment | Build status — proposed vs built (added 2026-07-28; I keep this cell current)
— GROUP A · ACCURACY (candidates for Build 46) —
1 | SS adoption odds (PRD #2) | Your statement says $2,600/mo at 67. You adopt claim-at-62 → the real check is ~$1,820. The SS screen showed you "74% chance" for that choice; Home and Plan then quietly compute with the full $2,600 and show ~79%. After the fix, every screen says 74%. | Home · Plan hub · SS timing | n/a (numbers, not layout) | NO | Screens look pixel-identical — only the disagreement disappears. No mock needed; an agreement test pins all three screens to one number. | BUILT — riding Build 46 (v1.1.0 #46, CUT 2026-07-29) · pinned by tests · walk it on TestFlight
2 | Unpriced holding shows $0 (Invest #2) | Your LCTX has no live price feed yet. Invest list today: "LCTX … $0". After: "LCTX … $1,132" with the small words "what you paid" beneath — the same honest treatment its own detail page already uses. | Invest list | v7 mock shows priced rows only | TINY | One number and three small words change on an existing row. I will show you the exact row rendering before it builds if you want — say "show me" and it is in the next mock batch. | BUILT — riding Build 46 (v1.1.0 #46, CUT 2026-07-29) · pinned by tests · walk it on TestFlight
3 | Insight sheet escapes the mask (PRD #6) | Eye ON (balances hidden): the card says "••••" — but tap it and the pop-up sheet reads "You can still contribute $9,200 this year" in plain dollars. After: the sheet shows "•••• this year" like everywhere else. | Home insights pop-up | n/a | NO | Visible only when you hide balances; then it simply masks like every other surface. No mock needed. | BUILT — riding Build 46 (v1.1.0 #46, CUT 2026-07-29) · pinned by tests · walk it on TestFlight
— GROUP B · TRUST & DRIFT TRAPS (fix soon) —
4 | Bond/alt sales skip the ledger (Home·NW #20) | Sell your $10,000 CD → the balance drops, but the account's Activity shows nothing. A month later there is no way to see where $10,000 went. After: a SELL row appears in Activity, exactly like stock sales already do. | Bond/Alt editors · Account detail activity | Account-detail FINAL shows the activity list | NO | No layout change — rows simply start appearing in the existing, approved activity list. | BUILT — riding Build 46 (v1.1.0 #46, CUT 2026-07-29) · pinned by tests · walk it on TestFlight
5 | Market-average math duplicated (Strategy #5) | Home and Invest both say "the market: up 8.2%" because two identical copies of the formula exist. Edit one copy alone someday and the two screens silently disagree. The fix merges them into one shared calculation. | Home · Invest | n/a | NO | Invisible. An agreement test pins both screens to the one helper. | BUILT — riding Build 46 (v1.1.0 #46, CUT 2026-07-29) · pinned by tests · walk it on TestFlight
6 | Equity vesting months disagree (PRD #4) | You add $24,000/yr of stock vesting in March + September. Cash flow correctly shows $12,000 in Mar and $12,000 in Sep — the income engine's year view still parks all $24,000 in December. | Income detail vs Cash flow | n/a | NO | No layout change — the December lump just moves to the months it really lands. | BUILT — riding Build 46 (v1.1.0 #46, CUT 2026-07-29) · pinned by tests · walk it on TestFlight
7 | Adoption sheet thinner than contract (Design ICP #25) | Today, adopting claim-62 shows two lines ("Claim age 67 → 62 · Check $2,600 → $1,820") and a Confirm. The approved design also shows "Will my money last: 84% → 74%", "You'll see this on: Home, Plan, Cash flow", and two EQUAL-weight buttons. | The Use-this-plan sheet (all scenarios) | Not drawn in any final mock | YES | PARKED. I will mock the full sheet (rich + minimal states) and build only after your approve. | PARKED — mock first (full adoption sheet, rich + minimal states) · upcoming mock batch
— GROUP C · APPROVED BUT NEVER BUILT (your triage) —
8 | "Your path ahead" row on Net worth (Home·NW #15) | Under the trend chart, one calm line: "Your path ahead (from your Plan): on course for ~$310,000 by 67 ›". Today: nothing there. | Net worth | YES — drawn in networth-v7 FINAL | YES (to the approved picture) | The new look already exists — open networth-v7-hifi-FINAL and you are looking at it. Building = making the app match your approved mock. Zero new design. | BUILT — riding Build 46 (v1.1.0 #46, CUT 2026-07-29) · pinned by tests · walk it on TestFlight
9 | NW grouping toggle (Home·NW #13) | Above the class list: [By class] [By institution] [By type]. Tap "By institution" → your two E*TRADE entries roll up under one E*TRADE header. Today: only the class view exists. | Net worth | YES — drawn in networth-v7 FINAL | YES (to the approved picture) | Same as above: your approved mock IS the picture. No new design needed. | BUILT — riding Build 46 (v1.1.0 #46, CUT 2026-07-29) · pinned by tests · walk it on TestFlight
10 | Source chips on NW rows (Home·NW #14) | Each account row would wear a small pill: "🔗 Connected · Jul 22" / "📄 Imported · Jun 12". Today the sub-line text carries it only in the setup path. | Net worth rows | NO — not in v7 | YES | PARKED — mock first, then your call. | BUILT — source chips as approved (connected/imported/by-hand + paused amber) on NW account rows · verify on 47
11 | Return breakdown on Invest (Design ICP #3) | Under YOUR RETURN +$1,860: "price change +$1,540 · dividends +$260 · interest +$60" — adding up to the headline. | Invest | NO — not in v7 | YES | PARKED — mock first. | PARKED — mock first · mock batch
12 | Per-number staleness stamps (Home·NW #6) | E*TRADE hasn't updated for 3 days → the hero gains a line "as of Jul 21 (E*TRADE part)". | Home · Net worth | NO | YES | PARKED — mock first. | BUILT — approved with your change (left-justified, in the box) · stamp on Home + NW heroes when a connection is 3+ days old · pinned · verify on 47
13 | Loading / offline states (Home·NW #4) | Airplane mode → today the numbers just render with no hint. Approved: "We couldn't refresh just now — showing your numbers from Jul 21. [Try again]". | Home | NO | YES | PARKED — mock first (it is one banner line, but you will see it drawn). | BUILT — banner approved (real screen untouched, honest as-of time, clears on success); grey-bars skeleton REPLACED by the hydration hold per your question — device-local numbers load in a blink, so the screen simply holds for it (also kills the cold-start doors-flash) · verify on 47
14 | SS compare for ages 67-69 (Design ICP #22) | You are 68: today the compare greys out 62 and 67 as "passed" and only 70 is real — there is no "claim now" option. After: the rows become "Claim now (68): $2,710/mo" vs "Wait to 70: $3,220/mo". | SS timing | Screen pattern approved; this state not drawn | TINY | Same approved table, different rows for this age group. I will include the 68-year-old state in the next mock batch for your eyes. | BUILT — Build-47 payload (2026-07-30, founder approved all 25) · pinned · suite 1,311 green
15 | Goals starter examples (Design ICP #23) | Goals empty state today: "No goals yet — add one on the Goals screen." Approved: four grey example goals (New roof $18k · Trip $6k · Car $30k · Gift $10k) + "Add your own". | Multi-goal | NO | YES | PARKED — mock first. | PARKED — mock first · mock batch
16 | Roth banner + save + action item (Design ICP #24) | The Roth screen today has no "You're trying things out — nothing is saved" banner (every other scenario screen has it), no Save-scenario, and adopting creates no "Convert by Dec 31" item on the Plan hub. | Roth · Plan hub | Banner exists on sibling screens (approved element) | TINY-YES | The banner = the exact approved element from sibling screens (conforming). The hub action item is new — mock first for that part. | BUILT — Build-47 payload (2026-07-30, founder approved all 25) · pinned · suite 1,311 green
17 | Look-back extras (Design ICP #9) | "What if I'd put $10,000 in NVDA a year ago" exists — but no "…or left it in cash" chip, no 6-month window, no reset link, no stale-price note. | Look-back | NO | YES | PARKED — mock first. | PARKED — mock first · mock batch
18 | Matured bond banner (Design ICP #8) | Your CD matured Jun 30. Today it still sits listed as a bond with "(matured)". Approved: a banner "This CD matured — record what happened [Record payoff]". | Account detail (bonds) | NO | TINY-YES | PARKED — mock first (one banner). | BUILT — matured-bond banner as approved (dated, three outcomes; paid-out writes the ledger row) · verify on 47
19 | Bonds-only hero (Design ICP #5) | A user holding only CDs opens Invest and gets no summary at all. Approved: "Total value $84,000 · returns appear when prices or your reported return exist." | Invest | NO (mock shows priced state) | TINY-YES | PARKED — mock first (empty-state rule: you see every data state). | PARKED — mock first · mock batch (you see every data state)
20 | Invest empty state + import door (Design ICP #4) | Brand-new user: today one door ("＋ Add a holding"). Approved: the sentence + TWO doors (add by hand / import from a file). | Invest day-one | NO — v7 has no empty state | TINY-YES | PARKED — mock first. | PARKED — mock first · mock batch
21 | Reduce-motion (UX #17) | iPhone Settings → Reduce Motion ON: today the app still animates count-ups and slides. After: those users get instant, still screens. | App-wide | n/a | NO | Nothing changes for you — only for users who asked their phone for less motion. | BUILT — Build-47 payload (2026-07-30, founder approved all 25) · pinned · suite 1,311 green
22 | Disconnect on the account page (Home·NW #21) | To unlink E*TRADE today you must find Settings → connections. Approved: the account's own page carries [Disconnect] with "your numbers and history stay". | Account detail | Not drawn in account-detail FINAL | TINY-YES | PARKED — micro-mock first. Note the wording depends on your keep-vs-delete decision (Group E). | PARKED — micro-mock first · wording now decided: offer the choice (2026-07-28)
23 | Richer duplicate matching (Home·NW #18) | You import a file containing the E*TRADE account you already track. Today's match keys are coarse (institution+kind); the approved rule also matches name / last-4 / balance-within-10% and suffixes "keep both" twins. | Connect/import merge | n/a | NO | Invisible logic — just fewer duplicate-account accidents. | BUILT — Build-47 payload (2026-07-30, founder approved all 25) · pinned · suite 1,311 green
24 | Treasury kind (Home·NW #19) | Adding a T-bill today: you pick "Bond/CD" and it is treated right only if the word "treasury" is in the label. Approved: an explicit Treasury choice in the editor. | Add-account/bond editor | NO | TINY | One extra chip in an existing picker — included in the next mock batch. | PARKED — one extra chip · next mock batch
25 | Undated-value nudge (Design ICP #29) | An account whose value has no date today shows nothing. Approved: "value date unknown — confirm it once", same style as the existing "still right?" nudge. | Account detail | Same style as approved nudge | TINY | One line in the approved nudge style. | BUILT — Build-47 payload (2026-07-30, founder approved all 25) · pinned · suite 1,311 green
26 | Month switcher vs Debts tab (Design ICP #16) | Flip Cash flow back to June: This month / Income / Spending all time-travel — Debts silently keeps showing today. Either Debts respects the month or it honestly says "Debts are always current". | Cash flow · Debts tab | Mock does not address it | TINY | Your pick of the two behaviors; one is a label, the other is real month-travel. Both described, neither built until you choose. | OPEN — your pick of the two behaviors; I will bring both drawn in a mock batch
27 | Investment-income line (Design ICP #14) | THIS MONTH today: Salary $6,200. Approved: also "Dividends & interest · $310" as its own labeled line when it exists. | Cash flow · This month | NO — not in cashflow-4tabs FINAL | TINY-YES | PARKED — mock first (one line, but it changes your approved This-month card). | PARKED — mock first · mock batch (it changes the approved This-month card)
28 | Will-it-last range strip (Design ICP #13) | Strip today: "84% · estimate". Approved: "84% — holds 71-95% across bad-to-good markets". | Cash flow strip · Will-it-last | NO | TINY | A few words appended to an existing line — in the next mock batch. | PARKED — a few words, but shown drawn first · next mock batch
29 | Plan-hub small honesty rows (Design ICP #19-21) | Claim-window date badge on the SS row ("you can claim from Sep 2026") · reopened scenario shows "was 79% saved, 78% today" · Revert opens the same field-diff sheet instead of a bare alert. | Plan hub | NO | TINY-YES | PARKED — one combined micro-mock for the three. | PARKED — one combined micro-mock for the three rows
30 | Will-it-last detail depth (Design ICP #26) | Approved: a drawn band chart, ranked "what moves it most" ("spend $500 less → 89%"), a sharpen meter, inline edits. Today: text range + unranked drivers + link-outs. | Will-it-last detail | NO — never drawn hi-fi | YES (biggest) | PARKED — this is the largest unbuilt piece. Mock first, and you decide pre- vs post-launch. | PARKED — the biggest unbuilt piece · mock first; you decide pre- vs post-launch when you see it
— GROUP D · COPY & POLISH SWEEP —
31 | Bare acronyms (UX #18) | "12.99% APR" → "12.99% yearly interest (APR)" · "YTM 4.1%" → "Yield to maturity: 4.1%" · glossary title "RMD" → "Required withdrawals (RMD)". | Budget · Bonds · glossary | n/a | TINY | Words only, layouts identical. Also your standing no-acronyms rule. | BUILT — riding Build 46 (v1.1.0 #46, CUT 2026-07-29) · pinned by tests · walk it on TestFlight
32 | Nest-egg info dot verbatim (Design ICP #12) | You approved: "…The amount shown represents the incremental wealth… An estimate, not a promise." The shipped text drifted to wonkier phrasing. After: your words, letter for letter. | Look-ahead info dot | Your copy IS the approval | TINY | Restores your exact approved text. | NO CODE CHANGE NEEDED — hand-verified in git: the shipped text IS the copy you approved on 2026-07-19 (commit "Founder copy for the nest-egg info dot"). The audit compared against the design doc’s OLDER wording — the doc is what drifted, and it now carries your copy. If you remember your original differently, paste it and it lands letter for letter.
33 | Dollar-first what-needs-you (Home·NW #1) | "42% of your investable money is in one account" → "$71,000 (42%) sits in one account" — dollars first, as your approved Home mock shows. | Home | YES — home-v2 mock shows dollar-first | TINY | Conforms to your approved mock — open home-v2 and you are looking at it. | BUILT — riding Build 46 (v1.1.0 #46, CUT 2026-07-29) · pinned by tests · walk it on TestFlight
34 | Wording unifications (UX #10/#13, Design ICP #17) | Ten "estimate" chip variants → one; three "trying it out" banners → one wording; Debts empty line and /budget landing aligned to the approved sentences. | Various | Approved sentences exist | TINY | Same layouts, one consistent voice. | BUILT — riding Build 46 (v1.1.0 #46, CUT 2026-07-29) · pinned by tests · walk it on TestFlight
35 | Tap targets (UX #5) | Some rows/links are 32-40pt tall vs the 44/52 rule — fingers miss them. Fix: the same rows, a touch taller. | NW rows · sheet links | Spacing only | TINY | Nothing moves or changes words; rows get slightly taller. A ratchet test keeps it. | BUILT — riding Build 46 (v1.1.0 #46, CUT 2026-07-29) · pinned by tests · walk it on TestFlight
36 | Paycheck card details (Home·NW #10) | "This year $71,600" → "~$71,600" · button "See all 12 months" → "See July's paycheck". | Home paycheck card | Doc-specified | TINY | Words only. | BUILT — riding Build 46 (v1.1.0 #46, CUT 2026-07-29) · pinned by tests · walk it on TestFlight
37 | Masked money spoken as "hidden" (Home·NW #8) | A screen reader today reads "••••" as dots; after, it says "hidden". | App-wide | n/a | NO | Spoken only; nothing visual. | BUILT — riding Build 46 (v1.1.0 #46, CUT 2026-07-29) · pinned by tests · walk it on TestFlight
— GROUP E · YOUR OPEN DECISIONS (examples of each option) —
38 | 17pt money floor (UX #3) | Winners table RETURN column today: 10.5pt. At 17pt the same column is ~60% larger — on your approved v7 table that means fewer columns fit or rows wrap. | All dense tables | v7 tables approved at current sizes | YES if adopted | If you choose 17: I mock the affected tables FIRST so you see the wrapping trade-off before anything changes. | DECIDED 2026-07-28 — dense tables keep their approved compact sizes; nothing changes (question closed)
39 | Empty-odds strip (Home·NW #3) | Option A (your Jul-15 approval): locked gauge "Sample: 84%…". Option B (the later mock): "Answer 3 quick questions in Plan to see your odds ›". | Home | BOTH approved, dates conflict | Pick one | Both already exist as pictures — say A or B. | DECIDED 2026-07-28 — Sample gauge wins (already what the app shows); the 3-questions mock is retired · nothing to build
40 | Disconnect promise (Home·NW #17) | Option A: "Disconnect — your numbers and history stay" (doc). Option B: "Disconnect — we delete the connection's data" (shipped consent). | Consent + Settings + account page | n/a | Words + behavior | Pick the promise; copy and behavior then align everywhere. | DECIDED 2026-07-28 + COPY BUILT — Build 46: consent and Settings now state the same offer-the-choice promise (walk row 16). The account-page disconnect door stays parked (item 22).
41 | Legacy modules in v1 (Strategy #4) | Estate, Insurance, Tax organizer, Job safety, Credit are reachable today. Keep = more value, more to test (they are in your 97-row walk). Hide = tighter launch. | Menu / routes | Not in FCC docs | Pick | Either way is one small change. | DECIDED 2026-07-28 — keep in v1 · nothing to build; the five modules stay in your 97-row sign-off walk
42 | Price provider (Strategy #3) | Your "vs the market" hook rides a free unofficial feed that can break without notice. The keyed-provider seam is ready — the pick (Tiingo is ruled out) is yours. | Invest · NW history | n/a | NO | Engine only; unblocks dividends/total-return and live LCTX pricing (kills the $0 class for good). | ONE-PAGER DELIVERED — awaiting your pick · docs/FCC-core-55-70/price-provider-onepager-v1-2026-07-29.xlsx (recommend Intrinio, fallback Twelve Data Venture; your 2-minute email inside)
43 | Color palettes (UX #1-2) | Example: Cash is teal on Net worth but a different color in the Invest chart; the doc's validated palettes were never adopted. | Charts app-wide | Mocks show shipped colors | YES if adopted | If you want the validated palettes: recolored mocks first. | BUILT — validated palettes ADOPTED (your YES, 2026-07-30) · token swap, pinned exactly · mock in final/ · verify on 47
44 | Emergency cushion card (Home·NW #16) | Doc: a cushion card below the fold ("4.2 months of essentials"). Your final v7 mock dropped it, and the code never renders it. | Net worth | Absent from v7 FINAL | Pick | Say "drop" (doc edit + dead code removed) or "build" (mock first). | BUILT — cushion card as approved (3 states, math on the card); path-ahead stays its OWN card (as Build 46 — the mock drew it inside the box in error) + gained the how-ⓘ per your ask · verify on 47

## UX design v1.1
# | Where (doc tab · rule) | The document says | The code actually does (file evidence) | Classification | What it means for you / recommended action | Build status — proposed vs built (added 2026-07-29; kept current)
1 | Color · status colors | A validated 4-color status set (good green, warning amber, serious orange, critical red) with specific hex values for verdicts/scam/stale/budget states. | None of the 4 specified colors exist in the app. It uses its own amber/red families (src/utils/theme.ts:10-16) and a 5-step gauge ramp instead. | CODE GAP | The app is colorblind-safe in practice (word + icon everywhere), but the palette you validated was never adopted. Decide: adopt the doc palette, or bless the shipped one and update the doc. | BUILT — validated palettes ADOPTED (your YES, 2026-07-30) · token swap, pinned exactly · mock in final/ · verify on 47
2 | Color · allocation palette | A fixed validated 7-color set for asset-class charts (specific hexes for stocks, cash, real estate, bonds, alternatives, personal, mixed). | A different set shipped (ClassMarkColors, theme.ts:52-56); the Invest chart additionally uses a positional palette, so the same class can wear different colors on different screens. | CODE GAP | Same-class-same-color everywhere is the point of a fixed palette. Recommend unifying on ONE keyed palette (either set) — small change, real consistency win. | BUILT — validated palettes ADOPTED (your YES, 2026-07-30) · token swap, pinned exactly · mock in final/ · verify on 47
3 | Type · 17pt money floor | No money figure below 17pt outside three named dense tables. | The enforced floor is 10.5pt (type_floor_guard.test.ts:19-28); 13-14pt money appears outside the named tables (PaycheckCard.tsx:110-117, PerformanceScreen.tsx:809,830). | OPEN DECISION | This is your explicitly parked decision (17pt floor vs dense tables). Nothing enforces 17 until you decide. If you pick 17, I raise the ratchet and sweep every money size in one pass. | DECIDED 2026-07-28 — dense tables keep approved compact sizes; question closed, nothing to build (action item 38)
4 | Type · hero sizes via one component | Hero numbers render at 38/30pt through one shared AmountText component. | Heroes are local text at 26-36pt per screen (PaycheckCard.tsx:105, NetWorthScreen.tsx:768, WillItLastScreen.tsx:104); the shared component is used on one screen only. | CODE GAP | Visual drift risk, not a correctness bug. Worth one consolidation pass after launch-critical work. | BUILT — Build-47 payload (2026-07-30, founder approved all 25) · pinned · suite 1,311 green
5 | Layout · tap targets | Everything ≥44pt; list rows ≥52; primary buttons 52. | Several controls measure 32-50pt (MoneySheets.tsx:460, NetWorthScreen.tsx:761-776). | CODE GAP | A 65+ audience feels small targets. Recommend a one-pass sweep + a ratchet test so it never regresses. | BUILT — riding Build 46 (v1.1.0 #46, CUT 2026-07-29) · pinned by tests · walk it on TestFlight
6 | Charts · cash-flow month bars | Twelve slim vertical paired bars, current month bolded with a "now" marker. | Horizontal per-month rows without the now-marker (CashFlowScreen.tsx:604-625). Dated month labels are built and tested. | CODE GAP | The shipped rows are readable but not what the doc drew. Decide which you prefer — the cash-flow surface was approved later from mocks, so the DOC may be the stale one here. | OPEN — your pick, brought drawn: keep the shipped month rows (doc edit) or the doc’s paired bars with a now-marker (mock batch)
7 | Charts · donut slice labels | Every slice direct-labeled with name + percent (the mandated colorblind relief). | The ring carries no slice labels; relief is a legend + a spoken sentence (NetWorthScreen.tsx:56, 375, 819-822). | CODE GAP | Legend + spoken sentence is honest but not the mandated direct labeling. Small change if you want it. | OPEN — your pick, brought drawn: keep legend + spoken sentence (doc edit) or direct slice labels (mock batch)
8 | Charts · probability band drawn | The will-it-last 10th-90th range drawn as a soft band, never a line. | The range is words only ("range 47-92%") — no drawn strip (WillItLastScreen.tsx:63). | CODE GAP | Words are honest; the drawn band was the approved visual. Decide keep-words vs draw-band. | PARKED — the drawn band rides the will-it-last detail mock (action item 30)
9 | Charts · winners/laggards bars | Horizontal bars from a zero baseline. | Text rows with arrow + dollar + percent — no bars (PerformanceScreen.tsx:253-266). | DOC STALE | You approved the invest-v7 TABLE design on 2026-07-19 (mockups/final/invest-v7) which replaced the bar idea. The doc row predates it; the doc needs the edit, not the code. | DOC REFRESH — you approved the v7 table (2026-07-19); paper edit only, nothing to build
10 | Charts · one estimate chip | One shared outlined "estimate" chip component with one look. | About ten local variants with differing words and styles (WillItLastScreen.tsx:62, CashFlowScreen.tsx:567, HoldingDetailScreen.tsx:172). | CODE GAP | Consistency-of-honesty matters to trust. Recommend one shared chip component; mechanical change. | BUILT — riding Build 46 (v1.1.0 #46, CUT 2026-07-29) · pinned by tests · walk it on TestFlight
11 | Components · provenance chip | An emoji pill with tint on every account row; tapping opens a provenance sheet. | Rows carry a plain text stamp ("Manual · you update it", NetWorthScreen.tsx:159-163); detail screen has the fuller treatment. | CODE GAP | Shipped version is quieter than specced. Decide whether the pill + tap-sheet is still wanted. | PARKED — pill + tap-sheet rides the source-chips mock (action item 10)
12 | Components · adoption sheet equal buttons | Adopt / keep-current at equal visual weight, with a post-adopt undo bar. | Adopt is a filled button, keep is a bare text link (UseThisPlanSheet.tsx:74-77); undo lives on the Plan hub instead. | CODE GAP | The doc wanted no steering pressure on a money decision. One-line style change if you confirm. | PARKED — folded into the full adoption-sheet mock (action item 7)
13 | Components · "trying it out" banner | One wording on every scenario surface, including Roth. | Three different wordings across scenario screens; the Roth screen has no banner (SsTimingScreen.tsx:121, WhatIfScreen.tsx:85, MultiGoalScreen.tsx:92). | CODE GAP | Unify to one string constant + add the missing Roth banner. Small, real. | BUILT — riding Build 46 (v1.1.0 #46, CUT 2026-07-29) · pinned by tests · walk it on TestFlight
14 | Components · draw-order steer | Drag handles; a "see what changes" that re-runs the odds. | Deliberate deviations, written in code comments: arrow buttons because drag-only fails accessibility; the odds % is NOT re-run because the model is not order-aware and we will not fake a shift (DrawSteerSheet.tsx:5,148). | DELIBERATE | Both deviations protect honesty/accessibility and were surfaced when built. Doc should record them. | NO ACTION — deliberate, founder-known deviation (honesty/accessibility); recorded in the doc refresh
15 | Components · +Expense button on Home | The add-expense floating button on Home AND Cash flow. | Cash flow only — you reversed the Home button on 2026-07-16 (HomeScreen.tsx:448 comment). | DOC STALE | Your later decision wins; the doc needs the edit. | DOC REFRESH — your 2026-07-16 reversal wins; paper edit only
16 | Accessibility · money labels test | A UI test asserts every shared money component carries a spoken label. | The shared component sets no spoken label; screens label money per-card instead (UI.tsx:153-163). | CODE GAP | Screen-reader coverage is real but ad-hoc. Either add the label to the shared component or re-word the doc rule to match the per-card pattern. | BUILT — Build-47 payload (2026-07-30, founder approved all 25) · pinned · suite 1,311 green
17 | Accessibility · reduce-motion | The phone's reduce-motion setting disables count-ups/animations. | No reduce-motion handling exists anywhere in the app. | CODE GAP | Real accessibility gap for a 65+ audience. Moderate effort; recommend post-Build-46 but before public launch. | BUILT — Build-47 payload (2026-07-30, founder approved all 25) · pinned · suite 1,311 green
18 | Voice · no bare acronyms | Never show a bare acronym. | "APR" (BudgetScreen.tsx:753), "YTM" (BondsScreen.tsx:70), and a glossary entry titled "RMD". | CODE GAP | Also violates your standing no-acronyms rule. Quick sweep: "interest rate (APR)" spelled once, "yield to maturity", "required withdrawals (RMD)". | BUILT — riding Build 46 (v1.1.0 #46, CUT 2026-07-29) · pinned by tests · walk it on TestFlight
19 | Voice · stale-value wording | The Voice tab and the Components tab of the SAME doc specify two different sentences for the stale-value nudge. | Code matches the Components tab version (AccountDetailScreen.tsx:159). | DOC-INTERNAL | The doc disagrees with itself; pick one sentence and align the doc. | DOC REFRESH — the doc disagrees with itself; code matches the Components sentence; one-line paper fix
20 | (coverage) | 8 color rules, 7 type rules, 8 layout rules, 9 chart rules, 10 components, 10 accessibility checks, 10 voice rules checked. | Strong areas verified matching: balance masking (formatter-level + bypass scan), banned-phrase discipline, glossary info dots, keyboard machinery ratchets, tab bar. Items above are the full difference list. | — | Large-text survival, 375pt fit and thumb-reach are device-review items no code audit can prove — they belong on your device walk. | — coverage note · large-text, 375pt fit and thumb reach ride your device walk

## Design — Invest·CF·Plan
# | Where (doc tab · row) | The document says | The code actually does (file evidence) | Classification | What it means for you / recommended action | Build status — proposed vs built (added 2026-07-29; kept current)
1 | Invest · winners table depth | Winners = top 3 + bottom 1-2 ranked by contribution (weight × return). | Default shows 1 leader + 1 laggard, ranked by dollar gain; the contribution math is computed but unused (PerformanceScreen.tsx:97-113,251). | CODE GAP | Decide: keep the calmer 1+1 (then the doc gets edited) or show the 3+2 you specced. Ranking by contribution is the more meaningful ordering either way. | OPEN — your pick, brought drawn: keep the calmer 1 leader + 1 laggard (doc edit) or the doc’s 3+2 ranked by contribution (mock batch)
2 | Invest · unpriced holding shows $0 | A holding with no price never shows $0 — the row says "showing what you paid." | VERIFIED BY HAND: the invest list renders market value, which is 0 when no price exists (performance/index.ts:45, PerformanceScreen.tsx:349). The cost-basis fallback exists on the detail page only. | CODE GAP | A wrong $0 is the trust-killer class. Recommend fixing before Build 46 ships: fall back to cost basis with the honest "what you paid" word on the list row too. | BUILT — riding Build 46 (v1.1.0 #46, CUT 2026-07-29) · pinned by tests · walk it on TestFlight
3 | Invest · where-the-return-came-from | A 4-line breakdown (price change / realized / dividends / interest) summing to the headline, on the main invest screen. | Absent from the main screen; partial version on holding detail only, no interest line (HoldingDetailScreen.tsx:180-197). | CODE GAP | Meaningful transparency feature from the approved doc that never got built on the main screen. | PARKED — mock first (action item 11)
4 | Invest · empty state copy | "You haven't added any investments yet…" + two doors (add / import). | Different copy and a single "＋ Add a holding" door (PerformanceScreen.tsx:162-165). | CODE GAP | The import door matters on day one. Small fix. | PARKED — mock first (action item 20)
5 | Invest · bonds/alts-only users get no hero | Only-manual-assets still get a glance: total value + why returns need prices. | The hero renders only when priced rows exist — a bonds-only user gets no glance at all (PerformanceScreen.tsx:180). | CODE GAP | A real user state (CD-heavy 65+) that sees a half-empty screen. Worth fixing. | PARKED — mock first (action item 19)
6 | Invest · holding-detail period chip | The detail page mirrors the period selected on the main screen. | Detail hardcodes 1-year (HoldingDetailScreen.tsx:46). | CODE GAP | Mild but confusing when you switch periods. Small fix. | BUILT — Build-47 payload (2026-07-30, founder approved all 25) · pinned · suite 1,311 green
7 | Invest · concentration callout not tappable | Tapping the concentration callout scrolls to that holding. | Plain non-tappable text (PerformanceScreen.tsx:284-289). | CODE GAP | Small reach-through interaction never wired. | BUILT — Build-47 payload (2026-07-30, founder approved all 25) · pinned · suite 1,311 green
8 | Invest · matured bond banner | A matured bond invites "record what happened" with a payoff button. | Just a "(matured)" fact row; no banner or button (AccountDetailScreen.tsx:261-269). | CODE GAP | Matters for CD-heavy users; the money sits mislabeled after maturity. | BUILT — matured-bond banner as approved (dated, three outcomes; paid-out writes the ledger row) · verify on 47
9 | Invest · look-back windows & extras | Windows 6/12/24/36 months, a "cash" comparison chip, a reset link, a stale-price line. | Windows 12/24/36 only; no cash path, no reset, no freshness line (LookBackScreen.tsx:15-110, performance/lookBack.ts:32). | CODE GAP | The "what if I'd stayed in cash" comparison was a distinctive approved idea; still unbuilt. | PARKED — mock first (action item 17)
10 | Invest · tax rate on holding detail | Doc says flat 15%/24% tax estimate. | Code uses your bracket-derived personal rates — better than the doc (HoldingDetailScreen.tsx:75-76). | DOC STALE | The PRD-approved progressive-tax work (Jul 15) superseded this row. Doc edit only. | DOC REFRESH — code is better than the doc (your progressive-tax approval); paper edit only
11 | Invest · what-if gates | Only remaining gate = no accounts. | Two more honest gates exist: no earmarked accounts, and already-retired (WhatIfScreen.tsx:77-80,129). | DOC STALE | The extra gates were approved with the lookahead redesign. Doc edit. | DOC REFRESH — the extra honest gates were approved with the look-ahead redesign; paper edit only
12 | Invest · nest-egg info-dot copy | Your exact approved plain-English wording. | The glossary body drifted to wonkier phrasing ("incremental wealth generated by this additional monthly contribution…") (glossary.ts:30). | CODE GAP | Your verbatim copy was the approval. Restore it word-for-word. | NO CODE CHANGE NEEDED — hand-verified in git: the shipped text IS the copy you approved on 2026-07-19 (commit "Founder copy for the nest-egg info dot"). The audit compared against the design doc’s OLDER wording — the doc is what drifted, and it now carries your copy. If you remember your original differently, paste it and it lands letter for letter.
13 | Cash flow · will-it-last range strip | The strip shows the range ("71-95% across bad-to-good markets"). | Word + percent + "estimate," no range (CashFlowScreen.tsx:157-161). | CODE GAP | The range is the honesty device. Small copy addition. | PARKED — a few words, shown drawn first (action item 28)
14 | Cash flow · investment-income line | Dividends/interest appear as their own labeled income line. | No such line on the working-lens main (CashFlowScreen.tsx:523-575). | CODE GAP | Matters most for the 55-70 audience living partly on investment income. | PARKED — mock first (action item 27)
15 | Cash flow · steer sheet re-run | Steering shows the will-it-last percent shifting (84% → 82%). | Deliberately NOT re-run: the odds model is not order-aware, and the code refuses to fake a shift — shows lasts-to age + taxes instead (DrawSteerSheet.tsx:6-8,68-84). | DELIBERATE | Honesty deviation, surfaced when built. The doc should record it so it stops reading as a gap. | NO ACTION — deliberate honesty deviation (the odds model is not order-aware); recorded in the doc refresh
16 | Cash flow · month switcher vs Debts tab | The month switcher steers all four tabs. | The Debts tab (embedded) ignores it; month bars open month-detail instead of moving the switcher (CashFlowScreen.tsx:137-147). | CODE GAP | Debts is genuinely month-less today; either wire it or say so on the tab. | OPEN — your pick of the two behaviors, brought drawn (action item 26)
17 | Cash flow · +Expense on Home | The quick-add expense button lives on Home AND Cash flow (and the inventory tab claims it is built). | Cash flow only; Home has none — you reversed Home on 2026-07-16 (HomeScreen.tsx comment). | DOC STALE | Your later decision wins, but the doc claims it in TWO places (spec + build-status) — both need the edit. Flagging because the status column asserting "built" for something absent is exactly the doc-vs-truth risk you called out. | DOC REFRESH — your 2026-07-16 reversal wins, in both places the doc claims it; paper edit only
18 | Cash flow · small copy drifts | Debts first-open: "…if that's true, it's all yours"; /budget redirect lands on Spending. | Different empty-state sentence (BudgetScreen.tsx:733-734); redirect lands on This month. | CODE GAP | Two 1-line fixes; the redirect landing is defensible — your call. | BUILT — riding Build 46 (v1.1.0 #46, CUT 2026-07-29) · pinned by tests · walk it on TestFlight
19 | Plan · SS claim-window on the hub row | The hub decision row carries the claim-window date badge. | Generic sub-line only; the date lives on the detail screen + a Home insight (PlanHubScreen.tsx:98). | CODE GAP | Small; the date is the hook that makes the row feel personal. | PARKED — one combined micro-mock for the three Plan-hub rows (action item 29)
20 | Plan · reopened scenario honesty | Reopening a saved scenario shows "was 79% when saved, 78% today." | Shows the saved number only, and routes to the legacy cockpit (PlanHubScreen.tsx:120-123). | CODE GAP | The was/now contrast is an honesty feature worth building. | PARKED — same combined micro-mock (action item 29)
21 | Plan · revert diff | Revert opens the same sheet with the reverse field-by-field diff. | A plain OS alert with one sentence (PlanHubScreen.tsx:54-61). | CODE GAP | Symmetry of consent: reverting deserves the same clarity as adopting. | PARKED — same combined micro-mock (action item 29)
22 | Plan · SS ages 67-69 case | Someone past 67 sees compare re-centered on claim-NOW vs 70. | Re-centering only kicks in past 70; a 68-year-old sees greyed "passed" columns and no claim-now row (SsTimingScreen.tsx:50). | CODE GAP | Real cohort in your 55-70 target. Recommend fixing. | BUILT — Build-47 payload (2026-07-30, founder approved all 25) · pinned · suite 1,311 green
23 | Plan · goals empty state | Four gray starter example goals + "add your own." | A sentence pointing to the Goals screen (MultiGoalScreen.tsx:97-102). | CODE GAP | Starter examples teach the feature; small build. | PARKED — mock first (action item 15)
24 | Plan · Roth screen gaps | Save-scenario + trying-it-out banner + a dated Dec-31 action item on the hub after adoption. | None of the three exist (RothScreen.tsx); the April tax pin DOES hold. | CODE GAP | The banner is also a UX-doc rule; the action item is the follow-through that makes adoption real. | BUILT — Build-47 payload (2026-07-30, founder approved all 25) · pinned · suite 1,311 green
25 | Plan · adoption sheet contract | The sheet shows the will-it-last shift + a "where you'll see it" list + equal-weight buttons + a confirmation toast. | Field diffs only; confirm is visually louder than cancel; no shift, no list, no toast (UseThisPlanSheet.tsx:28-58). | CODE GAP | This sheet is the app's biggest consent moment and it is thinner than its approved contract. Recommend prioritizing. | PARKED — full adoption-sheet mock, rich + minimal states (action item 7)
26 | Plan · will-it-last detail depth | A drawn 3-line band chart, ranked what-moves-it-most with deltas, a sharpen meter, inline edit preview. | Text range, unranked drivers, links out instead of inline (WillItLastScreen.tsx:45-92). | CODE GAP | The flagship "honest odds" screen shipped at half its approved depth. Decide how much to build pre- vs post-launch. | PARKED — the biggest unbuilt piece; mock first, you decide pre- vs post-launch when you see it (action item 30)
27 | Inventory · 9 stale build statuses | Nine rows still say "not built / pending." | All nine are fully built and routed (holding detail, connect flow, bill calendar, steer sheet, Roth adoption, required withdrawals, add-account, Home doors, Invest shell). | DOC STALE | Code is AHEAD of the doc. The status column needs one refresh pass. | DOC REFRESH — code is ahead of the doc; the nine statuses get one refresh pass
28 | Engines · concentration double-fire | When holding-level and account-level concentration both fire, never two callouts. | Both can fire together — no suppression (insights/index.ts:69-71). | CODE GAP | One-line suppression rule. | BUILT — Build-47 payload (2026-07-30, founder approved all 25) · pinned · suite 1,311 green
29 | Engines · undated-value nudge | A value with no date gets "value date unknown — confirm it once." | Undated values simply show nothing (assets/index.ts:90-97). | CODE GAP | Quiet data-quality hole; small fix. | BUILT — Build-47 payload (2026-07-30, founder approved all 25) · pinned · suite 1,311 green
30 | (verification note) | The auditor also claimed hide-balances fails to mask the embedded Budget bodies and the monthly-income total. | REFUTED BY HAND: masking lives inside the base money formatter itself (domain/_shared/money.ts BALANCE_MASK + formatMoney), which every money() call inherits — those screens DO mask. | — | Included so you know the audit was checked, not just collected. Claims that failed verification were dropped. | — audit-integrity note · claim refuted by hand-check, nothing to build
31 | (coverage) | Invest 62 rows · Cash flow 67 · Plan 61 · Screen inventory 40 · New engines 13 checked. | Matches: 42 · 54 · 51 · 30 · 9. The approved core all verified: capped returns exactly as approved, 4-tab surface, income pop-up frames, paycheck hero, bill calendar v2, SSA factor table, multi-goal weigher. | — | Differences listed above are the complete set that survived verification. | — coverage note

## Design — Home·Net worth
# | Where (doc tab · row) | The document says | The code actually does (file evidence) | Classification | What it means for you / recommended action | Build status — proposed vs built (added 2026-07-29; kept current)
1 | Home · what-needs-you items percent-only | Items are dollar-first facts: "$18,400 cash earning about $0", "$353,800 (42%) sits in one account" — the approved mock shows the same. | Two items ship percent-only with no dollars, and one is worded as an instruction (insights/index.ts:67,71). | CODE GAP | Dollar-first was the approved persuasion device and one item breaks the facts-never-instructions rule. Small copy/math fix, real impact. | BUILT — riding Build 46 (v1.1.0 #46, CUT 2026-07-29) · pinned by tests · walk it on TestFlight
2 | Home · stored-vs-recomputed odds | Home READS the stored retirement odds, never recomputes. | Home recomputes live through the one shared seeded selector — same number as Plan, guaranteed by the shared code path (HomeScreen.tsx:159-162). | DOC STALE | The shared-selector approach is stronger than the doc's (numbers can never disagree). Doc edit. | DOC REFRESH — code is stronger than the doc (one shared selector); paper edit only
3 | Home · empty-odds strip | Empty strip: "Answer 3 quick questions in Plan to see your odds." | The locked "Sample: 84%…" gauge you approved in the 2026-07-15 design round (in-code approval comment) — but the FINAL mock, dated later, shows the doc copy. | OPEN DECISION | Your two approvals conflict by date. Pick one: sample gauge or the 3-questions line; I align the loser. | DECIDED 2026-07-28 — Sample gauge wins; the 3-questions mock is retired; nothing to build (action item 39)
4 | Home · loading & offline states | Grey placeholder bars while loading; an offline line "couldn't refresh — showing numbers from Jun 30 [Try again]". | Neither exists; numbers render straight from the stored data with no refresh-failed state anywhere. | CODE GAP | Honesty gap when the network is down — the user can't tell fresh from stale. Recommend before public beta. | BUILT — banner approved (real screen untouched, honest as-of time, clears on success); grey-bars skeleton REPLACED by the hydration hold per your question — device-local numbers load in a blink, so the screen simply holds for it (also kills the cold-start doors-flash) · verify on 47
5 | Home · stale-connection rule | Stale after 48 hours; the line opens the re-link flow. | Stale after 3 days, opens the Net worth tab; a separate re-link line exists for disabled connections (HomeScreen.tsx:314-327). | DOC STALE | The 3-day rule was your 2026-07-15 approval. Doc edit; keep the code. | DOC REFRESH — the 3-day rule was your 2026-07-15 approval; paper edit only
6 | Home · per-number staleness stamps | "as of Jun 27 (Chase part)" stamps on every number a stale connection affects + a tap explainer. | No per-number stamps; only the price-freshness line on the hero (HomeScreen.tsx:291-293). | CODE GAP | The per-number honesty stamps were a distinctive approved idea; unbuilt. | BUILT — approved with your change (left-justified, in the box) · stamp on Home + NW heroes when a connection is 3+ days old · pinned · verify on 47
7 | Home · hidden-balances banner | The "Balances hidden — tap the eye" banner shows on all five tabs. | Home only (single hit repo-wide, HomeScreen.tsx:250-252). | CODE GAP | Four one-line additions. | BUILT — Build-47 payload (2026-07-30, founder approved all 25) · pinned · suite 1,311 green
8 | Home · masked values spoken as "hidden" | Screen readers announce masked money as "hidden." | Labels embed the literal dot characters instead (useMoney.ts). | CODE GAP | One-line accessibility fix in the shared helper. | BUILT — riding Build 46 (v1.1.0 #46, CUT 2026-07-29) · pinned by tests · walk it on TestFlight
9 | Home · empty-Home doors | Exactly two doors (connect "Takes about 2 minutes" + add-by-hand into the add flow). | Three-four doors including Import; the 2-minutes line dropped; add-by-hand lands on the Net worth tab; the import door's "nothing is uploaded" contradicts the approved import honesty wording elsewhere (HomeScreen.tsx:199-224). | CODE GAP | The import door itself is right (you approved it post-doc) — but the wording contradiction and the landing spot need cleanup. | BUILT — Build-47 payload (2026-07-30, founder approved all 25) · pinned · suite 1,311 green
10 | Home · paycheck card details | "This year ~$71,600" with the ~; button "See July's paycheck"; hero tappable. | No tilde; link reads "See all 12 months →"; card not tappable (PaycheckCard.tsx:65-72). | CODE GAP | Three small conformance details. | BUILT — riding Build 46 (v1.1.0 #46, CUT 2026-07-29) · pinned by tests · walk it on TestFlight
11 | Home · first-run copy | "Welcome to FinWise", 3 intents, per the wireframe. | MoneyKeel brand + your 2026-07-15 redesigned intro with 4 intents (FirstRunScreen.tsx, in-code approval comment). | DOC STALE | Your later redesign wins. Doc edit. | DOC REFRESH — your 2026-07-15 first-run redesign wins; paper edit only
12 | Home+NW · pull-to-refresh | Pull-to-refresh on both tabs. | Neither screen has it; prices refresh on mount only. | CODE GAP | Standard-expectation gap; small build. | BUILT — Build-47 payload (2026-07-30, founder approved all 25) · pinned · suite 1,311 green
13 | NW · grouping toggle in the main view | The main expanded view offers By class / By institution / By type, with wrapper tags like "· 401(k)" — the approved v7 FINAL mock shows the toggle. | The main view has expand/collapse per class only; the toggle exists in the guided-setup path alone (NetWorthScreen.tsx:371-507 vs 212-218). | CODE GAP | A mock-approved element missing from the screen it was approved for. Decide: build the toggle or simplify the mock. | BUILT — riding Build 46 (v1.1.0 #46, CUT 2026-07-29) · pinned by tests · walk it on TestFlight
14 | NW · source chips on rows | Every account row carries its source chip + last-updated; a paused connection shows amber + Fix. | The class-member rows carry neither; chips live in the setup path and on account detail; no paused state exists (NetWorthScreen.tsx:442-452). | CODE GAP | Provenance-at-a-glance was a core FCC trust idea. Recommend building on the member rows. | BUILT — source chips as approved (connected/imported/by-hand + paused amber) on NW account rows · verify on 47
15 | NW · "Your path ahead" row | A projection row under the trend ("from your Plan") — in the doc AND the approved v7 FINAL mock. | Not rendered anywhere; the projection engine exists but nothing on Net worth calls it. | CODE GAP | Approved twice (doc + final mock), never built. High-visibility gap. | BUILT — riding Build 46 (v1.1.0 #46, CUT 2026-07-29) · pinned by tests · walk it on TestFlight
16 | NW · emergency cushion card | A cushion card below the fold. | Computed but never rendered — orphaned styles remain (NetWorthScreen.tsx:109-111, 798). Absent from the final mock too. | OPEN DECISION | Doc says yes, your final mock dropped it. Say keep-dropped (doc edit + dead code removed) or build it. | BUILT — cushion card as approved (3 states, math on the card); path-ahead stays its OWN card (as Build 46 — the mock drew it inside the box in error) + gained the how-ⓘ per your ask · verify on 47
17 | NW · connect flow branding & consent | "Continue with Plaid", Plaid institutions, consent ends "disconnect any time and keep your numbers." | Provider is SnapTrade (your decision, live and working); consent honestly adds the trading-access line but says disconnecting DELETES the connection's data (sync/index.ts CONSENT_COPY). | DOC STALE + OPEN DECISION | Plaid→SnapTrade is a doc edit. But keep-vs-delete on disconnect is a real product promise difference — pick the promise, then copy and behavior align. | DECIDED 2026-07-28 + COPY BUILT — Build 46: consent and Settings now state the same offer-the-choice promise (walk row 16). The account-page disconnect door stays parked (item 22).
18 | NW · merge matching rules | Match on institution AND (name similarity OR last-4 OR balance within 10%); "keep both" suffixes last-4. | Simpler keys: institution+kind in sandbox, provider-id in live; button always "Track N accounts" (ConnectFlowScreen.tsx:56-58, sync/ingest.ts:52-62). | CODE GAP | The richer matching prevents duplicate-account messes at scale. Fine for beta; build before broad launch. | BUILT — Build-47 payload (2026-07-30, founder approved all 25) · pinned · suite 1,311 green
19 | NW · bond/treasury kind | A treasury kind exists in the account-kind list with an editor toggle. | No treasury kind; T-bills detected by label pattern only (assets/index.ts:176-185). | CODE GAP | Works by accident of labeling; the explicit kind is sturdier. | PARKED — one extra chip, next mock batch (action item 24)
20 | NW · bond & alt sale audit trail | Buy/sell on bonds and alternatives write real ledger entries (BUY/SELL/COUPON) via the one transaction recorder. | Sales still silently patch the balance — zero ledger rows (BondsScreen.tsx:129-150, OtherInvestmentsScreen.tsx:95-110). Two independent auditors confirmed. | CODE GAP | The audit-trail promise ("all classes write one ledger") is broken for two asset classes. Recommend prioritizing — it is also why matured/sold money can drift unexplained. | BUILT — riding Build 46 (v1.1.0 #46, CUT 2026-07-29) · pinned by tests · walk it on TestFlight
21 | NW · disconnect control | Account detail offers [Disconnect] with "your numbers and history stay." | CORRECTED AFTER HAND-CHECK: Disconnect exists — in Settings, with a real unlink call (SettingsScreen.tsx:76-83) — but not on the account's own detail page where the doc placed it, and without the "your numbers and history stay" promise wording. | CODE GAP (partial) | Add the same control to account detail (or a pointer to Settings), and align the wording with whichever disconnect promise you pick (see consent row). | PARKED — micro-mock first; wording now decided: offer the choice (action item 22)
22 | NW · value-as-of in bond/alt editors | The editors show "value as of" + the 6-month staleness nudge; rows wear a stale tag. | The nudge exists on account detail only; those editors neither show nor stamp the date (AccountDetailScreen.tsx:157-172). | CODE GAP | The stamp exists at 3 of the 5 places it should. Finish the sweep. | BUILT — Build-47 payload (2026-07-30, founder approved all 25) · pinned · suite 1,311 green
23 | (coverage) | Home: 60 rows checked, 34 match. Net worth: 55 rows checked, 33 match. | Mock-sanctioned deviations counted as matches (daily-snapshot trend, expand-in-place). Two connection-state copy rows unverifiable in code (browser handoff) — belong on the device walk. | — | Also: at least 6 founder-approved deviations live only as code comments, never logged in the doc's Changelog tab — that is WHY the doc and app keep diverging. Recommend: every approval gets a changelog row, same day. | — context/coverage row · nothing to build

## Strategy & data lineage
# | Where (doc tab · row) | The document says | The code actually does (file evidence) | Classification | What it means for you / recommended action | Build status — proposed vs built (added 2026-07-29; kept current)
1 | Strategy · bank connection | The one big new capability v1 depends on. | DELIVERED AND LIVE — SnapTrade relay deployed, the relay address ships in the app config, and your own E*TRADE connection proved it end-to-end. (The auditor flagged it inactive; I corrected this — the config wiring commit and your live connection are the evidence.) | DELIVERED | Remaining gated pieces: Fidelity application, plan upgrade before beta, Teller/banks for checking-account coverage. | DELIVERED — live and verified; remaining founder-gated: Fidelity application, plan upgrade before beta
2 | Strategy · "your data stays yours" | Privacy positioning. | The consent honestly says data flows through the connection service read-only and is deletable (sync/index.ts:77-85) — a relay, not local-only. | DELIVERED (nuanced) | The in-app copy is honest. Make sure marketing copy matches the same honest framing, never "we never see your data." | DELIVERED — in-app copy is honest; keep marketing copy to the same standard (your side, when written)
3 | Strategy · market-comparison hook | "How you're doing against the market" is the weekly habit hook. | Works today on an unofficial free price feed (marketData.ts:25); the keyed-provider seam is ready but the provider decision is open. | FOUNDER-GATED | The core hook rides an endpoint that can break without notice. The price-provider decision is the highest-leverage open external. | ONE-PAGER DELIVERED — awaiting your pick · docs/FCC-core-55-70/price-provider-onepager-v1-2026-07-29.xlsx (recommend Intrinio, fallback Twelve Data Venture; your 2-minute email inside)
4 | Strategy · out-of-scope surfaces still shipped | Estate, insurance, deep tax organizer are out of scope for v1. | The pre-FCC screens still exist and are routed (app/estate.tsx, insurance.tsx, tax-organizer.tsx, itemize.tsx, jobsafety.tsx, credit.tsx). | OPEN DECISION | Keep them (extra value, review burden) or hide them for launch (focus, less to test). 97-row sign-off includes them either way — your call. | DECIDED 2026-07-28 — keep in v1; the five modules stay in your 97-row sign-off walk (action item 41)
5 | Lineage · market average duplicated | The market-comparison number comes from one shared helper. | Identical formula pasted inline in BOTH Home and Invest (HomeScreen.tsx:151-155, PerformanceScreen.tsx:72-74). Two auditors confirmed. | CODE GAP | Values agree today because the copies match. One edit to one copy breaks your one-number rule silently. Extract the helper + agreement pin. | BUILT — riding Build 46 (v1.1.0 #46, CUT 2026-07-29) · pinned by tests · walk it on TestFlight
6 | Lineage · Roth math orphaned | The Roth screen computes its tax-now via the shared rothConversion helper. | The screen does its own inline marginal-tax math; the helper has zero callers (RothScreen.tsx:46). | CODE GAP | Same one-number risk. Either wire the helper or delete it — an orphaned duplicate concept is a trap. | BUILT — Build-47 payload (2026-07-30, founder approved all 25) · pinned · suite 1,311 green
7 | Lineage · two savings-capacity helpers | One capacity concept. | Goals uses one helper, multi-goal/cash-flow another; they coexist (GoalsScreen.tsx:37 vs MultiGoalScreen.tsx:58). | CODE GAP | Consolidate to one before they drift. | BUILT — Build-47 payload (2026-07-30, founder approved all 25) · pinned · suite 1,311 green
8 | Lineage · scenario-diff hand-built | A shared diff helper feeds the adoption sheet. | Each screen hand-builds its diff rows; adopt/revert/history machinery IS shared (useStore.ts:783-791). | CODE GAP | Consolidation candidate — becomes urgent when the adoption sheet is upgraded (see Plan tab). | PARKED — rides the adoption-sheet rebuild (action item 7)
9 | Lineage · source-chip wording ×3 | One shared source-chip component. | Three inline variants with diverging wording (NetWorthScreen.tsx:159-161 vs AccountDetailScreen.tsx:60 vs SettingsScreen.tsx:417). | CODE GAP | Same fix class as the estimate chip: one component, one wording. | BUILT — Build-47 payload (2026-07-30, founder approved all 25) · pinned · suite 1,311 green
10 | Lineage · RMD growth math | Future-year required withdrawals use the shared projection engine. | The schedule grows balances by its own rule instead (decumulation/index.ts:47-59). | CODE GAP | Minor divergence risk between the RMD table and other projections; align when touched next. | BUILT — Build-47 payload (2026-07-30, founder approved all 25) · pinned · suite 1,311 green
11 | (coverage) | Strategy: 15 commitments checked, 11 delivered as promised. Lineage: 98 rows checked, 78 verified — the named helper really feeds the named screen. | Verified delivered: scenarios suite, confidence engine, quantified non-advice nudges, multi-goal in v1, milestones, estimate labeling, zero advice language, no parent-sharing (correctly cut). | — | The one-concept-one-helper rule holds on 78 of 98 rows; the exceptions above are the complete list. | — context/coverage row · nothing to build

## PRD v1.1
# | Where (doc tab · row) | The document says | The code actually does (file evidence) | Classification | What it means for you / recommended action | Build status — proposed vs built (added 2026-07-29; kept current)
1 | THE HEADLINE PATTERN | The PRD is dated Jul 1 and marks ~75 capabilities as gaps, partial, or missing. | 73 of those 75 are now FULLY BUILT — the July marathon closed them: bank sync + provenance + merge, the per-month paycheck engine, dated bills + rolling grid, progressive per-month tax with filing status + state, actuarial Social Security compare, steerable withdrawal order with the RMD-first legal guard, required-withdrawal schedule feeding the odds, money-weighted returns from the ledger, look-back, multi-goal weigher + commitments, scam flags with dismiss/snooze, typed history, scenario adopt/revert. | DOC STALE | The PRD massively UNDERSTATES the product. One refresh pass brings it true. The rows below are the only genuine code-side differences that survived verification. | DOC REFRESH — one pass updates the 73 built rows; nothing to build
2 | Sameness · SS adoption odds (VERIFIED BY HAND) | One number everywhere: adopting a plan updates the whole app consistently. | Adopting a claim age stores both the raw statement and the age-adjusted check — but the odds engine reads the RAW amount and never applies the reduction (willItLast.ts:67,91; the simulator delays the benefit to the claim age but uses it unreduced, retirement/index.ts:144,169). The SS screen's own comparison DID apply the reduction. | CODE GAP — TOP FINDING | Adopt claim-at-62 and the hub's odds come out quietly HIGHER than the number you chose from — an optimistic cross-screen disagreement in the flagship figure. Recommend fixing before Build 46; one-line engine change + an agreement pin. | BUILT — riding Build 46 (v1.1.0 #46, CUT 2026-07-29) · pinned by tests · walk it on TestFlight
3 | Sameness · net-worth on three surfaces | The identical net-worth figure shows on Home, the top bar, and Net worth. | The top-bar chip was removed in the approved top-bar redesign; the two remaining surfaces share one helper (TopBar.tsx, HomeScreen.tsx:117, NetWorthScreen.tsx:112). | DOC STALE | Doc edit; the two-surface agreement is intact. | DOC REFRESH — the top-bar chip was removed in an approved redesign; paper edit only
4 | Sameness · equity-comp month placement | All grids place lumpy income identically. | Bonus and one-time now agree via the landing-month field — but EQUITY comp still lands in December in one engine and in its vest months in another (income/onboarding.ts:245 vs incomeMonthlyGrid:401-414). | CODE GAP | A user with vesting stock sees different month shapes on different screens. Finish the landing-month unification for equity. | BUILT — riding Build 46 (v1.1.0 #46, CUT 2026-07-29) · pinned by tests · walk it on TestFlight
5 | Sameness · two expected-return figures | One expected-return concept. | The snapshot still carries its own average-target-return alongside the live helper (snapshot.ts:93) — the doc flagged this and it remains. | CODE GAP | Known duality, still open. Consolidate when the snapshot is next touched. | BUILT — Build-47 payload (2026-07-30, founder approved all 25) · pinned · suite 1,311 green
6 | Insights · masking hole (VERIFIED BY HAND) | Hide-balances masks every money figure. | The insight drill-down sheet masks its detail rows but renders the TITLE and BODY unmasked — and several titles carry dollar figures (InsightsScreen.tssx sheet block: title/body lack the masker the detail rows use). | CODE GAP | Small hole in your mask-everything rule; two-line fix. | BUILT — riding Build 46 (v1.1.0 #46, CUT 2026-07-29) · pinned by tests · walk it on TestFlight
7 | Insights · plan-incomplete nudge | Fires whenever the plan is under 100% complete. | Renamed and additionally gated on a non-empty next-step, so it can stay silent when the doc says it should fire (insights/index.ts:81). | CODE GAP (minor) | Confirm the extra gate is wanted; otherwise remove it. | OPEN — quick call: keep the extra gate (the nudge stays quiet more often) or remove it (fires whenever the plan is incomplete)
8 | Insights · RMD card vs taken | The required-withdrawal nudge reflects reality. | The dedicated screen tracks taken-vs-due properly; the Insights card does not check whether the withdrawal was already taken (InsightsScreen.tsx:72). | CODE GAP (minor) | Wire the same taken check into the card. | BUILT — Build-47 payload (2026-07-30, founder approved all 25) · pinned · suite 1,311 green
9 | Transactions · flag coverage | Outlier / new-payee / duplicate flags on transactions. | Unusually-large, first-time-payee and odd-pattern rules exist — connected transactions only, and no explicit duplicate-charge rule (transactions/flags.ts:69-144). | CODE GAP (minor) | Duplicate detection and manual-entry coverage are the two missing slices; fine for beta, note for later. | BUILT — Build-47 payload (2026-07-30, founder approved all 25) · pinned · suite 1,311 green
10 | Capability map · scenarios module | One reusable scenarios engine. | Composed across three well-tested pieces instead of one module; behavior delivered, architecture differs. | DOC STALE | Accept the composed shape; doc edit. | DOC REFRESH — accept the composed engine shape; paper edit only
11 | Capability map · legacy savings/investments cleanup | Update/delete actions for the legacy entry types. | Ledger reversal exists; the legacy arrays remain without update/delete actions (useStore.ts:224-225). | CODE GAP (minor) | Post-launch cleanup with the planned legacy-migration removal. | POST-LAUNCH — rides the planned legacy-migration removal (pre-approved deferral)
12 | Capability map · unit-normalization migration | A migration normalizes legacy debt interest-rate units. | No migration code found; legacy debts only migrate on a screen mount. | CANNOT VERIFY | Belongs on a device check with a legacy account, or accept the mount-time migration as the mechanism. | DEVICE CHECK — verify with a legacy account on your device walk (or accept the mount-time migration)
13 | Contribution room · HSA | Contribution-room math covers the accounts. | The HSA line still uses a hard-coded zero (ContributionRoomScreen.tsx:74) — the doc itself flagged this and it remains. | CODE GAP (minor) | Small honest gap; either wire the real limit or label it. | BUILT — Build-47 payload (2026-07-30, founder approved all 25) · pinned · suite 1,311 green
14 | (coverage) | Acceptance criteria 180 rows · Sameness 12 · Calculation catalog 92 · Capability map 26 — all checked. | Matches: 105 · 7 · 59 · 1, and 73 "gap" rows verified BUILT. Formulas, rounding and edge cases of the calculation catalog verified against the cited helpers. | — | Every difference that survived verification is listed above; everything else agrees. | — context/coverage row · nothing to build

## Build 47 — plan
Order | What | Which items (this file) | How it gets approved / what you will see | Status
1 | Your Build-46 device walk | Whatever you find — five suggested first checks: Net worth path-ahead row + grouping pills, Social-Security odds agreement, base-salary pop-up typing, bond partial-sale activity row, VoiceOver saying "hidden" | Findings go in the feedback workbook as always; fixes are always the FIRST thing in the next batch | WAITING ON THE BUILD — then you
2 | Mock batch 1 (pictures for approval) | Cushion card on Net worth (item 44) · recolored chart palettes (item 43) · first parked micro-mocks: source chips (10), staleness stamps (12), loading/offline banner (13), matured-bond banner (18) | Full-screen pictures per the mock rules (rich + empty states, numbers add up); each picture you approve joins Build 47, each you reject gets a doc changelog row | DELIVERED 2026-07-29 — 6 mocks in mockups/build47-batch1/ · awaiting your verdicts
3 | Build-47 walk (no new pictures needed) | The ~20 NEXT WALK ROUND rows across the five tabs — e.g. Social-Security ages 67-69 state (14), Roth banner + save (16), reduce-motion (21), richer duplicate matching (23), undated-value nudge (25), hidden-balances banner on all tabs, pull-to-refresh, value-as-of sweep, the invisible helper consolidations, HSA limit | Same as last time: one workbook, one row per fix with exact before → after, APPROVE/CHANGE/SKIP dropdowns; only approved rows build | BUILT 2026-07-30 — all 25 rows approved verbally + built same day · suite 1,311 green
4 | Price provider | Item 42 — unblocks dividends & total return, live pricing for thinly-traded holdings (kills the $0 class for good) | One-page comparison of licensed providers (coverage, dividend data, price, license terms) with a recommendation; wiring builds after your pick | DELIVERED 2026-07-29 — one-pager in docs/FCC-core-55-70/ · awaiting your pick
5 | Your five open picks, brought drawn | Debts tab month-travel (26) · cash-flow month bars (UX 6) · donut slice labels (UX 7) · winners table depth (Design 1) · plan-incomplete nudge gate (PRD 7) | The visual four arrive as drawn pairs in mock batches — you point at the one you want; the nudge gate you can answer any time in one sentence | ALL RESOLVED in the verdict rounds (dots C, growth link keep, periods keep) except the plan-incomplete nudge gate (PRD 7) — still open, answer any time
6 | Cut Build 47 | Everything approved above that is built, tested and green | Hard gates re-run fresh (full suite, type check, clean pushed tree) → checklist presented → ships ONLY on your literal "cut the build". Quota resets Aug 1 (15 iOS builds) | CUT 2026-07-31 on your word ("cut build 47") — gates fresh: 1,321 green, type check clean, clean pushed tree; code-vs-master review PASSED (49 of 49 payload claims pinned); EAS building → auto-submit → TestFlight

## Build 48 — payload
# | Item | Status
1 | B47 walk findings 1-14 — all fixes (symbol field, Done button, Vanguard balance, delete flash, CD class, holding screen to approved mock, class-slice view, history decimals/Activity, winners since-bought answer, ONE Add-income chooser, repayment-shaped debt editor, slider drag engine, coasting box copy, Cash-and-cash-equivalents label) | BUILT
2 | Plan hub redesigned to approved mock v9 (both lenses, all states, dynamic door) | BUILT
3 | Big one-time costs capture + simulation (mock APPROVED 2026-08-02) | BUILT — capture + sim + hub rows, 6 pins
4 | Orphan screens + Tips/Rewards: FOUNDER DECIDED 2026-08-02 — KEEP ALL (reusable for other age groups); no deletions, menu unchanged | DECIDED — no action
5 | Alignment-audit Tab A (10 items): deferred-loan capture field, bonus/one-time income visibility + editors, debt-editor mock fidelity, Plan-hub copy fidelity, holding-screen fidelity, Net-worth class order + labels, matured-banner fidelity, UX gates on the retired walk (17pt/tabular/estimate chip/safe-draw dedupe/RMD words), CF strip range | BUILT — 10 of 10
6 | Decision round 2026-08-02: adopt-verb sweep ("Use as my plan") · SS Remind-me · voice softening ×3 · menu trim (Rewards/Tips/Credit out) · goal-offtrack insight · Add-something-else link · 4% reword | BUILT — all 7 decision items
7 | Invest return-breakdown (Price change · Realized · Dividends · Interest) | BUILT — approved same day, riding 48
8 | Doc refreshes (Tab B: PRD amendments, voice-sheet Plaid row, menu/FAB rows, design-sheet refresh, flows doc) | DONE — PRD amendments tab, UX rows, design rows, flows v2
9 | PROVIDER PIVOT ON HOLD (founder 2026-08-02): talking to Plaid, SnapTrade AND Teller first — no stack changes until their word. Earlier Plaid-for-beta decision suspended. | ON HOLD — founder evaluating providers

## Build 48 — findings
# | Your finding | Verified root cause | Fix | Status
1 | Setup screen, first bullet: "every account" — name the kinds: account (investment, 401k, checking, savings, etc.) | The first-run bullet said "every account, debt, and dollar" without examples — a 55-70 first-timer shouldn't have to guess what counts. | CLOSED (founder: "love it"): "All your assets and debts in one place — accounts (investment, 401k, checking, savings), your home and other property, and every debt (mortgage, cards, loans) — one live view." Complete inventory, parallel examples for assets AND debts. Rides Build 49. | FIXED — verify on 49
2 | Class-view addition line: "$224,690 + 63,405 + 60,400 + 4,235 + 1,080 + 838 + 504 = 838" — the sum is nonsense | MY BUG (introduced in the pre-48 audit fidelity pass, 3 days old): the visible list filters to the class you tapped, but the addition line I added beneath it summed EVERY holding in the account while the "=" showed only the tapped slice's total. Your seven numbers = the whole Vanguard account; 838 = the slice you were on. | FIXED same hour: the addition uses exactly the same class filter as the list — only the viewed slice's holdings appear, and the equality holds by construction. Pinned with a mixed connected-account test (the stock row can never leak into the bonds sum again). Rides Build 49. | FIXED — verify on 49
3 | Tapping LCTX from Invest opens its full page; tapping the same LCTX line inside the account page does nothing — same name, different behavior | RIGHT — the account page listed holdings as print-only rows. One investment should have ONE page, reachable from every door. | FIXED same hour: every holding row on the account page (whole view AND class view) now opens the same holding page Invest opens. Cash and option rows stay print-only (they have no page). Rides Build 49. | FIXED — verify on 49
4 | The ✎ edit mark top-right of the holding page is tiny and hard to see | RIGHT — a lone pencil glyph at link size. Too small for anyone, not just 55-70 eyes. | FIXED same hour: it now reads "✎ Edit" at the same size and weight as the Back link. Rides Build 49. | FIXED — verify on 49
5 | Imported CD sits under Cash and cash equivalents; the Vanguard CD sits under Bonds & CDs | CONFIRMED inconsistency: standalone CDs are sorted by maturity (under 1 year = cash, longer = bond) but the file import never asks for a maturity date, so it guessed. CDs inside a brokerage always count as bonds. | PARTIAL BUILD: editing a CD/bond account now exposes its maturity date, and the date re-sorts the class by the one rule (under 1 yr = cash · 1 yr+ = bond). STILL TO BUILD in this batch: reading the date out of the name text automatically (import + connected), the import asking for maturity on CDs. | IN PROGRESS
6 | Imported CD carries its maturity (8-24-26) IN ITS NAME, but Edit offers only name/value — no maturity field | CONFIRMED: the import never captures maturity, and the imported holding's edit path has no maturity field — even though the date is sitting in the description text. | AWAITING RESEARCH (your order): fix will read the date out of the description automatically + add the maturity field to edit. | OPEN — research first
7 | Vanguard stocks list as ONE line (Vanguard - Brokerage) under Stocks/ETFs; the E*TRADE stock lists as "Etrade LCTX" | CONFIRMED: connected accounts keep the broker's account name; the file import names a single-stock file BY ITS TICKER. Different door, different naming rule. | PARTIAL BUILD: the import no longer names an account after a ticker (rule 1). STILL TO BUILD: full institution+type naming sweep. | IN PROGRESS
8 | Freshness wording differs: "Imported 2026-08-03" vs "Connected · updated today" | CONFIRMED: two formats for the same concept. | AWAITING RESEARCH BATCH: one wording (relative words: today / yesterday / N days ago) everywhere. | OPEN — research first
9 | By class vs By type unclear; and under By type Vanguard stays ONE account while E*TRADE splits into several | CONFIRMED ROOT CAUSE (your diagnosis): E*TRADE the institution delivers MULTIPLE internal accounts (brokerage + sweep etc.); Vanguard delivers one. By-type groups whole accounts by their kind, so E*TRADE's pieces land under different types. The app must normalize institution data shapes, not mirror them. | PARTIAL BUILD: rule-6 case built — a "savings"-typed account from the brokerage-only pipe now maps to BROKERAGE (not confident → the account-type question can still fix IRAs); your mistyped E*TRADE account heals on next sync. STILL TO BUILD: institution grouping presentation. | IN PROGRESS