## Plan & approvals
Section | Item | Detail / what good looks like | Gate | ✅ Approve? (Y/N) | 💬 Your comments
PROCESS | Design-first, gated | NO code is written until a robust, winning design is approved. Documents only, reviewed step by step. | —
| Build model | Direct-to-consumer (D2C) now; architected so it can go institution-embedded (B2B2C) later. | —
| Big picture | Most of what these two products need is ALREADY BUILT — this is re-organizing around life transitions + targeted net-new work, NOT a from-scratch build. (See 'Reuse & net-new' tab.) | —
TARGET GROUPS | FCC-36-65 | Finance Command Center — peak-complexity / pre-retirement. 128M people · 48% of US adults (the largest, least-served band). | —
| FCC-65+ | Finance Command Center — retirement / decumulation. 57M people · 21% of US adults. | —
DELIVERABLES | 1 · Problem / gap / need (per group) | Who · sub-segments · evidenced jobs-to-be-done · the market gap · the unmet need. NO solutions yet. | input
| 2 · Strategy + goals (per group) | Objective · where-to-play · the spearhead/entry · the daily hook · scope in/out · SPECIFIC measurable goals (north-star + supporting). Feeds the sequencing call. | input
| 3 · High-level conceptual design | The solution shape: ALL features · information architecture · navigation spine · primary journeys (block level) · product principles · scope. Graspable in 10 min; every feature traces to a need. | ✅ FIRST GATE
| 4 · PRD (requirements) | Per feature: user stories · acceptance criteria · business rules · data · states/edge cases · non-functionals (privacy/security/a11y) · success metrics. PLUS the calculation catalog + sameness contract (see RIGOR). Testable, unambiguous, prioritized. | ✅ gate
| 5 · Detailed design | Every screen: layout · components · content/messaging · all states (empty/loading/error/success) · navigation map · transitions. PLUS the data-lineage map (see RIGOR). Every requirement traceable to a screen. | ✅ gate
| 6 · UX design | Design system (type/color/spacing/components) · interaction patterns (incl. expand/collapse) · usability · accessibility (contrast, 44px, screen-reader) · motion · trustworthy-finance tone. | ✅ gate
| 7 · Build | ONLY after 3-6 are approved. Reuse the canonical helpers; sameness contract becomes agreement tests; quality gates green (tsc · jest · UI gate · a11y). | —
RIGOR (your 2 mandates) | Requirements pin the MATH | Calculation catalog: every derived number = formula + inputs + rounding + edge cases. | in #4
| Requirements pin SAMENESS | An explicit contract: which figures must be IDENTICAL everywhere vs which LEGITIMATELY DIFFER (and why). | in #4
| Detailed design = DATA LINEAGE | For every on-screen number: where it's CAPTURED · its SOURCE (user / synced / derived) · the canonical HELPER that produces it. So any number is traceable; 'same concept = same source' is auditable. | in #5
| Payoff | Every 'must-match' row becomes a cross-screen agreement test → numeric consistency is checkable BEFORE code. (The agreement-test pattern already exists in the codebase.) | —
REVIEW CADENCE | Q1 — gates | Problem (#1) + Strategy (#2) are INPUTS (not separately gated); the first FORMAL review gate is the High-level design (#3); then PRD, Detailed design, UX each gated. | your call ✓
| Q2 — group cadence | Write Problem + Strategy for BOTH groups first (the comparison is what lets us pick the sequence), THEN take the chosen group deep through design → PRD → detailed → UX. | your call ✓
SEQUENCE | Phase A | Problem + Strategy for BOTH groups → present → YOU make the sequencing call (which group goes deep first). | —
| Phase B (chosen group) | High-level design (#3) → first formal gate. | —
| Phase C | PRD (#4) → gate · Detailed design (#5) → gate · UX (#6) → gate. | —
| Phase D | Repeat B-C for the second group; then build (#7). | —
FORMAT GOING FORWARD | Excel/Word + approve/comment | EVERY gated artifact (high-level design, PRD, detailed design, UX) delivered in this approve-and-comment format — not raw markdown. | —
NEXT STEP (on approval) | Produce Problem + Strategy (both groups) | Complete FCC-36-65 Problem, write FCC-65+ Problem, then Strategy for both → present for the sequencing decision. | —

## Reuse & net-new
Bucket | Item | Detail (from the codebase inventory) | 💬 Your comments
ALREADY BUILT (reuse) | 65+ decumulation engine | src/domain/decumulation — taxBucketSplit · withdrawalPlan · rmdAtAge · withdrawalOrder · depletionAge; RetirementCockpit Monte-Carlo + guaranteed income + Social Security claim age. ≈80% of the 65+ product.
| 36-65 retirement projection | simulate() (Monte-Carlo + band) · projectNestEgg() (deterministic) · solveRetireAge() · capitalNeeded().
| Net worth + allocation | investableAssets · cashTotal · retirementEarmarkedValue · portfolioActualReturn · asset allocation.
| Cash flow / surplus / income | takeHomeMonthly · surplusByMonth · monthlySavings · plannedMonthlySpend · effectiveTaxRate · grossAnnualBaseline.
| Goals · tax · estate · insurance | Goals (college/house, waterfall, goalStatus) · TaxOrganizer · Estate checklist · Insurance need · Bonds/Performance/Debt math.
| Calculation-catalog seed | One-helper-per-concept across src/domain/* — directly seeds the PRD calculation catalog.
| Sameness-contract infrastructure | number_agreement.test.ts · surplus_agreement · assets/agreement · spend_agreement · glossary — the cross-screen agreement pattern already exists; we extend it.
| Stack | React Native + Expo Router · Zustand · on-device AsyncStorage + SecureStore (encrypted) · Firebase auth/Firestore (household sync) · jest logic/ui · gates (tsc · jest · UI gate · a11y).
NET-NEW (the real build) | Privacy-preserving bank sync | The D2C-locked precondition; the biggest gap. No bank sync today (manual + CSV only).
| Household / shared model | Spouse, an aging parent, kids — today's data is single-user.
| Caregiving / sandwich tools (36-65) | Nothing exists — the single emptiest white space in the market research.
| A daily / recurring hook | For these ages (not young-person safe-to-spend) — e.g. 'am I on track / will it last + next decision'; for 65+, 'safe-to-spend in retirement'.
| Life-transition orchestration | Event-triggered guidance (home · college · caregiving · claiming Social Security · RMDs).
| Trust + accessibility + fraud | Especially for 65+ — higher trust bar, accessibility, fraud protection.
| Extend traceability discipline | Apply the calculation catalog + sameness contract + data lineage to all new surfaces.