## Master action list
ID | Area | Item / feedback | Source | Type | Status (verified in code) | Evidence / what's left | Claude recommendation | Priority | ✅ Your approval | 💬 Your comments
— A. DONE THIS SESSION — verify on device —
NW-1..16 | Net Worth | Full NW design audit: bonds-by-class, Stocks/ETFs title, import value column, left-align copy, donut caption, insight-by-class, investable line, smart +Add, add-specifics links, tap targets, a11y labels, overflow autosize | This session (NW audit doc) | Bug+UX | DONE | 16/16 fixed, committed 91bdb1b+1da8d10; 774 tests green | Device-verify all 5 NW screens | P1
FB-A | Net Worth | Readability: light-gray text failed contrast → darkened textTertiary app-wide to AA (~4.5:1) | This session (your device note) | UX/a11y | DONE | theme.ts textTertiary #76766F; commit 281653d | Verify legibility on device | P1
FB-B | Net Worth | Donut legend is now tappable → scrolls to those accounts | This session (your note '[pj-tab not working]') | UX | DONE | NetWorthScreen scrollToClass; 281653d | Verify the tap-scroll on device | P2
FB-C | Net Worth | Grammar: 'debts are the red line' → 'your debt is the red line below it' | This session | Copy | DONE | 281653d | — | P3
ITEM | Net Worth | Itemize an account into holdings (decompose a $2.5MM lump → stocks/bonds/options/cash; keep-as-cash remainder; total never drifts) | This session (your Q2) | Feature | DONE | itemize.ts + ItemizeScreen; 10 reconcile tests; e637ba5+043055d | Device-test the meter + keep-as-cash; then decide on live-tracking itemized stocks (open item below) | P1
BUG-TX | Stocks/ETFs | Transaction sheet offered bond ('Chase – fixed income') + alternative accounts on the stocks screen | This session (your bug #1) | Bug | DONE | accountAllowsTicker excludes bonds/alts; 76c2bf0; 3 tests | Verify on device | P1
— B. VERIFIED FIXED IN CODE — build-34 device test predated the fix; re-verify on next build —
B-93 | Money/Goals | 'Free cash to save' / 'you free up ~$Y/mo' must be income − spend − DEBT | build-34 #1 + Money test #1 | Accuracy | DONE | GoalsScreen:37 surplusByMonth(op,liabilities); matches Home/Cashflow; tested | Re-verify on device (your recurring catch-point) | P1
B-95 | Goals | Goal status GREEN only when committed monthly funding ≥ required (not just spare cash) | build-34 #1b | Logic | DONE | goals/index.ts:136 on_track iff fundedThisMonth≥requiredMonthly; funding.test pins it | Re-verify on device | P1
B-94 | Budget | Bucket header total = sum of its line items (no unexplained $7,597) | build-34 #3 | Accuracy | DONE | categoryMonthly is the single helper for header & lines; budget.test:231 | Re-verify on device | P2
INC | Income | Edit Equity Comp / Rental / Self-employment (not just base+bonus) | build-34 Money #7 | Bug | DONE | IncomeManagerScreen:54-56 wires RsuEditor/RentalEditor/SelfEmploymentEditor; income.test:104 | Re-verify; see gap INC-2 below | P1
NAV | Navigation | Contribution-room + Cash-flow detail no longer loop back to Home | build-34 #12 | Bug | DONE | routeGuard MODAL_SEGMENTS has contribution-room+cashflow; both app routes exist | Re-verify on device | P1
TITLE | Stocks/ETFs | Screen no longer titled 'Portfolio Performance' | build-34 #9 | Bug | DONE | NW-2; eyebrow = ASSET_CLASS_LABEL['stocks_etf']; 1da8d10 | Re-verify on device | P2
— C. OPEN — real gaps (need work) —
OPEN-1 | Investing | 'Grow & track' / 'Portfolio' entry points route ONLY to the stocks Performance screen — bonds & crypto 'can't grow' | build-34 #10 | UX gap | OPEN | TopBar:30, HomeScreen:42-44, insights→/performance all go to stocks-only screen | Make 'Grow & track' a hub (Stocks/Bonds/Alternatives) OR route by the asset the card is about. Recommend a small 'Investments hub' screen | P1
OPEN-2 | Education | InfoDot (ⓘ) coverage only ~35% (6 of 17 terms). Missing: take-home, net worth, runway, nest egg, savings rate, APR, coupon, yield, vesting | build-34 'info buttons on all key terms?' | UX gap | OPEN | UI.tsx InfoDot; only surplus/bonds/alts/rmd/contributionRoom/asset-classes wired | Add glossary entries for apr/coupon/yield/vesting; attach InfoDot to take-home, net worth, runway on Home/Budget/NW | P2
OPEN-3 | Money | Cash-flow detail redesign: actual-this-month + bar chart + table of monthly cash flow (like onboarding) + tap a bar → that month's planned popup | build-34 #6 + Money #6 | Feature | OPEN | CashFlowScreen exists but not the bar/table/popup | Design first (mock), then build. Strong retention surface | P2
OPEN-4 | Net Worth | Ordering inconsistent: 'Explore your holdings' box (import/stocks/bond/alts) vs the account sections — and chip order within forms | build-34 #7 + [pj] notes | UX polish | OPEN | Different orders in different places | Define ONE canonical class order (Cash→Stocks→Bonds→Alts→RE→Property) and use everywhere | P2
OPEN-5 | Net Worth | 'If I have cash sitting in my investment account, what do I select?' + edit sheet still shows brokerage/checking/savings with unclear guidance | build-34 #8 | UX/clarify | PARTIAL | New picker added cash sub-types + 'What's inside?' but cash-sleeve-in-brokerage path is unclear | Add a 'cash sleeve' option on the brokerage/retirement forms; clarify kind guidance | P2
INC-2 | Income | Income manager only shows a row to edit if that source already has a value — no way to ADD a brand-new equity/rental/self-employment stream from scratch | Verification (this session) | UX gap | OPEN | IncomeManagerScreen rows render only when value>0 | Add '+ Add income type' that can create equity/rental/SE from scratch | P2
OPEN-6 | Investing | Itemized stocks are captured for allocation but NOT yet live-tracked on the Stocks/ETFs Performance screen (they aren't 'positions') | This session (itemize follow-up) | Feature | OPEN | ItemizeScreen creates class accounts, not positions | Wire itemized stocks-with-ticker into positions so they show on Performance (optional, your call) | P3
B-69 | Retirement | Two retirement engines historically disagreed on 'on track' | Bug ledger (only open row) | Accuracy | PARTIAL | Both routes now → RetirementCockpit (one engine); BUT no agreement test + ledger row still 'open' | Add a guard test that only the cockpit engine is reachable; close the ledger row | P2
KBD | Forms | Amount field hidden behind keyboard on a SHORT NW sheet | build-34 #5 (Fail) | Bug | PARTIAL | KeyboardAwareSheet has automaticallyAdjustKeyboardInsets; NW AssetSheet imports it — should be fixed; device said fail on older build | Re-verify on device; if still failing, force scroll-to-focus | P1
OPEN-7 | Insights | Insights aesthetics ('center-justified, not pleasing; heading centered + body left?') | build-34 UI question | UX/clarify | CLARIFY | InsightsScreen has NO textAlign — body already left-aligned; nothing centered | Confirm with you what you want (center the heading? current is all-left). Low effort once decided | P3
— F. NW ONBOARDING / ADD-FLOW — my Sr UI Designer review (earlier this session) —
UI-1 | Net Worth | Wrapper question over-asked for the common taxable case; class-first fought the account-first mental model | Sr UI Designer review | UX | DONE | Add picker defaults wrapper='Taxable' + offers account-first picks (Retirement / Brokerage) | — | P2
UI-2 | Net Worth | Step-count fatigue in the add flow | Sr UI Designer review | UX | DONE | Quick-add row + smart defaults + smart per-section jump (NW-12) | — | P2
UI-3 | Net Worth | 7 icon-only 'add more' buttons + 3 overlapping entry points → I'd recommended ONE reused '+ Add an account' | Sr UI Designer review | UX | PARTIAL | Chose smart per-section +Add (4 contextual buttons) instead of ONE; the single setup-hub button wasn't built | DECIDE: keep smart per-section (current) OR collapse to one '+ Add an account'. Your call | P2
UI-4 | Net Worth | View-by-section vs add-by-class mismatch confused the model | Sr UI Designer review | UX | DONE | Captions label donut = allocation, sections = accounts (NW-8) | — | P3
UI-5 | Net Worth | Heavy individual-bond form deterred entry | Sr UI Designer review | UX | DONE | Bonds form takes a total value + 'Add specific holdings →' link (NW-16) | — | P3
UI-6 | Net Worth | Cold tone → wanted net-worth-as-hero + gentle nudges + warmer coaching voice | Sr UI Designer review | UX | PARTIAL | Donut/net-worth hero + mixed-allocation nudge exist; warmer copy + celebratory moments not done | Do a coaching-tone copy pass + add a success moment (see UI-8) | P2
UI-7 | Net Worth | Setup flow: the polished recap/hub ('net worth so far' + '+ Add' + "I'm done") with net-worth-as-hero | Sr UI Designer review / approved mock | Feature | PARTIAL | Guided wizard shows a running 'Net worth so far' + Finish, but the polished recap-hub mock was never built as designed | Build the recap-hub, OR confirm the current wizard is enough | P2
UI-8 | Net Worth | Guided 'Finish' has no success/celebration moment — anticlimactic after a multi-step setup | Sr UI Designer review + NW audit | UX | OPEN | NetWorthScreen: Finish → setNwSetupChoice('self'), no confirmation | Add a 'You're set — here's your net worth' beat | P2
UI-9 | Net Worth | Setup choice is a one-way door — can't return to the guided walkthrough after picking 'I'll add my own' | Sr UI Designer review + NW audit | UX | OPEN | nwSetupChoice can't be reset from the UI | Add a way to re-enter guided setup (e.g. from a menu / Settings) | P3
— D. PARKED V1 — launch blockers (see finwise-launch-and-parked.xlsx) —
L-1 | Data | Switch to a paid/licensed price source (Tiingo). Free Yahoo feed isn't legal for a paid app | Parked V1 | Blocker | OPEN | Seam ready; needs your API key | You get a key; I do the swap | P1
P-71 | Branding | Pick + trademark final app name ('FinWise' may be taken; 'Hatcho' front-runner) | Parked V1 | Blocker | OPEN | Not started | Decide name; then I do the rename pass (once, late) | P1
L-5..L-26 | Launch ops | App Store listing, privacy questionnaire, reviewer login, screenshots, build #35, submit | Parked V1 | Blocker | OPEN | Your-owned; build #35 blocked on free EAS quota (~Jul 1) | Sequence after the code is launch-ready | P1
P-23/P-63 | Safety | Dependency security scan + audit all data-fetch error handling (not just happy path) | Parked V1 | Important | OPEN | Not started | I can do both before submit | P2
— E. PARKED — fast-follow & V2 highlights (full list in parked xlsx) —
P-1 | Data | Bank/brokerage linking (auto-sync balances & transactions) | Parked V2 | Feature | OPEN | Large build; needs secure server | SEE PM REVIEW — this is the #1 retention lever; reconsider priority | P1
P-8 | Insights | 'Can I afford a $600k house?' — plain-question affordability simulator | Parked V2 | Feature | OPEN | Not built | SEE PM REVIEW — standout/shareable; move up | P2
P-35 | UI/UX | Home card: net worth over time ('up $40k in 6 months') | Parked V2 | Feature | OPEN | Snapshot only today | SEE PM REVIEW — retention dopamine; move up | P2
P-53 | Goals | Finish the full savings-goals screen (progress, priority, projections) | Parked fast-follow | Feature | OPEN | Logic exists; visual screen unfinished | Good stickiness; pair with OPEN-3 | P2
P-28/P-29 | a11y | Screen-reader support + reliably-tappable buttons app-wide | Parked fast-follow | a11y | PARTIAL | NW screens now labeled; rest of app partial | Roll the NW a11y pattern across all screens | P2
P-41/P-39 | UI/UX | Undo-after-delete + skeleton loaders / offline-sync states | Parked fast-follow | UX | OPEN | Not built | SEE PM REVIEW — part of the 'feels trustworthy' system | P2
EXPAND | UI/UX | Expand/collapse on long lists/sections (your example) — declutter every dense screen | Your meta-feedback (this session) | UX system | OPEN | Not implemented anywhere | SEE PM REVIEW — build as a reusable pattern, apply to NW sections, budget buckets, holdings, insights | P2

## Principal PM review
# | Theme | Honest finding | Recommendation | Why it matters / which persona | Effort | ✅ Approve? | 💬 Your comments
VERDICT | HONEST VERDICT: As-is, this won't convert paying users yet — not because the math is weak (it's strong, and well-tested), but because (1) manual entry kills retention vs auto-sync competitors, (2) there's no single sharp hook, (3) breadth (NW+budget+goals+retirement+insurance+estate+tax+jobsafety) dilutes depth, and (4) the clumsy seams you keep finding erode trust — for a finance app, a clumsy flow reads as 'can I trust the number?'. The good news: the bones (accuracy, privacy-by-design, taxonomy) are a real moat IF we pick a persona, cut scope, and build a UX SYSTEM instead of one-off screens.
1 | Pick a persona (wedge) | The app serves nobody sharply because it tries to serve everyone (18yo→retiree). 18yo won't pay (no net worth, retirement irrelevant); retiree needs trust+simplicity we don't yet nail. | Lead with the 25–38yo 'building wealth' professional: take-home clarity, debt payoff, equity comp, first home, first investments, 'can I afford X'. Push retiree/estate/tax depth to V2. | Biggest paying market + highest willingness ($5–10/mo). Focuses every other decision. | L
2 | Manual entry is an existential risk | Every competitor (Monarch/Empower/Copilot) auto-syncs. Manual entry → week-2 churn. Today bank-linking (P-1) is parked to 'later'. | Move read-only bank/brokerage sync UP (Plaid or a privacy-preserving sync). Until then make manual MAGICAL: 60-sec onboarding, CSV import (have it), receipt OCR (parked P-4), Apple-Wallet hints. | Without sync, the value prop is 'a beautiful spreadsheet you maintain by hand'. This is the #1 retention lever. | XL
3 | No single hook | 'Does everything, privately, manually' is not a wedge. Store visitors won't get the one reason to install. | Pick ONE: (a) 'The planner that never sells your data' (privacy), or (b) 'Your honest retirement number' (Monte-Carlo + tax-smart withdrawals), or (c) 'A 20-something's first money command center'. Lead the listing with it. | Conversion + word of mouth. A wedge beats a feature list. | M
4 | Build a UX SYSTEM, not screens | You keep finding clumsy flows (random ordering, missing expand/collapse, dead drill-ins, transaction sheet showing bonds). Each one = a trust ding. I've been fixing reactively, not designing the system. | Define + enforce ONCE: (1) one canonical asset-class order everywhere, (2) one text-alignment rule, (3) expand/collapse pattern for every dense list, (4) skeleton loaders + empty states, (5) undo-after-delete. Then sweep every screen. | For a finance app the UX system IS the product — it's what makes the math feel trustworthy. Death by a thousand papercuts is the current risk. | L
5 | 'Can I afford X?' simulator | P-8 is parked but it's the most shareable, viral, universally-wanted feature (18yo: 'can I afford this trip?'; 40yo: 'can I afford this house?'). | Build a simple scenario simulator on top of the existing engine. Make the result shareable. | Differentiator + organic growth. Both ends of the persona range ask this. | M
6 | Net worth over time | Net worth is a snapshot today. A growing line ('up $40k in 6 mo') is the dopamine that brings people back weekly. | P-35: store monthly net-worth snapshots, show a trend card on Home. | Retention/habit. Cheap relative to impact. | S
7 | Progressive disclosure / modes | One-size-fits-all-complex overwhelms the 18–25yo and under-serves nobody well. | Two modes: 'Simple' (cash, spending, one goal, net worth) for young users; 'Full' (retirement, equity, tax) for 35+. Same data, different surface. | Lets one app serve the persona range without dumbing down or overwhelming. | M
8 | Trust theater (earn the paywall) | People pay for finance apps when they FEEL accurate and safe. You have the accuracy (agreement tests) but don't SHOW it. | Surface 'every number is cross-checked', the privacy promise, '$ stays on your device', provenance drill-downs (you have these in Insights — extend them). | Justifies the subscription; converts the privacy-conscious segment. | S
9 | Cut scope to ship quality | Insurance, estate, tax-organizer, jobsafety are half-built breadth that dilutes polish on the core. | For v1 launch, hide/curtail the half-built modules; ship a tight spine (NW + cash flow + goals + a credible retirement number) that's flawless. | Quality bar > feature count. A tight, polished app beats a broad, clumsy one — especially for trust. | M
10 | My honest meta-answer | You're right that I've been executing tactically, not thinking like a Principal PM: fixing the thing in front of me (the expand/collapse miss is the tell) instead of defining persona → wedge → UX system → ruthless scope cuts. | Going forward: every change gets weighed against 'does this help the target persona pay?' and reuses a system, not a one-off. I'll propose the system + scope cuts above as the next plan if you approve the direction. | This is the difference between a feature pile and a product people buy. | —

## Phase 2 — Persona platform
# | Section | Decision / item | Detail | Phase / sequencing | ✅ Approve? | 💬 Your comments
WHY | PHASE 2 — 'Money Command Center' as ONE platform serving two personas: Employed (18–55, accumulation) and Retired (decumulation). Decision: build as ONE platform with two switchable persona MODES sharing a common spine — NOT two separate apps. The spine (~70%: data model, net worth, holdings, taxonomy, security, prices, accuracy guarantees) is built once; the persona 'mode' swaps the Home dashboard, module set, planning lens, and tone. Sequence: ship Employed mode first → add Retired as the 2nd surface on the same spine → a 'glide path' for the 50–65 transition (the highest-value, semi-retired segment).
— ARCHITECTURE —
A1 | Architecture | ONE platform, two switchable persona modes (NOT two separate softwares) | Forking into two apps = 2× maintenance, the cross-screen accuracy guarantees break across the fork, and you orphan the pre-retiree. One codebase, one subscription, one accuracy net. | Decision
A2 | Architecture | Shared spine — build once | Auth, security/encryption, sync, the full data model (accounts, net worth, holdings, taxonomy, income, debts, transactions), market prices, most calculations + the agreement tests. ~70% of the work, identical for both personas. | Foundation (largely built)
A3 | Architecture | Persona 'mode' layer — diverges | Home dashboard (the hero question), the active module set, the planning lens (grow-toward vs draw-down), tone + onboarding questions, which insights fire. | Per persona
A4 | Architecture | Mode chosen at onboarding; switchable | Auto-suggest from age + employment/retirement status; user can switch. Stored on the profile. | With Employed mode
A5 | Architecture | 'Glide path' for the 50–65 transition | Semi-retired / phasing users see BOTH lenses — still earning + starting to draw down. Highest-anxiety, highest-willingness-to-pay segment; the bridge competitors miss. | After both modes exist
— SCREEN SPLIT —
S1 | Screens | Shared | Auth · onboarding (persona fork early) · Net Worth · Investments/holdings · Settings · security. | Spine
S2 | Screens | Employed lens (accumulation) | Home (on-track?) · Budget / cash-flow · Goals · Debt payoff · accumulation retirement projection · 'Can I afford X?'. | Mode 1 (first)
S3 | Screens | Retired lens (decumulation) | Home (will it last? safe-to-spend) · Withdrawal planner (required minimum withdrawals, Social Security timing, Roth conversions, draw sequencing) · healthcare/Medicare · odds-based drawdown projection · estate · tax-smart spend-down. | Mode 2 (next surface)
— SEQUENCING —
Q1 | Sequencing | Ship Employed mode FIRST | Mostly built, bigger market, faster to revenue. Focus the wedge here (18–35 start). | Now
Q2 | Sequencing | Extract the shared spine AS you add Retired mode | Don't speculatively architect a 'platform' before the 2nd mode proves the seams — premature abstraction = 2× complexity, ships nothing. | When building mode 2
Q3 | Sequencing | Retired mode = 2nd surface on the spine | Not a parallel build. Reuse the spine; add the decumulation modules + lens. | After mode 1 ships
Q4 | Sequencing | Do NOT build both pre-launch | Scope discipline — nail one persona to revenue before the second. | Guardrail
— PROCESS (doc chain, gated) —
P1 | Process | Product Requirements (PRD) per persona | Persona + WEDGE + jobs-to-be-done + success metric + explicit scope cut (what's OUT). 2–3 pages. → YOU APPROVE before design. | Gate 1
P2 | Process | Conceptual design | Experience architecture, navigation model, key flows, how the wedge shows up. Mockup-level. → APPROVE before detail. | Gate 2
P3 | Process | Detailed design (per screen/flow) | Layouts, states, components, copy, edge cases. → APPROVE before build. | Gate 3
P4 | Process | Build → verify → device-test | Each approved spec becomes code; gates stay green; verify on device. | Gate 4

## FCC 36-65 strategy
# | Item | Detail / decision | Status | ✅ Approve? | 💬 Your comments
WHY | FCC 36-65 = Finance Command Center for the 36-65 peak-complexity / pre-retirement years. This refines the earlier 'Employed 18-55' framing (Phase 2 tab) per the market research: the under-served MIDDLE is the white space. Strategy/design/planning depth lives in docs/FCC-36-65/. We work this group FIRST.
— TARGET —
T1 | Target band | 36-65 · 128M · 48% of US adults — the largest, least-served band. Peak complexity: first home, kids/college, sandwich-generation caregiving, peak earn + tax, pre-retirement. | Set
T2 | Strategic basis | White space + highest willingness-to-pay is the under-served middle (your cradle-to-grave research). REUSES the breadth already built: retirement cockpit, net worth, tax, estate, insurance, goals, budgets. | Set
— FRAMING DECISIONS (pending your call) —
D1 | Spearhead / wedge | PROPOSED: the pre-retirement → retirement transition (~55-65) — highest WTP, thinnest execution (planners model, none execute with daily money), connective tissue to FCC-65+. Alts: caregiving white space; peak-earn/tax. | Pending
D2 | Daily hook | PROPOSED: 'Am I still on track / will my money last + what's the next decision?' — a retirement-confidence number that moves + transition-triggered guidance. | Pending
D3 | Distribution | PROPOSED: direct-to-consumer first, designed for institution-embedded (B2B2C) scaling (advisors, employers near retirement). | Pending
D4 | Sequencing | PROPOSED: build FCC-36-65 first (largest band, on-ramp, reuses engine); FCC-65+ next. | Pending
— DOCS (depth in the folder) —
X1 | Strategy / design / planning | docs/FCC-36-65/ — separate gated docs (strategy → conceptual → detailed → plan). See folder README. | Folder ready
X2 | Status | Strategy doc not started — awaiting the framing decisions above. | Not started

## FCC 65+ strategy
# | Item | Detail / decision | Status | ✅ Approve? | 💬 Your comments
WHY | FCC 65+ = Finance Command Center for retirement / decumulation. Refines the earlier 'Retired' framing per the market research. Strategy/design/planning depth lives in docs/FCC-65+/. QUEUED — we work FCC-36-65 first.
— TARGET —
T1 | Target band | 65+ · 57M · 21% of US adults. Decumulation: turn assets into income, Social Security/Medicare timing, required minimum withdrawals, estate/legacy, fraud protection. | Set
T2 | Strategic basis | Thinly served (planners model the math; none execute with daily money); high WTP; trust-sensitive → institution-embedded (B2B2C) fits. Reuses: retirement cockpit (decumulation), RMD, SS, estate. | Set
— FRAMING DECISIONS (pending) —
D1 | Spearhead / wedge | PROPOSED: decumulation 'safe-to-spend in retirement' (how much can I spend this month without running out) + SS/Medicare timing. | Pending
D2 | Daily hook | PROPOSED: 'How much can I safely spend this month / is my retirement income on track' — safe-to-spend, reframed for drawdown. | Pending
D3 | Distribution | PROPOSED: institution-embedded likely (advisors, Medicare/benefits brokers) given the trust bar. | Pending
— DOCS —
X1 | Strategy / design / planning | docs/FCC-65+/ — separate gated docs. See folder README. | Folder ready
X2 | Status | QUEUED — we work FCC-36-65 first (one strategy at a time). | Queued