## V1 — Next launch
V1 — Next launch
EVERYTHING ON THIS TAB IS V1 — the genuine must-ship list for the next launch, nothing optional. It's the ship process (L-#, in critical-path order) plus the only backlog items that truly can't wait: the final app name (legal), two safety items, and one feature that's already built. Type: 'Blocker' = can't ship without it · 'Important' = strongly recommended before submit · 'Decision'/'Recommended' as labelled. Stage = where it is (Plan→Design→Build→Test→Refine→Ready, or Done). Yellow columns are yours (J Rank / J Notes / Decision); 'Your rank' is my suggested order. Things I'd do right after launch are on the 'Fast follow-up' tab; everything else is on 'V2 — Future'.
ID | Area | Item | Owner | Type | Stage | Status / what's left | Your rank | J Rank | J Notes | Decision (when) | Notes / next step
L-1 | Data | Switch to a paid, properly-licensed source for stock & fund prices (the free Yahoo feed isn't legal for a paid app). | You→Claude | Blocker | Plan | Open — the long pole | 1 | 4 |  | NOW | You pick a provider (Tiingo is cheapest, ~$10–50/mo) and get a key; then I do a small swap. This is a legal must-fix.
L-15 | Accuracy | Make a spending category entered as a percentage turn into the SAME dollar amount everywhere it's used. | Claude | Accuracy | Done | Done — verified in code 2026-06-27 | 2 | done | Test | DONE | Confirmed: % spending resolves against the take-home base everywhere (pinned by budget tests).
L-16 | Accuracy | Make every screen show the SAME number for the same thing (take-home pay can't differ screen to screen). | Claude | Accuracy | Done | Done 2026-06-25 | 3 | done | Test | DONE | Locked in by an automatic check. A wrong number = lost trust.
L-17 | Accuracy | Confirm no money figure shown anywhere is wrong. | Claude | Important | Test | Ongoing — none currently open | 4 |  |  | NOW — verify | Re-check before each submission.
L-2 | Security | Lock down the cloud database so each person can only read their own data. | You | Blocker | Done | Done 2026-06-17 (the old checklist was stale) | 5 | done |  | DONE — confirm console | Already deployed; just confirm it's active in the console.
L-19 | Compliance | Write the note to Apple's reviewer explaining the app is an educational planner (no money movement). | You | Important | Refine | Draft exists | 6 | 5 |  | NOW | Reduces the risk of rejection under finance-app rules.
L-5 | Listing | Enter the App Store description, keywords, subtitle, and promo text. | You | Blocker | Refine | Drafted — needs entering | 7 | 6 |  | NOW | The wording is written; paste it into App Store Connect.
L-8 | Compliance | Fill in Apple's privacy questionnaire so it matches what the app actually collects. | You | Blocker | Plan | Open | 8 | 7 |  | NOW | Declare email, name, financial info, crash data — all to run the app, none for tracking. Apple cross-checks.
L-6 | Listing | Set the app's category (Finance) and age rating (4+). | You | Blocker | Plan | Open (quick) | 9 | 8 |  | NOW | Short questionnaires in App Store Connect.
L-9 | Compliance | Create a test login with sample data for Apple's reviewer and include it in the submission. | You | Blocker | Plan | Open | 10 | 9 |  | NOW | Without it the reviewer can't get past sign-in and will reject.
L-7 | Listing | Publish a live Privacy Policy page and a Support page, and link them. | You | Blocker | Build | Part done — privacy page needs the new wording re-published; support page not made yet | 11 | 1 |  | NOW | The privacy page is live but its text changed (see L-11).
L-11 | Compliance | Re-publish the privacy page with the new wording: financial data and receipts never leave your device. | You | Blocker | Refine | Wording done in the app; the public page isn't re-published | 12 | 2 |  | NOW | The promise is already true in the app; the public page must say the same.
L-20 | Positioning | Decide to launch in the US only for now. | You | Decision | Plan | Likely already (US-dollars only) | 13 | 3 | Have Claude confirm | NOW — decide | Confirm; don't market it globally yet.
L-21 | Positioning | Decide to track 'how many people finish setup' as the #1 success measure. | You | Decision | Plan | Decision needed | 14 |  |  | NOW — decide | Needs basic usage tracking (see the analytics item below).
L-13 | Compliance | Show a 'this is an estimate, not advice' note on every forecast or 'on-track' verdict. | Claude | Important | Done | Done | 15 | done | Test | DONE | Added everywhere; a guard test stops it being removed.
L-14 | Reliability | Make sure the app handles no-internet gracefully instead of crashing. | Claude | Important | Done | Done (verified) | 16 | done | Test | DONE | Already safe; proven by offline tests.
L-3 | Build | Build the real app installer (build #35) and check receipt-scanning + secure storage on a real phone. | You (EAS) | Blocker | Build | Blocked on the free build allowance (~Jul 1); the code is ready | 17 | done | Test | AT BUILD #35 | Everything's in and tested; push-button once the allowance resets.
L-23 | Data | Confirm prices load from the new paid source (not Yahoo). | You | Blocker | Plan | Waiting on the vendor swap (L-1) | 18 |  |  | AT BUILD #35
L-12 | Reliability | Confirm a crash report actually reaches the dashboard on the new build. | You | Blocker | Test | Wired; verify on the build | 19 | done | Test | AT BUILD #35 | Press the test button in Settings and check it lands.
L-10 | Compliance | Test that 'delete my account' fully wipes your data on a real build. | You | Blocker | Test | Open (needs build #35) | 20 | done | Test | AT BUILD #35 | Apple requires this; confirm it removes cloud data and login.
L-22 | Testing | Walk through setup as each user type (student, variable income, professional, retiree) and check the numbers add up. | You | Blocker | Test | Open (needs build #35) | 21 | done | Test | AT BUILD #35 | Use the user guide as the script.
L-24 | Testing | Test sign up → log out → recover account → log back in. | You | Blocker | Test | Open | 22 | done | Test | AT BUILD #35
L-18 | Testing | Run the automated tap-through tests on a real phone (sign-up, basic screens, add-sheet, net-worth, cash-flow). | You | Important | Test | Open (needs build) | 23 |  | ?? | AT BUILD #35 | These scripts have never run on a real device, so some may need small fixes the first time.
L-25 | Testing | Hands-on test on a real phone: gestures, keyboard, screen edges, large text. | You | Recommended | Test | Open (needs build) | 24 | done | Test | AT BUILD #35
L-4 | Listing | Take the App Store screenshots on a real iPhone. | You | Blocker | Build | Open (needs a device build) | 25 | 10 |  | AT BUILD #35 | 8 framed shots with captions are already planned out.
L-26 | Submit | Submit the build to TestFlight and then to App Review. | You | Blocker | Plan | Final step | 26 |  |  | SUBMIT (last) | Submitting doesn't use the build allowance.
P-71 | Branding | Pick and trademark a final app name, since 'FinWise' may already be taken. | You→Claude | Blocker | Plan | Not started |  |  |  | Before submit — legal | A real legal blocker before public launch; 'Hatcho' is the front-runner.
P-23 | Security | Scan the app's building blocks for known security holes and fix the risky ones. | Claude | Important | Plan | Not started |  |  |  | Before submit — safety | A high-priority safety check before launch.
P-63 | Quality | Review that every data fetch handles errors gracefully, not just the happy path. | Claude | Important | Plan | Not started |  |  |  | Before submit — safety | Prevents crashes and blank screens; high priority.
P-33 | UI/UX | Add a tap to hide or blur your balances for privacy. | Claude | v1 feature | Done | Done — verify |  |  |  | DONE | Lets you check the app in public without showing your money.

## Fast follow-up
Fast follow-up
MY RECOMMENDATION for the first quick update right after launch — high-value, lower-risk improvements that don't block the launch but I'd ship soon after. Listed in priority order (top = first). These were pulled out of the backlog so they don't get lost behind the bigger V2 work. Want any of these IN the launch instead? Tell me and I'll move it to V1. Want one pushed further out? It goes to V2.
ID | Category | Item | Stage | What's left | Your notes | Why it matters
P-62 | Quality | Add tests for the core retirement and investment math. | Plan |  |  | Protects accuracy of the most important calculations; high priority.
P-38 | UI/UX | Make total spending and the category breakdown always add up to the same number. | Plan |  |  | Prevents confusing double-counting between summaries and budget.
P-64 | Quality | Add timeouts and retries so the app never hangs waiting on data. | Plan |  |  | Stops endless loading spinners; medium priority.
P-73 | Other | Add usage tracking to see how many people finish setup and keep coming back. | Plan |  |  | Needed to measure success and the top launch metric.
P-4 | Data | Turn on snap-a-photo receipt scanning and improve how it reads the totals. | Plan |  |  | Nearly ready; needs a real device build to switch on and test.
P-5 | Data | Catch bad rows when you import a spreadsheet so imports don't break things. | Plan |  |  | Protects against messy files corrupting your data.
P-53 | Growth | Finish the full savings-goals screen with progress, priority, and projections. | Build | The goals tab and funding logic exist; the full visual screen isn't finished. |  | Helps people set and track goals; a stickiness feature.
P-28 | Accessibility | Make every screen work with the screen reader for blind and low-vision users. | Plan |  |  | The single biggest accessibility gap (for users with disabilities).
P-29 | Accessibility | Make buttons big enough to tap reliably for everyone. | Plan |  |  | An accessibility basic (for users with disabilities); high priority.
P-41 | UI/UX | Add an 'undo' option after deleting something by mistake. | Plan |  |  | Friendlier than a blocking confirmation pop-up; medium priority.
P-39 | UI/UX | Add loading placeholders and clear offline / syncing states. | Plan |  |  | Makes the app feel smoother while data loads; medium priority.
P-34 | UI/UX | Show how many months your cash savings could cover if income stopped. | Plan |  |  | A reassuring 'safety cushion' number; overlaps the job-loss mode.
P-60 | Quality | Let users export their data to a file and import it back. | Plan |  |  | Gives users control of their data; medium priority.

## V2 — Future
V2 — Future
EVERYTHING ON THIS TAB IS V2 — a later, bigger release down the road (bank linking, the planning copilot, couples, more retirement modelling, translations, design polish, etc.). If it's not on the V1 or Fast follow-up tabs, it's here. Stage shows how far along each is; 'What's left' spells out what's unfinished for the part-done ones. The yellow 'Your notes' column is yours. To pull anything forward, tell me which tab to move it to. (The crash-reporting row was removed — it's the same work as launch item L-12.)
ID | Category | Item | Stage | What's left | Your notes | Why it matters
P-1 | Data | Connect the app to your bank and brokerage so balances and transactions pull in automatically. | Plan |  |  | Biggest convenience and stickiness win, but a large build needing a secure server.
P-2 | Data | Automatically figure out dividends from a stock ticker instead of you typing them in. | Plan |  |  | Saves manual entry for people who hold dividend-paying stocks.
P-3 | Data | Suggest stock tickers as you type and cache prices so they load faster. | Plan |  |  | Nice polish; the core performance views already work.
P-6 | Insights | Turn your saved history into smart nudges like 'gas spending up 15% this month'. | Build | A basic 9-rule version works; the richer history-driven version isn't built. |  | Makes the app feel personal and proactive.
P-7 | Insights | Put a consistent tap-to-explain button on every AI suggestion so you see the reasoning. | Plan |  |  | Builds trust; explanations exist but aren't uniform yet.
P-8 | Insights | Ask the app plain questions like 'can I afford a $600k house?' and get an answer. | Plan |  |  | A standout feature that sets the app apart.
P-9 | Insights | Compare life choices like buying a home, having a child, or a job change side by side. | Plan |  |  | Helps users weigh big decisions.
P-10 | Retire | Show retirees whether their money will last as they spend it down. | Build | A basic spend-down view exists; deeper retiree-focused views aren't built. |  | Answers the top question retirees have.
P-11 | Retire | Plan smart, tax-savvy withdrawals in retirement to keep more of your money. | Plan |  |  | Valuable but sensitive; needs careful, accurate tax handling.
P-12 | Retire | Assume your savings grow as your pay rises over the years. | Plan |  |  | Makes retirement projections more realistic.
P-13 | Retire | Support married filers and other countries' tax and account rules. | Plan |  |  | Today it only handles single US filers; needed to expand abroad.
P-14 | Retire | Let couples and households share goals while keeping personal views too. | Plan | Partner invites are partly built. |  | Needed for shared finances.
P-15 | Retire | Add saving-for-college planning. | Plan |  |  | Fills a gap for families with kids.
P-16 | Retire | Add life and long-term-care insurance planning. | Plan |  |  | Fills a life-stage gap many users hit.
P-17 | Retire | Add estate planning like naming who inherits and tracking key documents. | Plan |  |  | Rounds out planning for later life stages.
P-18 | Retire | Add a job-loss mode showing how long your cash lasts and a survival budget. | Plan |  |  | Helps people through a stressful transition.
P-19 | Retire | Add a mode for gig and freelance income that smooths uneven pay and sets aside taxes. | Plan |  |  | Serves the growing self-employed audience.
P-20 | Onboarding | Let users add more details later to sharpen their plan, prompted step by step. | Build | A simple checklist exists; the guided 'add more to sharpen' flow isn't built. |  | Improves plan accuracy without overwhelming people upfront.
P-21 | Security | Let partners securely share one encrypted account through an invite code. | Plan |  |  | Today two logins can't share the same encrypted data; needed for couples.
P-22 | Security | Add two-step login for stronger account security. | Plan |  |  | App lock already exists; this is the next security layer.
P-24 | Security | Add automated code scanning that flags security flaws as code is written. | Plan |  |  | Catches problems early; lower priority.
P-25 | Security | Scan the finished app file for insecure storage or data-transfer issues. | Plan |  |  | Extra security check; lower priority.
P-26 | Security | Make sure all data fetches use secure, encrypted connections. | Plan |  |  | Protects data in transit; lower priority.
P-27 | Security | Require a fingerprint or face check to confirm the most important actions. | Plan |  |  | App unlock already uses biometrics; this adds per-action confirmation.
P-30 | Accessibility | Add dark mode and a high-contrast theme. | Plan |  |  | A comfort and readability option; lower priority.
P-31 | Accessibility | Check that all text and charts have enough color contrast to be readable. | Plan |  |  | An accessibility review (for users with disabilities); medium priority.
P-32 | Accessibility | Tone down animations for users who prefer less motion. | Plan |  |  | A small comfort improvement; low priority.
P-35 | UI/UX | Add a Home card showing how your net worth has grown over time. | Plan |  |  | A motivating progress view like 'net worth up $40k in 6 months'.
P-36 | UI/UX | Redesign the top bar and bottom menu to match the newer look. | Build | The newer style exists elsewhere; the header and menu still use older styling. |  | Visual consistency across the app.
P-37 | UI/UX | Refresh the older detail screens like budget, transactions, settings, and rewards. | Plan |  |  | The new home tiles still open older-looking screens.
P-40 | UI/UX | Add an app-wide banner showing when you're offline or syncing. | Plan |  |  | Keeps users informed about connection status; lower priority.
P-42 | UI/UX | Add a reusable 'what's this?' tooltip and a searchable plain-language glossary. | Build | Simple explainer dots were added; the full tooltip and glossary module may be unfinished. |  | Helps users understand finance terms; lower priority.
P-43 | UI/UX | Set one consistent rule for showing money and dates so cents don't drift. | Plan |  |  | Keeps numbers looking correct and uniform; lower priority.
P-44 | UI/UX | Let users pin and rearrange the cards on their Home screen. | Plan |  |  | Personalizes the home view; lower priority.
P-45 | UI/UX | Let users switch any chart to a plain data table. | Plan |  |  | Easier to read for some users; lower priority.
P-46 | UI/UX | Build a notification system with frequency limits and per-type controls. | Plan |  |  | Prevents notification overload; lower priority.
P-47 | UI/UX | Explain why the app needs camera or notification access before the system asks. | Plan |  |  | Increases the chance users say yes; lower priority.
P-48 | UI/UX | Show a visible 'your data is encrypted' cue in the app. | Plan |  |  | Reassures users their data is protected; low priority.
P-49 | UI/UX | Make form error messages appear at consistent moments across the app. | Plan |  |  | Small polish for a smoother experience; low priority.
P-50 | UI/UX | Define standard text styles for titles, body, and captions. | Plan |  |  | Keeps typography consistent; low priority.
P-51 | UI/UX | Check that layouts work for one-handed use and large text sizes. | Plan |  |  | A comfort and accessibility review (for users with disabilities); low priority.
P-52 | Growth | Send reminder nudges like 'you're near your dining budget'. | Plan | The plumbing exists; the reminder logic isn't built. |  | Drives people back into the app.
P-54 | Growth | Add younger, motivational framing and a simpler app-wide mode. | Plan |  |  | Makes the app approachable; only one screen has a plain toggle today.
P-55 | Growth | Add more game-like rewards, mini lessons, and shareable wins. | Plan |  |  | Boosts engagement through milestones and streaks.
P-56 | Growth | Add trends, a year-in-review, shareable reports, widgets, and a weekly summary. | Plan |  |  | Turns saved history into ongoing value for users.
P-57 | Quality | Translate the app's wording into other languages, not just the numbers. | Plan |  |  | Needed to reach non-English users; currency formatting already done.
P-58 | Quality | Confirm money and date formats display correctly on a real device. | Build | The formatting logic is wired; it just needs checking on an actual phone. |  | Ensures numbers look right everywhere.
P-61 | Quality | Safely upgrade saved data as new fields are added over time. | Plan |  |  | Prevents data problems when the app updates.
P-65 | Quality | Replace outdated app components with their current versions. | Plan |  |  | Keeps the app maintainable and future-proof; medium priority.
P-66 | Quality | Simplify the most tangled parts of the code, like the retirement and income screens. | Plan |  |  | Makes future changes safer and easier; lower priority.
P-67 | Quality | Remove unused and leftover old code. | Plan |  |  | Tidies up the app after launch; lower priority.
P-68 | Quality | Tighten up loose data typing to catch more bugs automatically. | Plan |  |  | Reduces hidden errors; lower priority.
P-69 | Quality | Require core calculations to stay well-tested before any code change ships. | Plan |  |  | Guards the most important math automatically.
P-70 | Quality | Make design consistency a required check before new code is merged. | Plan |  |  | The rules are written but not yet enforced.
P-72 | Other | Improve overall speed and make the app work well offline. | Plan |  |  | A broad, behind-the-scenes quality improvement.
P-74 | Other | Test the app across many real phone models in the cloud to catch device-specific bugs. | Plan |  |  | Ensures it works on the wide range of phones people own.