## Read me
WHAT THIS IS | Everything you have to answer for Net worth, Cash flow and Performance to be launch-ready — by file, tab and row, which is what you asked for. Every line is ONE thing to answer and says what it blocks.
WHAT "LAUNCH-READY" MEANS HERE, and it is your definition not mine | A figure is not finished because it is coded and tested. Your ladder is RULED → CODED → TESTED → VERIFIED, and only your mark makes a row VERIFIED. A test can prove a figure is what the code gives; it can never prove it is the figure you wanted. So every row of these three modules needs reading.
THE ORDER I WOULD TAKE IT IN | 1. The unanswered questions — they block figures from moving behind their doors. 2. The questions you asked that nobody answered — they are not decisions yet. 3. The decisions recorded in my words — quickest to clear, "as written" is a complete answer. 4. The VERIFIED marks — the longest, and the one nobody can do for you.
WHAT IS NOT ON THIS LIST | Anything I can do myself. I have not put "write the remaining tests" or "fix the classifier" here — those are mine. This is only what needs you.
IT IS REBUILT, NEVER EDITED | Generated by build-launch-answer-list.py from the master file, the decision log and the working plan as they are on disk. Re-run it and it is current; a stale checklist once sent you on a wild-goose chase.

## EVERYTHING
18 things to answer
# | Module | WHAT TO ANSWER | WHERE — file | WHERE — tab | WHERE — row | Which column to type in | What it blocks if you do not | YOUR ANSWER
1 | Net worth | Q34 — Approve the exact wording for the average-price rule (info dot + column Q): 'Shares with no recorded purchase price are left out of the average. N of your shares are in that position.' — and the refusal: 'Average not available — none of these shares has a recorded price.' | moneykeel_calc_master_calculation-master_v01.xlsx | networth | MK-NW-M-032 — Price paid (average) | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule.
2 | Net worth | Q35 — Approve the exact label and the canon phrase for the twelve-month window. Proposed: 'Dividends received (trailing twelve months)' here, and 'trailing twelve months' in the other four places (spelled out — no initialism). Q36 — Dividends on this card: THIS account only, matching 'Realized from sales' beside it? Recommended: yes. | moneykeel_calc_master_calculation-master_v01.xlsx | networth | MK-NW-M-034 — Dividends received (12 mo) | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule.
3 | Net worth | VERIFY 65 rows — read each row and mark it VERIFIED, or say what is wrong. Only your mark makes a row VERIFIED; my tests can say a figure is what the code gives, never that it is the figure you wanted. | moneykeel_calc_master_calculation-master_v01.xlsx | networth | all 65 unverified rows on this tab | ROW VERIFIED — founder, date and how | The module cannot be called launch-ready: a TESTED row is proved to match the code, not proved to be right.
4 | Performance | VERIFY 21 rows — read each row and mark it VERIFIED, or say what is wrong. Only your mark makes a row VERIFIED; my tests can say a figure is what the code gives, never that it is the figure you wanted. | moneykeel_calc_master_calculation-master_v01.xlsx | performance | all 21 unverified rows on this tab | ROW VERIFIED — founder, date and how | The module cannot be called launch-ready: a TESTED row is proved to match the code, not proved to be right.
5 | Cash flow | VERIFY 64 rows — read each row and mark it VERIFIED, or say what is wrong. Only your mark makes a row VERIFIED; my tests can say a figure is what the code gives, never that it is the figure you wanted. | moneykeel_calc_master_calculation-master_v01.xlsx | cashflow | all 64 unverified rows on this tab | ROW VERIFIED — founder, date and how | The module cannot be called launch-ready: a TESTED row is proved to match the code, not proved to be right.
6 | Net worth | A QUESTION YOU ASKED AND NOBODY ANSWERED: what does screen look like for manual update? | moneykeel_log_decisions_v01.xlsx | networth | DEC-0470 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
7 | Performance | A QUESTION YOU ASKED AND NOBODY ANSWERED: Total return captures both realized and unrealized gains? Is there any place we display realized P/L, unrealized P/L, total dividend, and total interest separately? | moneykeel_log_decisions_v01.xlsx | performance | DEC-0479 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
8 | Performance | A QUESTION YOU ASKED AND NOBODY ANSWERED: stocks with dividends - will it also show dividends received? | moneykeel_log_decisions_v01.xlsx | performance | DEC-0483 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
9 | Performance | A QUESTION YOU ASKED AND NOBODY ANSWERED: What's the level of details displayed and how?r | moneykeel_log_decisions_v01.xlsx | performance | DEC-0497 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
10 | Performance | A QUESTION YOU ASKED AND NOBODY ANSWERED: Invest: what level of detail, and how? | moneykeel_log_decisions_v01.xlsx | performance | DEC-0510 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
11 | Cash flow | A QUESTION YOU ASKED AND NOBODY ANSWERED: How is income + spending captured, at what frequency, and what about cash / unconnected cards? | moneykeel_log_decisions_v01.xlsx | cashflow | DEC-0503 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
12 | Cash flow | A QUESTION YOU ASKED AND NOBODY ANSWERED: Are the month bars cash flows -- inflow / outflow? | moneykeel_log_decisions_v01.xlsx | cashflow | DEC-0512 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
13 | Net worth | Commit — the branch was 278 files behind on 2026-09-14; committed since: 983805a (catch-up), f0e1d6d (Net worth v08), c4f2679 (the Since crash), 727e22a (Performance v14). Nothing is pushed — the branch taxonomy-v1.0.7 is local only. | moneykeel_calc_plan_workplan_v01.xlsx | Workplan | Commit — the branch was 278 files behind on 2026-09-14; committed sinc | Status / Comments | Founder: say when to PUSH. (Note 2026-09-26: the Xcode licence has not been accepted on this Mac, so the normal git refuses to run — "sudo xcodebuild -license accept" once, then git works everywhere again.)
14 | Cash flow | Stand-in ages when the birth year is missing: the Retirement cockpit and Insights assume 45, the cash-flow model and the draw steer assume 68, the onboarding helper 35 (or 65 for the retirement age). Your rule R2 says an unknown input gives no number and a reason. | moneykeel_calc_plan_workplan_v01.xlsx | Workplan | Stand-in ages when the birth year is missing: the Retirement cockpit a | Status / Comments | Founder: say what those screens show when the birth year is missing (ask for it in place? show the door?); then Claude: mock first, then code
15 | Cash flow | Q-CF-2 'how much have I spent this month, against the plan, and what is left' — eight figures DRAFTED on MK-CF-O-003 thisMonth: expected inflow, planned outflow, planned surplus, each planned line, inflow so far, outflow so far, surplus so far, each received line (MK-CF-M-047…054) | moneykeel_calc_plan_workplan_v01.xlsx | Workplan | Q-CF-2 'how much have I spent this month, against the plan, and what i | Status / Comments | Founder: read the eight rows on the master's cashflow tab (Row status says DRAFT) and say yes, or say what changes. Claude: the moment you do, the Cash flow screen, the month detail screen and Home's cell move behind the door and stop working figures out themselves
16 | Net worth | One door, one term: the three ways to add an account read 'Link it (read-only)', 'Add by hand' and 'Import from a file' on every screen, under the heading 'How do you want to add an account?' — Home, Sharpen your plan, the Plan tab, Net worth (first day and the add sheet), the Connect an account screen and Performance | moneykeel_calc_plan_workplan_v01.xlsx | Workplan | One door, one term: the three ways to add an account read 'Link it (re | Status / Comments | Founder: approve the mock MoneyKeel/documents/home-screen/moneykeel_pres_mock_ways-to-add-an-account_v10.html (every affected screen, before and after). Claude: then build all of it the same day, with the tests and the canon row
17 | Cash flow | Two word collisions found building v08: Cash flow's 'Add by hand' adds an EXPENSE (the same words as the account door), and Settings still says 'Disconnect' beside 'Linked accounts' | moneykeel_calc_plan_workplan_v01.xlsx | Workplan | Two word collisions found building v08: Cash flow's 'Add by hand' adds | Status / Comments | Founder: say whether Cash flow's door should read differently (for example 'Add an expense by hand') and whether Disconnect becomes 'Unlink'.
18 | Net worth | LAUNCH ANSWER LIST — 61 things need you for Net worth, Cash flow and Performance to be launch-ready | moneykeel_calc_plan_workplan_v01.xlsx | Workplan | LAUNCH ANSWER LIST — 61 things need you for Net worth, Cash flow and P | Status / Comments | His ask, 2026-09-29: ‘Give me a list of files, tabs, and rows I need to answer for NW, CF, Performance sections of the app to be complete.’ Open MoneyKeel/documents/other/moneykeel_calc_plan_launch-answer-list_v01.xlsx. Five tabs: Read me, EVERYTHING, and one per module. Every line names its FILE, i

## Net worth
7 things to answer for Net worth
# | Module | WHAT TO ANSWER | WHERE — file | WHERE — tab | WHERE — row | Which column to type in | What it blocks if you do not | YOUR ANSWER
1 | Net worth | Q34 — Approve the exact wording for the average-price rule (info dot + column Q): 'Shares with no recorded purchase price are left out of the average. N of your shares are in that position.' — and the refusal: 'Average not available — none of these shares has a recorded price.' | moneykeel_calc_master_calculation-master_v01.xlsx | networth | MK-NW-M-032 — Price paid (average) | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule.
2 | Net worth | Q35 — Approve the exact label and the canon phrase for the twelve-month window. Proposed: 'Dividends received (trailing twelve months)' here, and 'trailing twelve months' in the other four places (spelled out — no initialism). Q36 — Dividends on this card: THIS account only, matching 'Realized from sales' beside it? Recommended: yes. | moneykeel_calc_master_calculation-master_v01.xlsx | networth | MK-NW-M-034 — Dividends received (12 mo) | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule.
3 | Net worth | VERIFY 65 rows — read each row and mark it VERIFIED, or say what is wrong. Only your mark makes a row VERIFIED; my tests can say a figure is what the code gives, never that it is the figure you wanted. | moneykeel_calc_master_calculation-master_v01.xlsx | networth | all 65 unverified rows on this tab | ROW VERIFIED — founder, date and how | The module cannot be called launch-ready: a TESTED row is proved to match the code, not proved to be right.
6 | Net worth | A QUESTION YOU ASKED AND NOBODY ANSWERED: what does screen look like for manual update? | moneykeel_log_decisions_v01.xlsx | networth | DEC-0470 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
13 | Net worth | Commit — the branch was 278 files behind on 2026-09-14; committed since: 983805a (catch-up), f0e1d6d (Net worth v08), c4f2679 (the Since crash), 727e22a (Performance v14). Nothing is pushed — the branch taxonomy-v1.0.7 is local only. | moneykeel_calc_plan_workplan_v01.xlsx | Workplan | Commit — the branch was 278 files behind on 2026-09-14; committed sinc | Status / Comments | Founder: say when to PUSH. (Note 2026-09-26: the Xcode licence has not been accepted on this Mac, so the normal git refuses to run — "sudo xcodebuild -license accept" once, then git works everywhere again.)
16 | Net worth | One door, one term: the three ways to add an account read 'Link it (read-only)', 'Add by hand' and 'Import from a file' on every screen, under the heading 'How do you want to add an account?' — Home, Sharpen your plan, the Plan tab, Net worth (first day and the add sheet), the Connect an account screen and Performance | moneykeel_calc_plan_workplan_v01.xlsx | Workplan | One door, one term: the three ways to add an account read 'Link it (re | Status / Comments | Founder: approve the mock MoneyKeel/documents/home-screen/moneykeel_pres_mock_ways-to-add-an-account_v10.html (every affected screen, before and after). Claude: then build all of it the same day, with the tests and the canon row
18 | Net worth | LAUNCH ANSWER LIST — 61 things need you for Net worth, Cash flow and Performance to be launch-ready | moneykeel_calc_plan_workplan_v01.xlsx | Workplan | LAUNCH ANSWER LIST — 61 things need you for Net worth, Cash flow and P | Status / Comments | His ask, 2026-09-29: ‘Give me a list of files, tabs, and rows I need to answer for NW, CF, Performance sections of the app to be complete.’ Open MoneyKeel/documents/other/moneykeel_calc_plan_launch-answer-list_v01.xlsx. Five tabs: Read me, EVERYTHING, and one per module. Every line names its FILE, i

## Cash flow
6 things to answer for Cash flow
# | Module | WHAT TO ANSWER | WHERE — file | WHERE — tab | WHERE — row | Which column to type in | What it blocks if you do not | YOUR ANSWER
5 | Cash flow | VERIFY 64 rows — read each row and mark it VERIFIED, or say what is wrong. Only your mark makes a row VERIFIED; my tests can say a figure is what the code gives, never that it is the figure you wanted. | moneykeel_calc_master_calculation-master_v01.xlsx | cashflow | all 64 unverified rows on this tab | ROW VERIFIED — founder, date and how | The module cannot be called launch-ready: a TESTED row is proved to match the code, not proved to be right.
11 | Cash flow | A QUESTION YOU ASKED AND NOBODY ANSWERED: How is income + spending captured, at what frequency, and what about cash / unconnected cards? | moneykeel_log_decisions_v01.xlsx | cashflow | DEC-0503 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
12 | Cash flow | A QUESTION YOU ASKED AND NOBODY ANSWERED: Are the month bars cash flows -- inflow / outflow? | moneykeel_log_decisions_v01.xlsx | cashflow | DEC-0512 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
14 | Cash flow | Stand-in ages when the birth year is missing: the Retirement cockpit and Insights assume 45, the cash-flow model and the draw steer assume 68, the onboarding helper 35 (or 65 for the retirement age). Your rule R2 says an unknown input gives no number and a reason. | moneykeel_calc_plan_workplan_v01.xlsx | Workplan | Stand-in ages when the birth year is missing: the Retirement cockpit a | Status / Comments | Founder: say what those screens show when the birth year is missing (ask for it in place? show the door?); then Claude: mock first, then code
15 | Cash flow | Q-CF-2 'how much have I spent this month, against the plan, and what is left' — eight figures DRAFTED on MK-CF-O-003 thisMonth: expected inflow, planned outflow, planned surplus, each planned line, inflow so far, outflow so far, surplus so far, each received line (MK-CF-M-047…054) | moneykeel_calc_plan_workplan_v01.xlsx | Workplan | Q-CF-2 'how much have I spent this month, against the plan, and what i | Status / Comments | Founder: read the eight rows on the master's cashflow tab (Row status says DRAFT) and say yes, or say what changes. Claude: the moment you do, the Cash flow screen, the month detail screen and Home's cell move behind the door and stop working figures out themselves
17 | Cash flow | Two word collisions found building v08: Cash flow's 'Add by hand' adds an EXPENSE (the same words as the account door), and Settings still says 'Disconnect' beside 'Linked accounts' | moneykeel_calc_plan_workplan_v01.xlsx | Workplan | Two word collisions found building v08: Cash flow's 'Add by hand' adds | Status / Comments | Founder: say whether Cash flow's door should read differently (for example 'Add an expense by hand') and whether Disconnect becomes 'Unlink'.

## Performance
5 things to answer for Performance
# | Module | WHAT TO ANSWER | WHERE — file | WHERE — tab | WHERE — row | Which column to type in | What it blocks if you do not | YOUR ANSWER
4 | Performance | VERIFY 21 rows — read each row and mark it VERIFIED, or say what is wrong. Only your mark makes a row VERIFIED; my tests can say a figure is what the code gives, never that it is the figure you wanted. | moneykeel_calc_master_calculation-master_v01.xlsx | performance | all 21 unverified rows on this tab | ROW VERIFIED — founder, date and how | The module cannot be called launch-ready: a TESTED row is proved to match the code, not proved to be right.
7 | Performance | A QUESTION YOU ASKED AND NOBODY ANSWERED: Total return captures both realized and unrealized gains? Is there any place we display realized P/L, unrealized P/L, total dividend, and total interest separately? | moneykeel_log_decisions_v01.xlsx | performance | DEC-0479 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
8 | Performance | A QUESTION YOU ASKED AND NOBODY ANSWERED: stocks with dividends - will it also show dividends received? | moneykeel_log_decisions_v01.xlsx | performance | DEC-0483 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
9 | Performance | A QUESTION YOU ASKED AND NOBODY ANSWERED: What's the level of details displayed and how?r | moneykeel_log_decisions_v01.xlsx | performance | DEC-0497 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
10 | Performance | A QUESTION YOU ASKED AND NOBODY ANSWERED: Invest: what level of detail, and how? | moneykeel_log_decisions_v01.xlsx | performance | DEC-0510 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.