## Open Items & Backlog
ID | Category | Item | Priority | Status | Owner | Next step / detail
L-1 | Launch | Market-data licensing — replace the unofficial Yahoo endpoint with a licensed end-of-day vendor (Tiingo / EODHD / Twelve Data) | Blocker | Open | You + Eng | Pick a vendor + get an API key; then a ~1-file PriceProvider swap in marketData.ts. THE main remaining launch blocker.
L-2 | Launch | App Store listing — screenshots (6.7in/6.5in), description, keywords, category, age rating | Blocker | Open | You | Prepare in App Store Connect.
L-3 | Launch | App Privacy 'nutrition label' must match the privacy manifest (Email, Name, Financial info, Crash data; all app-functionality, no tracking) | Blocker | Open | You | Enter in App Store Connect; Apple cross-checks against the manifest.
L-4 | Launch | Reviewer demo login — a working email+password with sample data in the submission notes | Blocker | Open | You | Without it the reviewer can't get past login -> rejection.
L-5 | Launch | On-device test of new flows (delete account, recovery code, Face ID lock) | Blocker (verify) | In progress | You | TestFlight v1.0.1 build #22 uploaded 2026-06-20 (crypto fix); test once it finishes processing.
S-1 | Security/Privacy | Household / partner sharing under zero-knowledge encryption | Next-up | Open | Eng | Two passwords can't share one key today; fails safe (no crash). Restore via a shared key passed through the invite code (key-wrapping).
S-2 | Security/Privacy | Multi-factor authentication (MFA) | Later | Open | Eng | App lock + inactivity timeout already shipped; MFA is the remaining auth-hardening item.
S-3 | Security/Privacy | Sentry crash reporting — wire @sentry/react-native properly | Later | Open | Eng | Needs Metro config (getSentryExpoConfig) + Expo plugin + DSN. Global JS error handler already ships crash capture locally.
S-4 | Security/Privacy | Deploy the AI proxy (functions/) + set AI_PROXY_URL — or ship v1 without AI tips | Next-up | Open | You + Eng | Needs the Firebase Blaze plan. App already falls back to on-device tips.
S-5 | Security/Privacy | Dependency audit — triage 58 npm advisories (npm audit --omit=dev) | Later | Open | Eng | Almost all are build-time tooling, not shipped in the app.
A-1 | Accessibility | Per-screen screen-reader labels on the remaining ~26 screens | Next-up | Open | Eng/UI | Shared Button/controls, tab bar, TopBar, Home + new screens already labelled.
A-2 | Accessibility | Dark mode | Later | Open | UI
A-3 | Accessibility | Privacy-blur when the app is backgrounded | Later | Open | Eng | Hide financial data in the app switcher.
A-4 | Accessibility | Color-contrast audit (G-32) | Later | Open | UI
F-1 | Features | Receipt OCR native rebuild + test (ML Kit) | Next-up | Open | Eng | npx expo run:ios to activate, then test a real receipt.
F-2 | Features | Plaid bank / brokerage linking | Later | Open | Eng | Biggest stickiness lever; manual entry doesn't scale. Needs Plaid keys + a backend.
F-3 | Features | Savings goals — finish the waterfall-backed goals screen UI | Next-up | Open | Eng
F-4 | Features | Drawdown deeper tax-awareness (Roth conversions, capital-gains harvesting, catch-up) | Later | Open | Eng | Drawdown v1 shipped (withdrawal order, depletion age, RMDs).
F-5 | Features | Single-total vs categories spend reconciliation — one source of truth | Next-up | Open | Eng
F-6 | Features | Full string internationalization (translate copy, not just numbers) | Later | Open | Eng | Currency picker already reformats numbers.
F-7 | Features | Auto-derive dividends from ticker; ticker autocomplete; price-cache TTL | Later | Open | Eng | Perf v2 polish.
F-8 | Features | Life-stage gaps: 529 college planning, life/LTC insurance, estate/legacy | Later | Open | Eng
F-9 | Features | Push notifications (reminders/nudges) — plugin configured, needs APNs + logic | Later | Open | Eng
P-1 | Polish | Net-worth-over-time card on Home; runway / emergency-fund insight | Later | Open | UI
P-2 | Polish | Header + bottom tab bar redesign; legacy detail-screen redesigns | Later | Open | UI
I-1 | Infra | GitHub Pages 'pages build and deployment' workflow keeps failing | Later | Open | You/Eng | Harmless; disable Pages in repo settings or fix the Jekyll build over docs/.

## Bug Ledger (all)
ID | Severity | Area | Description | Status | Resolution / notes
B-15 | HIGH | Onboarding→Net Worth | Re-running onboarding never updates Net Worth accounts; stale balances drive retirement math | fixed 2026-06-12 | 0
B-16 | HIGH | Onboarding restart | restartOnboarding wiped ALL asset accounts/liabilities incl. user-created ones, contradicting its own comment | fixed 2026-06-12 | Same origin-tag mechanism: restart clears only origin: 'onboarding' rows
B-17 | LOW | Income gate | Gate is on source selection, not amounts — but $0 amounts still yield $0 income, so selection alone can't fabricate income | by-design | Verified harmless; gate correctly blocks the working-40yo future-SS leak both ways
B-18 | MED | Market data | Network failure, invalid ticker, and malformed response all silently return null → stale cached prices shown with no staleness indicator, no retry, no ticker validation | fixed 2026-06-13 | Performance screen shows price freshness ("updated Nh ago" / "⚠ may be out of date · tap Refresh" past ~4 days) + flags implausible tickers in the holding editor. (Offline-vs-invalid distinction is a deeper provider refactor, left noted.)
B-19 | MED | Net worth accuracy | Position with a ticker missing from the price cache contributes $0 to account balance → silent net-worth understatement | fixed 2026-06-13 | recomputeBalances falls back to costBasis(p) when the live price is absent, instead of $0
B-20 | LOW | Goals capacity | Negative capacity (invest > surplus) — divide-by-negative risk in months-to-goal | by-design | Verified guarded; negative capacity passes through for display but never divides
B-21 | LOW | Onboarding seeding | Explicit $0 answers for retirement savings / holdings created no account at all (vs. a $0 account the user could edit later) | fixed 2026-06-13 | add now keys on field PRESENCE not value: an answered field (incl. explicit '0') seeds a $0 placeholder; an absent field (e.g. currentSavingsPortfolio in the accumulation flow) is still skipped. AssetSheet save relaxed to amt >= 0 so $0 accounts can be added/kept. Assets only — liabilities/goals/income still drop $0 (a $0 placeholder there is clutter)
B-22 | LOW | Retirement solver | Suspected non-monotonic solveRetireAge results from per-iteration rounding | closed — not a bug | Probe ran across 6 balance levels (100k→3.2M): strictly monotonic; rounding happens only on outputs
B-23 | LOW | Currency | A Settings currency picker let users choose EUR/GBP/INR/etc., but all tax & retirement math is hardcoded US (federal brackets, 401k/IRA/HSA limits, RMD age 73, 529s, single-filer) — picking a non-USD currency only swapped the symbol while still applying US tax math | fixed 2026-06-13 | Removed the currency picker; app/_layout.tsx forces setMoneyFormat('USD','en-US') so a stale synced currency can't desync the formatter. Currency plumbing (money.ts/CURRENCIES/store fields/setCurrency) left dormant for a future per-country tax epic. The ~500 hardcoded $ and AmountText's USD hardcode are now correct, so untouched (avoids needless churn)
B-24 | MED | Budget/Goals consistency | User states total spend AND itemizes part of it → month grid honored the full total, but projected_to_save (→ goal capacity) only saw the categorized part; goal pool overstated free cash by the uncategorized remainder | fixed 2026-06-13 | monthly_spending: max(bucket total, monthlySpending) — budget surplus now equals the month-grid savings; goal capacity no longer overstated
B-25 | LOW | Economic data | Fallback inflation/treasury values (BLS/Treasury outage) carry no flag, so projections silently run on defaults and the UI can't label them as estimates | fixed 2026-06-13 | Added per-source inflationIsFallback/treasuryIsFallback flags + exported FALLBACK_ constants. (fetchEconomicData isn't wired into the UI yet, so no live surface needed)
B-28 | MED | Goals/Plan tab | "Typical free cash to save $17,250/mo" = income BEFORE spending; true free cash $2,250/mo | fixed 2026-06-13 | Switched to savingsByMonth(op) (income − spend). Sim now shows negative lean months (impossible with the income grid), confirming the fix
B-29 | MED | Goals handoff | Onboarding goals (2 set) never appear on Plan tab ("No goals yet"); Sharpen checklist nags "Add a goal" | fixed 2026-06-13 | New seedGoals(op) store action (origin-tagged, seed-once via goalsSeeded, restart clears+re-seeds, manual goals preserved). Called at onboarding finish AND on Plan-tab mount. Verified live: Jane's Emergency fund $36k + House $45k now show
B-30 | LOW | DTI guideline | Mortgage holder graded with renter guideline (20% → "High" at 33% instead of homeowner 36%) | fixed 2026-06-13 | New inferDebtType(label) maps Mortgage→MORTGAGE, Car→AUTO, Student→STUDENT_LOAN, etc.; GoalsScreen homeowner check now true for a mortgage → 36% guideline
B-31 | HIGH | Retirement handoff | Cockpit computes with $0 guaranteed income and asks "Are you eligible?" although onboarding captured ri_ss $2,000 + ri_pension $1,500; pension never consumed at all; snapshot surfaces DO count it → contradictory advice ("keep saving $3,775/mo") | fixed 2026-06-13 | Guaranteed default now retirementIncomeMonthly(op) (ss+pension+annuities…); unset eligibility falls back to that figure (only explicit "Not eligible" zeroes it); row relabeled "Social Security & pension" and shows the amount "from your setup"
B-32 | LOW | Retirement copy | "You plan to spend $8,288/mo" — user said $15,000; Portugal COL ×0.6 applied silently on the cockpit | fixed 2026-06-13 | Cockpit now shows "Adjusted for Portugal's cost of living (40% lower than the US)" when a recognized location moves the figure; US/factor-1 shows no note
B-33 | MED | Stress test | Same screen said "$3,000 hit puts you in the red" AND "✓ you already have 3 months of essentials — strong cushion" | fixed 2026-06-13 | monthlyEssentials falls back to max(bucket total, monthlySpending) when uncategorized; gapToFund now positive so the screen shows the real shortfall, not "strong cushion"
B-34 | HIGH | Income accuracy | IncomeState salary = max(salaryByMonth)×12 — six $0 months ignored → Home take-home, IncomeDetail gross/net, Budget projected_to_save, and one-pool goal capacity all overstated (~$60k/yr gross for Jane); tax organizer & bill calendar use the true table → screens contradict | fixed 2026-06-12 | Booked salaryAnnual(op)/12 (and tipsAnnual(op)/12) as MONTHLY so the total equals the real table sum and matches totalGrossAnnual; employer-match annualization preserved. Verified: Jane IncomeState 336,510 → 276,510 = totalGrossAnnual
B-35 | MED | Tax organizer | 2026 taxable income included $42,000 SS/pension the (non-retired) user does not receive — the SS-leak gate was bypassed on this screen | fixed 2026-06-13 | Switched to currentRetirementIncomeMonthly (same gate as the rest of the app); working person's taxable total unchanged by future SS, retiree still reports it
B-36 | LOW | Tool prefills | Insurance check (savings/assets $0 → "$3.5M gap" for a 74yo with $1.75M), Roth converter (pre-tax $0 despite known $250k; misleading zero-state message) | fixed 2026-06-13 | Insurance prefills savings/assets from investableValue; Roth pre-tax balance filter fixed PRE_TAX (was a non-existent 'RETIREMENT' bucket → always $0)
B-37 | MED | Retirement framing | Retiree cockpit showed accumulation framing ("Grow my nest egg · assumes age 65") for a retired 74yo, contradicting Home's "drawdown" focus | fixed 2026-06-13 | Retiree's retire-age default is now their current age (not 65); plan divider shows "in retirement" and the return label "Assumed return on what's left" when retired. (Drawdown heroes/section already gated on isRetired.)
B-38 | MED | Retirement realism | RMDs (forced withdrawals age 73+) are computed in decumulation but simulate() never forces them — post-73 mandatory withdrawals & their tax drag aren't modeled in the Monte Carlo | fixed (transparency) 2026-06-13 | The drawdown view already shows RMDs ($/yr from age 73, "taxed whether you need it or not"); added that the success-chance figure tracks balances BEFORE tax, so set aside for the tax. (Modeling RMD tax inside the MC needs a retirement-tax-rate assumption — deferred to avoid churn in a sensitive engine.)
B-39 | MED | Retirement realism | Retirement projection ignores liabilities — it implicitly assumes debt-free at retirement; a user with a mortgage sees an over-optimistic "needed" | fixed (transparency) 2026-06-13 | screens_deep.test.tsx "user with debt sees the note". A user with debt is now told the projection assumes debt is covered within spending — include an ongoing mortgage payment in the spend figure (rather than silently assuming debt-free).
B-40 | MED | Edit-back coupling | Income/cashflow read raw onboardingProfile, so editing income after onboarding doesn't reflect unless the edit writes back into op — Net Worth/Budget edits write their own store arrays that income/cashflow don't read | fixed 2026-06-13 | IncomeManager writes edits back to onboardingProfile (verified); fixed the concrete gap where editing base pay to a flat amount left a per-month salary table in place (table takes precedence → edit was silently ignored) — now clears salaryByMonth
B-41 | LOW | Goals feedback | goals.waterfall() recommends a funding order but nothing records what actually got funded — suggestion-only, no feedback loop | closed — not a bug | Verified 2026-06-13: waterfall() is defined+tested but NOT imported/rendered by any screen, so there is no user-facing "suggestion without feedback" gap. Available for future use
B-42 | LOW | Legacy field | Legacy debts array still present in store (useStore.ts:208,395) alongside canonical liabilities; @deprecated + migration landing, not yet removed | deferred | Not a user-facing bug: @deprecated, unsynced, and BudgetScreen migrates it into liabilities on mount. It IS the migration landing spot — removing it now would drop legacy data and benefits nobody. Remove post-launch once no legacy data exists
B-43 | LOW | Transaction UI | TransactionSheet account chips render identically when two accounts share a name (no kind/last-4 disambiguator) | fixed 2026-06-13 | Transaction-sheet chips append the asset kind (or id last-4) when two accounts share a name; smoke-rendered
B-44 | LOW | Copy | "Your cash covers about 0.0 months of spending" reads robotically and alarms a user with large liquid investments but $0 in a cash bucket | fixed 2026-06-13 | Insights + Net Worth runway say "No cash set aside" at ~0 and note investments aren't counted
B-45 | LOW | Copy | "86% of your portfolio is a single position" — it's a single account, not a holding | fixed 2026-06-13 | Retitled "Concentrated in one account"; topHoldingPct→topAccountPct; body says add holdings + spread across accounts
B-46 | LOW | Copy | Tips screen "This month at a glance: Income $0.00" contradicts a declared-$276k user; also uses cents against the app-wide whole-dollar style | fixed 2026-06-13 | Added "From what you've logged this month — not your full income or budget" subtitle
B-47 | LOW | Copy | Student's $400/mo parental support labeled "Child support / alimony" in the income manager | closed — not a bug | Verified 2026-06-13: label is consistent with the question; the persona fixture mis-used the field. (Minor future enhancement: a dedicated "family/parental support" field — not a defect)
B-48 | LOW | Copy | "Room left in your 401(k)" nudge shown to users with no earned income (retiree, gig) | fixed 2026-06-13 | Added hasEarnedIncome (salaryAnnual > 0) gate to the rule
B-49 | MED-HIGH | Cross-module: assets basis | buildSnapshot derives net worth + retirement start_balance from assetsFromOnboarding(op) (onboarding answers), but the Net Worth screen, TopBar chip, and Retirement cockpit use the LIVE store.assetAccounts. After any account add/edit/delete, the two bases diverge — Home's "Net worth · see all plans" (op) ≠ TopBar chip (accounts); Home retirement outlook (op) ≠ cockpit nest egg (accounts) | fixed 2026-06-20 (verified) | RESOLVED by the resolveNetWorthRows refactor: buildSnapshot now REQUIRES explicit account/liability rows (no silent op fallback), and Home, TopBar, and the Retirement cockpit all derive rows from resolveNetWorthRows (live store accounts once seeded/non-empty; nest egg = retirementEarmarkedValue of those same rows). One basis everywhere. Locked by tests: home_integration.test.ts, journeys.test.ts (B-49), portfolio_usecases.test.ts (nest-egg basis), invariants.test.ts (retirement starts from the same total the NW chip shows).
B-50 | MED | Cross-module: emergency runway | The emergency-fund runway ("cash covers X months") uses spendBuckets.monthly_total | InsightsScreen.tsx:26 + NetWorthScreen.tsx:70 use the old bucket\ | \
B-51 | MED | Cross-module: toxic-debt threshold | "High-interest/toxic debt" is defined with 3 thresholds: insights "toxic-debt" rule fires at APR > 10% (InsightsScreen.tsx:36), but the debt module's toxic_debt_balance and the Net Worth "costliest" use > 7% (debt/index.ts:124, NetWorthScreen.tsx:80). An 8% debt is flagged toxic in Net Worth + counted in toxic_debt_balance, yet the Home "tackle high-interest debt" insight stays silent | fixed 2026-06-13 | Exported TOXIC_APR (0.07) from debt module; Insights + Net Worth now import it (was a hardcoded 0.10 in Insights). One threshold everywhere
B-52 | LOW-MED | Cross-module: "savings rate" | Two different numbers carry the name "savings rate": budget savings_rate_pct = (net income − spending)/net income (21.9% for the audit persona), while the insight's savingsRate = retirement contributions/gross (8.75%). Same term, ~2.5× apart → confusing | fixed 2026-06-20 | Disambiguated: the Insights metric was renamed savingsRate→investRate and now reads "investing X% of your gross income toward retirement" (insights/index.ts invest-rate rule). The Analytics "Savings rate" stat is now labelled "Savings rate (of take-home)" with a caption ("Share of your take-home pay you keep; investing as a % of gross is shown in Insights"), and the avg / by-month labels say "(take-home)". Two clearly distinct numbers, two clearly distinct labels.
B-53 | CRITICAL | Security | Firestore rules let ANY signed-in user read/write ANY other user's data: isHouseholdMember(victim) only checked the caller's own doc householdId == victim, and a user can write their own doc freely → setting householdId=<victimUID> self-granted full access. Invite-code gate existed only in client code, not rules | fixed + DEPLOYED 2026-06-17 | Grant now owner-side + invite-bound: join via households/{owner}/members/{me} carrying a code the rules verify; access gated on that member doc. 8/8 emulator tests; deployed to finwise-app-jj
B-54 | HIGH | Cross-module: nest egg | Retirement cockpit showed $0 nest egg despite $2.5M net worth — read empty legacy store.savings/store.investments arrays instead of the seeded earmarked accounts the Home NW box uses (a 3rd assets source; cousin of B-49) | fixed 2026-06-17 (ba999c1) | Cockpit now reads resolveNetWorthRows(uid, op, nwSeeded, assetAccounts, liabilities).accounts → retirementEarmarkedValue(...), same seeded source as Home
B-55 | MED | Income/tax | Onboarding cash-flow recap (retired) used gross retirement income ($24,333) while the spending-plan step used take-home ($18,889); "left over" computed off pre-tax → screens disagreed | monthlyIncome(a) (gross first) vs spending plan's net-first | retired-persona test 2026-06-17
B-56 | MED | Retirement | Legacy bequest (the "leave to heirs" target) was ignored in the drawdown — "will it last" drew down the full nest egg, not the spendable remainder | fixed 2026-06-17 (ba999c1) | New spendableEgg = max(0, nestEgg − legacyTarget) threaded into the retired chance/withdrawal/depletion calcs; verdict shows the reserve
B-57 | HIGH | Build / native | react-native-worklets peer dep missing (required by reanimated v4) → app can crash outside Expo Go, i.e. in the TestFlight/production build (passes in dev) | fixed 2026-06-17 (a99e2aa) | npx expo install react-native-worklets (0.8.3); babel-preset-expo auto-wires the plugin
B-58 | MED | Retirement / decumulation | Suggested withdrawal order was static, not RMD-aware — withdrawalOrder(split) ignored age, listing pre-tax last even for an 80-year-old whom RMDs legally force to withdraw from pre-tax FIRST | fixed 2026-06-17 | Added age param; for age≥73 with pre-tax, prepends a mandatory RMD step (amount = rmdAtAge), pre-tax step relabeled "the rest"; under-73 unchanged
B-59 | LOW-MED | Copy (age-blind) | Retirement "Heads-up" copy was static & ignored age — "Medicare starts at 65" shown to an 80-year-old; RMD note said "start at 73 / first year" for someone a decade past RMD age | fixed 2026-06-17 | Copy now branches on age: ≥65 → "you're on Medicare … watch IRMAA"; ≥73 → "RMDs apply now — you must withdraw ~$X this year". (Pattern flag: audit other screens for age-blind static copy)
B-60 | HIGH | Data loss: assets balance | Adding one holding to a manual-balance account to track its performance collapsed the whole account to that one holding — a ~$2.2M Fidelity total dropped to $179k (the single stock) after a price refresh. Any account with ≥1 position was treated as fully position-derived | cash_balance!=null, then overwrote balance = cash + Σpositions | store_prices.test.ts "manual-balance account with a partially-tracked holding (B-60)" (3 cases)
B-61 | LOW | UX / discoverability | Tax organizer buried deep in the Plan-screen module grid despite being a critical feature for many users | fixed 2026-06-18 (dd506fe) | Added a global Tax organizer chip stacked under the NW chip in TopBar — visible on every tab page; equal-sized to the NW chip. TopBar.test.tsx covers its navigation
B-62 | LOW | UX / layout | Bill calendar was a standalone card on Home, separate from the quick-action "focus" box | fixed 2026-06-18 (dd506fe) | Moved Bill calendar into the persona focus box (all personas); removed the standalone card
B-63 | LOW | UX / layout | Retire drawdown showed "Where your money sits" and "Suggested withdrawal order" as two separate cards | fixed 2026-06-18 (dd506fe) | Combined into one card split by a divider
B-64 | MED | Transparency | Retire "Suggested withdrawal order" showed an RMD of ~$26K with no derivation; steps 2–4 showed full bucket balances, so a user couldn't tell where $26K came from or whether it double-counted the pre-tax bucket | fixed 2026-06-18 (dd506fe) | RMD step now shows "= your $X pre-tax ÷ <IRS life-expectancy factor> at age N" + a note that the bucket amounts are balances while the RMD is just this-year's required slice of pre-tax (not money on top)
B-65 | LOW | UI layout | Retire "Your investments" table — the "Your 12-mo" and "Benchmark" column headers had no gap and ran together | fixed 2026-06-18 (dd506fe) | Added gap:14 to the header + data rows so the two numeric columns separate
B-66 | LOW | UX / layout | Net Worth — "Portfolio performance", "Bonds", "Other investments" rendered as three loose cards floating mid-screen, feeling out of place | fixed 2026-06-18 (dd506fe) | Grouped into one "Explore your holdings" box with dividers

## Shipped 2026-06
Item | Area | Status | Detail
Zero-knowledge cloud encryption | Security | Shipped | Financial data AES-256 encrypted on-device (password-derived key, never sent) before sync; Firestore stores only ciphertext.
Recovery code | Security | Shipped | Wrapped-key model; unlocks data after a forgotten-password reset, re-locks under new password. Shown at signup; regenerate in Settings.
In-app account deletion | Compliance | Shipped | Settings -> Delete account (re-auth -> wipes Firestore + Auth). App Store 5.1.1(v).
Biometric app lock | Security | Shipped | Face ID / Touch ID / passcode + 2-min background auto-relock; Settings toggle.
Apple Privacy Manifest | Compliance | Shipped | ios.privacyManifests — no tracking; data types declared.
Hardened auth | Security | Shipped | Removed plaintext-password store; anti-enumeration messaging.
AI provider key moved server-side | Security | Shipped | Anthropic/Vision keys no longer bundled; configurable proxy (functions/aiTips).
Accessibility labels (start) | Accessibility | Shipped | Screen-reader labels on shared controls, tab bar, TopBar, Home, back button; 44pt targets.
Formal QA suite + CI fix | Quality | Shipped | 587 tests incl. golden scenarios + precision guards; CI green (Java 21 fix for the rules job).
RN secure-random fix | Security | Shipped | react-native-get-random-values polyfill so CryptoJS works on-device (signup crash fix); makes local encryption actually take too.
B-49 assets-basis divergence | Bug fix | Fixed | All surfaces use resolveNetWorthRows -> one net-worth/nest-egg basis; locked by tests.
B-52 'savings rate' ambiguity | Bug fix | Fixed | Insight = 'investing % of gross'; Analytics = 'Savings rate (of take-home)' + caption.
TestFlight build v1.0.1 (#22) | Launch | Done | Built on EAS + auto-submitted to TestFlight 2026-06-20.