## Modules
Module | Route | Screen file | Approved design | The design, and where it stands | Design work owed | One term per concept | Precision (Q49) | Empty state (Q48) | MoneyKeel top bar | Figures declared by identifier (rule 11) | Orchestrator questions | Behind a door? | Rulings touching it | Test files | Open workplan rows | What happens next
Home | /home | src/screens/HomeScreen.tsx | NOT RECORDED | No approved design on file. The record names Home, Cash flow and every pushed screen as still needing their Build 53 design traced. | — | PASSES in the code — the canon guard scans every string and comment in src/ and MoneyKeel/functions: 0 retired words app-wide. | CHECK — pctToOneDp prints the hero return to ONE decimal (HomeScreen.tsx:571); Q49 says two unless the figure’s row states otherwise. | 3 EmptyNote doors | YES (tab screen) | 0 declared · 13 still printed without one | Q-PF-1, Q-PL-1, Q-CF-1, Q-CF-2, Q-CF-4, Q-HM-1 | NO — every Map row is still PROPOSED; no question anywhere has moved behind a door | 4 | 30 | 4 | Trace its Build 53 design and record it, then mock it like the others. It reads six questions — more than any other tab — so it moves last, after those doors exist.
Net worth | /analytics | src/screens/NetWorthScreen.tsx | APPROVED AND BUILT | moneykeel_pres_mock_net-worth-quiet-instrument_v08.html — approved 2026-09-14 ("approved"), built the same day (f0e1d6d). | v09 owed: with no accounts but past day one, the empty groups still repeat "Add your accounts ›" | PASSES in the code. Its MOCK (v08) is clean too — its only hits are the change notes quoting the retired words on purpose ("EMERGENCY CUSHION becomes EMERGENCY FUND"). | CHECK — the debt APR prints to one decimal (:480) and the cushion prints "N.N months" (:921). The APR is a rate (two decimals); months has no stated precision on its row. | 5 EmptyNote doors — the seeded-empty frame still duplicates (v09 owed) | YES (tab screen) | 0 declared · 51 still printed without one | Q-NW-5, Q-PL-1 | NO — every Map row is still PROPOSED; no question anywhere has moved behind a door | 6 | 29 | 6 | v09 for the seeded-empty duplication; otherwise it waits for its doors (Q-NW-1..5 are all still PROPOSED).
Performance | /invest | src/screens/PerformanceScreen.tsx | APPROVED AND BUILT | moneykeel_pres_mock_performance_v14.html — approved 2026-09-25 ("approved. save and built it"), built the same day (727e22a). | — | PASSES in the code, and its mock (v14) is clean in the drawn frames. | PASSES — every percent goes through one pct() at two decimals; the only one-decimal figures are a sentence ("2.0 years") and SVG coordinates. | 2 — the one line, and it opens the three ways to add an account (built 2026-09-25) | YES (tab screen) | 0 declared · 24 still printed without one | Q-PF-1 | NO — every Map row is still PROPOSED; no question anywhere has moved behind a door | 7 | 18 | 4 | Nothing for the design. It carries a recorded debt: Q-PF-1 is still PROPOSED, so this screen moves behind its door later.
Cash flow | /cashflow | src/screens/CashFlowScreen.tsx | NOT RECORDED | No approved design on file. Two word collisions found on 2026-09-14 are still open ("Add by hand" adds an EXPENSE here; "Disconnect"). | — | PASSES in the code. Its MOCK (this-month v06) still draws "In (take-home)" and "spending". | PASSES — no one-decimal rounding in the file. | 10 EmptyNote doors | YES (tab screen) | 0 declared · 44 still printed without one | Q-PL-1, Q-PL-2, Q-PL-6, Q-CF-1, Q-CF-2, Q-CF-3 | NO — every Map row is still PROPOSED; no question anywhere has moved behind a door | 2 | 20 | 6 | Trace and record its design; settle the two word collisions; then its doors (Q-CF-1..4).
Plan | /plan | src/screens/PlanHubScreen.tsx | APPROVED, NOT BUILT | moneykeel_pres_mock_plan_v05.html — the v4 design approved 2026-08-14, filed into the structure 2026-09-26. The tab still shows the 2026-08-12 layout the founder rejected. | 8 questions + 5 blockers open in the mock; "Your plan at a glance" never built | PASSES in the code. Its MOCK (v05) still draws retired words — the odds said "out of 10" not out of 100, "spending", "/mo", "%/yr", "$X a month". Listed as mark 14 in the file; fixed when v06 is drawn. | CHECK — the withdrawal rate prints to one decimal in two places (PlanHubScreen.tsx:332,337). | 2 — day one is drawn in the design but not built | YES (tab screen). Pushed screens still lack it — Account detail got it 2026-09-25; the rest is a row waiting on the founder. | 0 declared · 17 still printed without one | Q-PL-1, Q-PL-2 | NO — every Map row is still PROPOSED; no question anywhere has moved behind a door | 4 | 22 | 23 | The founder answers Q1–Q8 → v06 → approval. The CODE waits for MK-PL-O-001 (Q-PL-1) and the Q-PL-2 door, so the tab is built once.

## Read me
Field | What it means, and where it came from
What this is | The five modules of the app — the five tabs — against every standard and every piece of machinery that came after they were built. One row per module on "Modules"; the evidence behind each column is named here so any figure can be checked.
Written | 2026-09-26, at the founder’s ask: "remind me of the five parent modules — which ones we have finalized, and where do they stand against new requirements".
The five modules | Home · Net worth · Performance · Cash flow · Plan. Everything else in the app is a screen opened FROM one of these.
Approved design | Read from MoneyKeel/documents/standards/moneykeel_pres_spec_design-each-screen-was-built-from_v01.md — the record of which design each screen was built from, and which is current.
One term per concept | src/__tests__/one_term_per_concept.test.ts reads the canon table and scans every string, template and comment in src/ and MoneyKeel/functions. It passes: 0 retired words. It does NOT scan the mocks — five approved mocks still carry retired words, which is its own workplan row.
Precision (Q49) | Measured, not assumed: every one-decimal rounding in each screen file was opened and read. "CHECK" means a figure prints to one decimal where the standard says two, and its master row has not been checked for a stated exception.
Empty state (Q48) | Counted from EmptyNote in each screen file.
Figures declared by identifier | Rule 11 is PROPOSED, not adopted. "declared" is from the figure census (moneykeel_figure_census.json); "printed without one" is the undeclared-figures ratchet, which may only fall.
Orchestrator questions | From the Map tab of moneykeel_calc_spec_orchestrator-map_v01.xlsx — the questions whose figures appear on that tab. Every Map row is still marked PROPOSED: no question in the app has moved behind a door.
Tests · rulings · open rows | Test files that name the screen; rulings in the ledger whose rows name it; workplan rows naming it that are not DONE.
What it does NOT say | Nothing here is a verdict on whether the numbers are right. That is the master file’s job: 109 open findings and 42 questions for the founder sit across all five.

## Findings
# | Kind | Module | What was found | Why it matters | What to do
F-1 | Precision | Home | The hero return prints to ONE decimal — pctToOneDp (HomeScreen.tsx:571), used by the "▲ up $X (Y%)" line and the you-vs-market line. | Q49 says a percent shows two decimals unless the figure’s row states otherwise. Performance was corrected on 2026-09-25; Home was not looked at. | Open the two figures’ master rows; if neither states one decimal, make them two.
F-2 | Precision | Net worth | The debt APR prints to one decimal (:480), and the cushion prints "N.N months" (:921). | A rate is two decimals under Q49. "Months" has no stated precision anywhere, which the standard says must be stated on the figure’s row. | Same check; state the months precision on its row or round it.
F-3 | Precision | Plan | The withdrawal rate prints to one decimal in two places (PlanHubScreen.tsx:332, 337). | Same rule. | Fold into the Plan build rather than touching the rejected layout now.
F-4 | Rule 11 | All five | NOT ONE of the five tabs declares a single figure by identifier. 149 figures across them are printed without one (Home 13 · Net worth 51 · Performance 24 · Cash flow 44 · Plan 17). | Rule 11 is proposed and unadopted, so this is expected — but it is the gap between "the master says it" and "the screen proves it". | Falls out of the orchestrator work: a door declares its figures, the screen prints only by identifier.
F-5 | Design record | Home, Cash flow | Neither has a recorded approved design. Home reads six questions — more than any other tab. | The record exists precisely because this was lost once already (Build 53). | Trace both from the Build 53 commit the same way Net worth and Performance were traced.
F-6 | Debt | Performance | Built to its approved design on 2026-09-25 while Q-PF-1 is still PROPOSED, so the screen will move behind its door later. | Recorded so it is not discovered later as a surprise. | Move it with phase 5, by blast radius.
F-7 | One term | Mocks | Eight LIVE mocks still DRAW retired words: cash-flow this-month v06, income end-to-end v07, look-ahead v03, money-four-tabs v01, account-detail v01, empty-state-pattern v01, filing-status v02, and plan v05. The workplan said five; measured on 2026-09-26 over the drawn frames only, it is eight. | No SCREEN carries them — the code guard passes. But a mock is the spec a screen is built from, so a stale mock quietly re-introduces a retired word at the next build. | Founder: say whether each gets a new version now or at its next change (already a workplan row). Plan v05 is listed in the file itself as mark 14 and is fixed when v06 is drawn.

## What is open
Module | Status | The row | What it waits on
Home | WAITING ON YOU | One door, one term: the three ways to add an account read 'Link it (read-only)', 'Add by hand' and 'Import from a file' on every screen, under the heading 'How do you want to add an account?' — Home, Sharpen your plan, the Plan tab, Net worth (first day and the add sheet), the Connect an account screen and Performance | Founder: approve the mock MoneyKeel/documents/home-screen/moneykeel_pres_mock_ways-to-add-an-account_v10.html (every affected screen, before and after). Claude: then build all of it the same day, with the tests and the canon row
Home | WAITING ON YOU | The retirement sentence (Net worth, Plan, Home) prints future dollars without saying so, and the odds calculation charges no tax on withdrawals from taxable accounts — found checking the founder's question on v07 ($4.1M at 65 is about $2.0M in today's money) | Founder: say whether to show today's money and to tax taxable withdrawals (recommended). Claude: then write both as findings on the master rows (MK-XS-M-002 and the pot/leftover figures) before any code.
Home | WAITING ON YOU | With the odds exact, the Retirement cockpit disagrees with Home and the Plan tab for the same household: the working household reads 13.3% in the cockpit and 13.9% on Home and Plan; the retired household reads 87.8 out of 100 in the cockpit and 93.2% on Home and Plan (it was 90 against 95 before, so that one was already visible). Rounding to 5 hid the first. | Claude: find which input the cockpit builds differently from willItLastInputs, and fix it in the Plan step, with a screens-agree check covering the cockpit. Founder: nothing, unless you want it before Plan.
Home | WAITING ON YOU | SEQUENCING DECISION — is the Plan tab’s CODE built against its doors (MK-PL-O-001 thePlan for Q-PL-1, and the Q-PL-2 door) or in front of them? Built in front, the screen is built twice and can still disagree with Home about the same household — which is what it does today (13.3 vs 13.9; 87.8 vs 93.2). | Founder: say which. Claude’s recommendation 2026-09-26: finish the Plan DESIGN now (no code), then the pilot, then Q-PL-1 and Q-PL-2 behind their doors, then build the Plan tab once against them.
Net worth | WAITING ON YOU | Commit — the branch was 278 files behind on 2026-09-14; committed since: 983805a (catch-up), f0e1d6d (Net worth v08), c4f2679 (the Since crash), 727e22a (Performance v14). Nothing is pushed — the branch taxonomy-v1.0.7 is local only. | Founder: say when to PUSH. (Note 2026-09-26: the Xcode licence has not been accepted on this Mac, so the normal git refuses to run — "sudo xcodebuild -license accept" once, then git works everywhere again.)
Net worth | WAITING ON YOU | One door, one term: the three ways to add an account read 'Link it (read-only)', 'Add by hand' and 'Import from a file' on every screen, under the heading 'How do you want to add an account?' — Home, Sharpen your plan, the Plan tab, Net worth (first day and the add sheet), the Connect an account screen and Performance | Founder: approve the mock MoneyKeel/documents/home-screen/moneykeel_pres_mock_ways-to-add-an-account_v10.html (every affected screen, before and after). Claude: then build all of it the same day, with the tests and the canon row
Net worth | WAITING ON YOU | Nothing recorded which design each screen was built from. The Build 53 Net worth and Performance finals (networth-FINAL.html, performance-FINAL.html, the two Net worth PDFs, Net worth screens 01 to 11) were filed under networth-and-performance/archive/ on 2026-09-01, which marks them replaced. They were not replaced. Six hours of mocks then started from the wrong files. CORRECTION 2026-09-14: Buil | Claude: done 2026-09-14 — Build 53 files matched by exact content and recorded in MoneyKeel/documents/standards/moneykeel_pres_spec_design-each-screen-was-built-from_v01.md. Founder: (1) confirm Net worth = v5 + square corners; (2) say whether to draw Net worth v6 from the Build 53 code (v5 with squ
Net worth | WAITING ON YOU | Net worth v07 — the three ways to add an account on Net worth (first day, the add sheet, the add button), plus every ruling since Build 53 that touches the screen (empty state, Debts, Emergency fund, Stocks / Funds, /month, you entered, expenses, odds to the nearest 5), each marked | Founder: say yes to v08, or name a mark. Also: today's money for the retirement figures and tax on taxable withdrawals (recommended); whether dark/light bars replace the Plan tab's quiet labels. Claude: once approved, record v08 as the current Net worth design, archive v06, then build marks 1–4 and
Net worth | WAITING ON YOU | The retirement sentence (Net worth, Plan, Home) prints future dollars without saying so, and the odds calculation charges no tax on withdrawals from taxable accounts — found checking the founder's question on v07 ($4.1M at 65 is about $2.0M in today's money) | Founder: say whether to show today's money and to tax taxable withdrawals (recommended). Claude: then write both as findings on the master rows (MK-XS-M-002 and the pot/leftover figures) before any code.
Net worth | TO DO | Net worth with no accounts yet but past the first day (the Q48 frame) still repeats 'Add your accounts ›' under each empty group — the same duplication the founder removed from the first day | Claude: draw it in the Net worth series (v09) for approval before building.
Performance | WAITING ON YOU | Commit — the branch was 278 files behind on 2026-09-14; committed since: 983805a (catch-up), f0e1d6d (Net worth v08), c4f2679 (the Since crash), 727e22a (Performance v14). Nothing is pushed — the branch taxonomy-v1.0.7 is local only. | Founder: say when to PUSH. (Note 2026-09-26: the Xcode licence has not been accepted on this Mac, so the normal git refuses to run — "sudo xcodebuild -license accept" once, then git works everywhere again.)
Performance | WAITING ON YOU | One door, one term: the three ways to add an account read 'Link it (read-only)', 'Add by hand' and 'Import from a file' on every screen, under the heading 'How do you want to add an account?' — Home, Sharpen your plan, the Plan tab, Net worth (first day and the add sheet), the Connect an account screen and Performance | Founder: approve the mock MoneyKeel/documents/home-screen/moneykeel_pres_mock_ways-to-add-an-account_v10.html (every affected screen, before and after). Claude: then build all of it the same day, with the tests and the canon row
Performance | WAITING ON YOU | Nothing recorded which design each screen was built from. The Build 53 Net worth and Performance finals (networth-FINAL.html, performance-FINAL.html, the two Net worth PDFs, Net worth screens 01 to 11) were filed under networth-and-performance/archive/ on 2026-09-01, which marks them replaced. They were not replaced. Six hours of mocks then started from the wrong files. CORRECTION 2026-09-14: Buil | Claude: done 2026-09-14 — Build 53 files matched by exact content and recorded in MoneyKeel/documents/standards/moneykeel_pres_spec_design-each-screen-was-built-from_v01.md. Founder: (1) confirm Net worth = v5 + square corners; (2) say whether to draw Net worth v6 from the Build 53 code (v5 with squ
Performance | TO DO | App-wide · selector corner radius is inconsistent — 23 places use the semicircle (Radii.pill) and 157 use the 12-point corner (Radii.md); the Performance window chips were semicircles. Founder, 2026-09-25: “make the buttons same as all radio buttons across all screens — rounded corners not semicircle ends.” | Performance chips are fixed in mock v11 (mark 10). Sweep the other semicircle selectors and bring them to 12 points, screen by screen, each with its own mock.
Cash flow | TO DO | Second verification — 14 rulings coded but without a named test: G14, G16, G18, G19, G20, G23, G25, G26, G27, G29, G33, G35, C2, C4 (plus Q07, A15 and the cash-flow worked example on the rulings tab) | Claude: write the test that fails on the old code for each, then move the row to TESTED
Cash flow | WAITING ON YOU | Master questions Q34–Q45 and Q50 (your cash-flow example arithmetic) — open | Founder: answer in the master (column "YOUR ANSWER — use the same number"); the REVIEW column filters every coloured cell: 42 questions, 10 input lists, 25 answers to read
Cash flow | WAITING ON YOU | Five approved mocks still carry words the canon retired (cash-flow this-month v06 and money-four-tabs v01: "spending"; filing-status v02: "partner", "told us"; look-ahead v03: "/mo"; empty-state-pattern v01: "spending"). The app copy is on the canon; these mocks are not. | Founder: say whether each gets a new version on the canon (old archived) now, or at its next change; then Claude: re-version the ones you name
Cash flow | WAITING ON YOU | Stand-in ages when the birth year is missing: the Retirement cockpit and Insights assume 45, the cash-flow model and the draw steer assume 68, the onboarding helper 35 (or 65 for the retirement age). Your rule R2 says an unknown input gives no number and a reason. | Founder: say what those screens show when the birth year is missing (ask for it in place? show the door?); then Claude: mock first, then code
Cash flow | WAITING ON YOU | Two word collisions found building v08: Cash flow's 'Add by hand' adds an EXPENSE (the same words as the account door), and Settings still says 'Disconnect' beside 'Linked accounts' | Founder: say whether Cash flow's door should read differently (for example 'Add an expense by hand') and whether Disconnect becomes 'Unlink'.
Cash flow | TO DO | Q-PL-2 — ‘What will my retirement paycheck be’ behind its own door: 10 figures, 88 functions, spilling onto Plan, Cash flow, Monthly income and Retirement. The Plan tab prints its paycheck, so this door and MK-PL-O-001 both stand between the approved design and a built Plan tab. | After the pilot. Step 1 is the founder’s row; the identifier is named there.
Plan | WAITING ON YOU | Four questions from the cluster work: #3 "spending" in prose (173 places), #11 the "Close position" button, #13 "plan for the lump sum" (my answer is on the row), #14 "/qtr", "/wk" labels | Founder: answer in column "YOUR ANSWER"; then Claude: code + test
Plan | WAITING ON YOU | Empty state, the last 8 of 58 rows (4 more do not apply — the holding page): Account detail (the classes and income inside one account — MK-NW-M-019/020/021); a past month that predates tracking (MK-CF-M-004); a goal row (MK-CF-M-021, appears only when committed); the Roth "Extra tax" row (MK-PL-M-023, "—" until a plan is adopted); Job safety asks in place (MK-MN-M-021). And one question: Debts ca | Claude: build the Account-detail rows; Founder: say whether the three rows that show a dash or vanish should show $0 with the line instead, and whether to add an "I have no debts" answer (a new input)
Plan | TO DO | One-door architecture — will it last, MK-PL-O-001 thePlan: the row, then the door beside the old code, then 16 callers moved one at a time against the photograph, then the old doors closed | Claude: after the pilot proves the pattern; each caller moved with the suite green and the photograph byte-identical
Plan | WAITING ON YOU | Orchestrator plan · phase 1d — Conflicts: every grouping conflict one row by identifier with a recommendation (two totals for one concept; a function under two questions; two functions for one concept; a figure the screen computes) | Claude: done 2026-09-13 — tab Conflicts, 30 rows each with a recommendation; Founder: answer each row
Plan | WAITING ON YOU | Orchestrator plan · phase 1 gate — approve the Map, answer Conflicts, name the pilot question (proposed: Social Security timing) | Founder: on the Map mark YES per row or say what moves; on Conflicts answer each row; on Census confirm the proposed rows; name the pilot
Plan | TO DO | Orchestrator plan · phase 2 — the loop guards: one producer per figure row; the forward hop read from screen imports; the reverse hop generated from the rows; the trace test | Claude: after the phase-1 gate; four guards in build-all.sh
Plan | TO DO | Orchestrator plan · phase 3 — the pilot question through the six steps (row → photograph → door → callers moved one at a time → old doors closed → reconcile) | Claude; Founder: verdict on the pilot's row before it is built
Plan | TO DO | Orchestrator plan · phase 4 — will my money last: MK-PL-O-001 thePlan; the 16 files move behind the door | Claude; Founder: verdict on its row
Plan | TO DO | Orchestrator plan · phase 5 — every remaining Map row by blast radius, one question at a time, same gate each | Claude; Founder: verdict per row
Plan | TO DO | Orchestrator plan · phase 6 — the walls: every ratchet at zero and turned into a wall; Calculation Module code/engines/ emptied and removed; the trace test over all figure rows | Claude; Founder: VERIFIED marks
Plan | WAITING ON YOU | Orchestrator plan — proposed rule 11: a door DECLARES each figure by identifier beside the code that computes it, the screen prints only by identifier, and the builder generates the master's figure rows from those declarations (deleting the ~140 hand-typed lines that are the origin of every mismatch) | Founder: rule on it before the pilot is built — it changes what a door is. As specified today the door hands out property names, not identifiers, and the row is still typed by hand, so two records must be kept in agreement and they drift
Plan | WAITING ON YOU | Q-CF-2 'how much have I spent this month, against the plan, and what is left' — eight figures DRAFTED on MK-CF-O-003 thisMonth: expected inflow, planned outflow, planned surplus, each planned line, inflow so far, outflow so far, surplus so far, each received line (MK-CF-M-047…054) | Founder: read the eight rows on the master's cashflow tab (Row status says DRAFT) and say yes, or say what changes. Claude: the moment you do, the Cash flow screen, the month detail screen and Home's cell move behind the door and stop working figures out themselves
Plan | WAITING ON YOU | One door, one term: the three ways to add an account read 'Link it (read-only)', 'Add by hand' and 'Import from a file' on every screen, under the heading 'How do you want to add an account?' — Home, Sharpen your plan, the Plan tab, Net worth (first day and the add sheet), the Connect an account screen and Performance | Founder: approve the mock MoneyKeel/documents/home-screen/moneykeel_pres_mock_ways-to-add-an-account_v10.html (every affected screen, before and after). Claude: then build all of it the same day, with the tests and the canon row
Plan | WAITING ON YOU | MoneyKeel at the top of every screen — today only the five tab screens show it; every pushed screen (Import from File, Add by hand, Link an account, Sharpen your plan and the rest) has a native bar or none | Claude: draw it on every pushed screen in mock v10 (‹ Back in place of Menu); Founder: approve before it is built
Plan | WAITING ON YOU | The Plan tab does not match the Plan design you approved (Claude Design Plan v4, brief v3-2026-08-14, built for Build 53). Built from it: the two dials, the typed target, Retire / Goals / Prepare, 'Can I spend more?' in plain English, the Social Security row. NOT built: 'Your plan at a glance' — seven equal question rows, collapsed, dials staying small while it is open. Today's app still shows the | Founder: say whether to (a) run a full mock-match audit of the Plan tab against the v4 design, then mock the tab as approved with today's rulings, then build — or say otherwise. Claude: mock v10 sections 4 and 5 were drawn from today's code, so they show the rejected layout; they are not to be appro
Plan | WAITING ON YOU | The retirement sentence (Net worth, Plan, Home) prints future dollars without saying so, and the odds calculation charges no tax on withdrawals from taxable accounts — found checking the founder's question on v07 ($4.1M at 65 is about $2.0M in today's money) | Founder: say whether to show today's money and to tax taxable withdrawals (recommended). Claude: then write both as findings on the master rows (MK-XS-M-002 and the pot/leftover figures) before any code.
Plan | WAITING ON YOU | With the odds exact, the Retirement cockpit disagrees with Home and the Plan tab for the same household: the working household reads 13.3% in the cockpit and 13.9% on Home and Plan; the retired household reads 87.8 out of 100 in the cockpit and 93.2% on Home and Plan (it was 90 against 95 before, so that one was already visible). Rounding to 5 hid the first. | Claude: find which input the cockpit builds differently from willItLastInputs, and fix it in the Plan step, with a screens-agree check covering the cockpit. Founder: nothing, unless you want it before Plan.
Plan | WAITING ON YOU | Exact odds moved the amounts found by holding 80%: June's draw $4,155 → $4,140 a month (paycheck $8,155 → $8,140), a retiree's surplus $4,025 → $4,010, a future paycheck $2,460 → $2,455; Ray's claim at 70 now reads 79.5% (under 80%). The Plan brief carries a dated erratum. | Founder: read, no action — these follow from your ruling. Claude: re-run every Plan brief figure at 1,000 futures in the Plan step.
Plan | WAITING ON YOU | Plan — the approved design filed into the MoneyKeel structure and made standalone (founder, 2026-09-26: “move it to moneykeel structure. I do not want to work on anything which is not is new file structure, and meets new standards.”) | Founder: read MoneyKeel/documents/plan/moneykeel_pres_mock_plan_v05.html and answer the eight questions marked in it (Q1 extra-saving row, Q2 save-as-you-type, Q3 cap or overfill, Q4 where the suggested target sits, Q5 the mortgage odds placeholder, Q6 today’s money + tax on the retirement sentence,
Plan | TO DO | Plan v06 — the five blockers fixed and every figure re-run at 1,000 futures: the below-yield mortgage frame ($6,304 → $5,814; $40,217 → $31,873), the spend-more bucket that says 9 in 10 where $2,500 is really 81%, the mortgage caption stated as fact, the 10.5-point chip, and amber meaning two things on day one | Blocked on the founder’s answers to Q1–Q8 in moneykeel_pres_mock_plan_v05.html. Then Claude draws v06 for approval. No code.
Plan | WAITING ON YOU | Q-PL-3 — ‘When should I claim Social Security’ as the PILOT door: 4 figures, 3 functions, one screen (/ss-timing). The smallest thing on the Map that proves the six steps end to end, and its answer is a decision row inside the Plan design. | Founder: name it as the pilot at the phase 1 gate (the spec already proposes it). Then step 1 is his row — what it answers, the formula in plain English, inputs, decisions, identifier, the exact figures — before any code.
Plan | TO DO | Q-PL-2 — ‘What will my retirement paycheck be’ behind its own door: 10 figures, 88 functions, spilling onto Plan, Cash flow, Monthly income and Retirement. The Plan tab prints its paycheck, so this door and MK-PL-O-001 both stand between the approved design and a built Plan tab. | After the pilot. Step 1 is the founder’s row; the identifier is named there.
Plan | WAITING ON YOU | SEQUENCING DECISION — is the Plan tab’s CODE built against its doors (MK-PL-O-001 thePlan for Q-PL-1, and the Q-PL-2 door) or in front of them? Built in front, the screen is built twice and can still disagree with Home about the same household — which is what it does today (13.3 vs 13.9; 87.8 vs 93.2). | Founder: say which. Claude’s recommendation 2026-09-26: finish the Plan DESIGN now (no code), then the pilot, then Q-PL-1 and Q-PL-2 behind their doors, then build the Plan tab once against them.