## Open gaps vs mock
# | Found by | Screen | Gap | Class of defect | Status | Verified against the CODE (2026-08-11)
1 | Founder | NW main | E*TRADE CD still shows under Cash | DATA REALITY — the cash-only rule was applied to NEW data only; existing/synced accounts were never re-classified | CLOSED | CLOSED — a one-time re-classification runs over ALREADY-STORED accounts (store.runReclassifyOnce, called from Home on mount; reclassifyAccounts + RECLASSIFY_VERSION, idempotent). Test: 'a stored CD leaves Cash for Bonds'. A connected account that sends no holdings also keeps its own class now (fixed 2026-08-10), which was the same defect one layer down.
2 | Founder | NW main | VMFXX (money-market fund) still under Cash | same class as #1 — needs a one-time migration over existing accounts | CLOSED | CLOSED — same migration; test: 'VMFXX leaves Cash for Stocks'. Positions INSIDE an account are re-classified too, not just the account row.
3 | Founder | NW main | Inside the Cash group there is a SECOND "Cash" sub-heading with the items under it | NESTING — group bar and class sub-band duplicate each other | CLOSED | CLOSED — a lone class matching its group renders its accounts directly (no repeated heading). Test: 'nesting: no class header repeats its own group name' asserts zero bare 'Cash' headers.
4 | Founder | NW main | Group totals sit slightly LEFT of the row numbers | ALIGNMENT — band value inset differs from row value inset | CLOSED | CLOSED — fixed structurally, not nudged: the whole own/owe list became one flat table where EVERY row (bands included) reserves the same 16pt arrow column. Test measures the rendered right inset of a section total, a group total, a class total and an account amount and asserts they agree.
5 | Founder | NW main | "By category / By institution" pills sit BELOW What you owe; the mock puts them above the lists | ORDER | CLOSED | CLOSED — pills render above the lists. Test: 'order: the grouping pills render BEFORE the WHAT YOU OWN band'.
6 | Claude | NW main | Hero band reads "YOUR NET WORTH"; mock reads "YOUR NET WORTH · AUG 4, 2026 info-dot" | TEXT DIFF | CLOSED | CLOSED — the band reads 'YOUR NET WORTH · AUG 11, 2026' (today's date restored at the founder's ask 2026-08-11). Test asserts the dated title AND that today appears exactly once on the screen.
7 | Claude | NW main | Retirement card still uses the OLD "path ahead ... by 92" wording, unbanded; mock has the banded card with the approved sentence | TEXT DIFF + approved-words decision not applied here | CLOSED | CLOSED — the card speaks the Plan hub's own sentence via onCourseSentence + lensChanceWord, with its info dot. Test: the retirement-card block in NetWorthScreen.test.
8 | Claude | NW main | Under the change: code shows "as of Aug 10"; mock shows "since Aug 3, 2026" | TEXT DIFF — different meaning | CLOSED | CLOSED — the line reads 'since Aug 3, 2026' (the true measured-from day, with the year), and the title's date is a separate fact (as-of today). Test: 'hero: today stamps the title, the since line carries the measured-from day'.
9 | Claude | NW main | Emergency cushion card differs between the with-data screen and the mock | TEXT/STRUCTURE | CLOSED | CLOSED — one cushion card in both states: 2.0 months + Tight ⚠ + the math line, and a progress bar (founder Q6). It also divides by the SAME cash the CASH group shows, which it did not before (it read $8,000 against a group of $8,838).

## Method that must be used
1. Extract every visible string from the approved mock, in order — that list is the spec.
2. Render the screen with real-shaped data; dump every visible string, in order.
3. Diff the two lists. Every different/missing/extra line is a defect. Report N of N identical.
4. Check order, nesting, alignment, data reality (rule changes must re-classify EXISTING accounts).
5. State what was NOT verified — appearance is never proven by these tests.