## Brief & objective
Section | Content
Objective | MoneyKeel on a big screen — the chief-of-staff desk your 55-70 audience actually plans at. Same engines, same numbers, same honesty rules; laid out FOR a monitor: side-by-side panels, real tables, print/export. Desktop is where this audience does serious money work.
What we already have | The entire money brain is portable TODAY: all ~6,000 lines of engines (retirement odds, debt, the 12-month grid, paycheck, net worth) have zero phone dependencies — verified line by line. Firebase (login, sync, households) is already the web version. The store carries over. Roughly 95% of the business logic and ~65% of all code reuses mechanically.
What the June docs got right | The finwise-desktop drafts (June 17, never approved): share the brain / rebuild the face; same Firebase backend, desktop is just another signed-in device; Simple-vs-Advisor toggle (still in the app today). These carry forward.
What must be rewritten | Everything product-side predates the FCC pivot: they say Finwise not MoneyKeel, target "everyone 15-100", draw a 9-module Facebook-style feed and a turtle mascot. Phase 0 rewrites the design doc against the approved FCC 55-70 set — with your approval gate before any code.
The three honest hard parts | (1) LAYOUT: the phone screens have no wide-screen story — on a monitor everything stretches edge-to-edge; the real work is designing the 5 tabs for width (mock-first, your gates). (2) A popup-dialog shim used on 104 spots must be replaced for browsers (mechanical, one day). (3) SECURITY: on a plain web build the phone's keychain encryption and Face-ID lock silently turn off — the installable-app shell restores both; this decides web-vs-installable more than looks do.

## Decisions for you
# | Decision | My recommendation | ✅ Approve? | 💬 Comments
1 | Who is it for first? | Beta users + you — same 55-70 audience, ships alongside the phone beta. (Alternatives: just-you cockpit; or public-launch quality from day one.)
2 | Browser app or installable download? | Web first (moneykeel login in any browser — zero install, works on Mac/Windows/iPad), then wrap the SAME code as an installable Mac/Windows app for the keychain security + a real product feel. The wrap is Phase 4, not a rewrite.
3 | Scope of the first version? | Big-screen redesign of the 5 tabs — not a stretched phone port. Home + Plan side-by-side is the money shot: the verdict, the next decision, and the sandbox on ONE screen. Mock-first, every screen, your verdicts.
4 | Process? | Same gates that rebuilt trust: Phase-0 design doc → your approval → hi-fi mocks per screen → build → your walk rounds. No screen builds unapproved.

## Phases & timeline
Phase | What ships | My build time | Calendar (with your review gates)
0 — Design docs v2 | Desktop design + tech-arch rewritten against the approved FCC set (brand, 55-70 lenses, 5-surface navigation as a left sidebar, security model). Your approval gates the rest. | 1–2 days | Week 1
1 — It boots in a browser | Web build turned on; the popup shim; font + storage + crash-reporting swaps; sign-in, sync, and every engine running; phone-column layout as scaffolding (not shown to users). | 2–3 days | Week 1–2
2 — The desktop shell | Left sidebar from the same one nav map the phone uses; width system; mouse hover states app-wide; keyboard basics (Esc closes sheets, Enter saves). | 3–4 days | Week 2
3 — The 5 surfaces, designed for width | Mock-first: Home (glance + what-needs-you side by side) · Plan (verdict + decisions + sandbox on one screen) · Net worth (real table) · Invest (table + holding detail two-pane) · Cash flow (grid + calendar side by side). Built to your approved pictures with the same pinned-test discipline. | ~2 weeks | Weeks 3–5 (pace set by your mock verdicts)
4 — Installable + security | Mac/Windows wrapper around the same code: OS-keychain encryption restored, app lock, native notifications, signed installers. TestFlight-equivalent distribution for beta. | ~1 week | Week 5–6
5 — Your walk rounds | Same as phone builds: walk workbook, findings fixed same-hour where possible, repeat until you say ship. | 2–3 days per round | Week 6+
TOTALS | Fast path (browser port, just you, no redesign): ~1 week to usable. RECOMMENDED path (web app, 5 surfaces redesigned, gated): my build time ~3 weeks; calendar ~5–6 weeks end to end. Installable app adds ~1 week on top. | — | —

## Reuse & risks
Item | Detail
Reuse, by layer | Engines ~100% · services ~85% (file-reading, notifications, receipt-scan get web branches) · store ~95% · components ~70% · screens: logic carries, layout redesigned. Receipt photo-scan stays phone-only (its cloud-vision path can come to desktop later as drag-a-PDF).
Risk 1 — layout | No responsive machinery exists (verified: zero window-size reads, 124 fixed pixel widths). Priced into Phase 3 as real design work, not a port.
Risk 2 — security | Plain web = encryption key falls back to browser storage + no app lock. Mitigation: Phase 4 shell restores the OS keychain; until then beta desktop carries a plain-words note. Your call if that note is acceptable for beta.
Risk 3 — connect flow | The broker-connect handoff (portal → back to app) is the hardest single flow on desktop; also frozen anyway pending your Plaid/SnapTrade/Teller decision. Phase 1 ships manual + import first; connect lands with the provider decision.
Not duplicated | One design system (the same theme tokens), one nav map, one store, one engine set — the desktop consumes them; nothing forks. Phone pins keep protecting the shared brain.