## Build 41 walk
MoneyKeel Build #41 · v1.1.0 — the FCC redesign device walk (2026-07-14)
Yellow columns are yours. Walk in order; step 0 matters most (the upgrade over your existing install). Anything odd → a comment here is enough, I will ledger it.
# | Step (what to do) | What you should see | Pass / Fail | 💬 Your comments
0 | Update MoneyKeel in TestFlight over your existing install and open it | Your data survives the upgrade; the app opens as MoneyKeel — no reset, no blank screens
1 | Look at the bottom bar | FIVE tabs: Home · Net worth · Invest · Cash flow · Plan
2 | Look at Home | YOUR INVESTMENTS hero + one net-worth line + What needs you (top 3) + the Will-my-money-last strip
3 | Cross-check the hero | Home's investments number equals the Invest tab's header number to the dollar
4 | Tap the eye (top bar), look at every tab, tap it back | Every dollar everywhere becomes •••• ; percentages and the odds stay readable
5 | Tap + Expense (bottom-right on Home) and log a real coffee | Amount → category → Save. Two taps, no chooser menu. It appears in Cash flow
6 | Cash flow tab | This month in / out / Planned surplus + twelve DATED month bars + the future-paycheck PROJECTION card (working view)
7 | Tap any month bar | That month's page: money in with real dates, big bills, regular bills — the rows visibly add up to the number
8 | Plan tab → tap the big will-it-last number | What drives this: every input listed with its value AND its source (you set it / estimated from your data), each tappable
9 | Plan → Claim Social Security → type 2600 | The 62 / 67 / 70 table in your dollars ($1,820 / $2,600 / $3,224) + the effect on your odds
10 | Tap "Use claim at 67 as my plan" | The sheet shows exactly what changes (old → new) BEFORE anything changes; after adopting, the hub shows 'Back to previous plan'
11 | Use "Back to previous plan" | Everything switches back exactly — Home, Plan and Cash flow all agree again
12 | Plan → Afford it all? → toggle a goal on | 'Covered, $X/mo to spare' or 'Short $X/mo' + what it does to retirement (before → after) + trim hints
13 | Net worth → tap any account | Its own page: source chip, freshness, activity history; cash accounts get Deposit / Withdraw / Transfer
14 | On a checking account, record a $1 transfer to savings | A preview shows both sides before saving; both balances move; the activity list shows it
15 | If you track a bond, open it | Bond facts + 'If interest rates move — Estimate, not a prediction' with the honest range
16 | Invest tab → Look back | Real past prices: what the money became where it sat vs moved, and the plain difference — “not a prediction”
17 | Invest tab → What if I add more? | The +$100/mo dial moves the projected nest egg and the odds, before → after
18 | Settings → Your setup → 'Retired, or nearly' | The tab ORDER changes (Cash flow moves next to Home); Home leads with SAFE TO SPEND — with the Social Security + pension + safe-draw breakdown
19 | On the retired Home, tap the (i) next to Safe draw | The plain answer to 'says who?' — the largest steady draw that keeps your odds at Likely
20 | Switch Your setup back to 'Still working' | Everything returns exactly as before
21 | General feel | Nothing red or alarming anywhere; every projection says “estimate”; nothing feels slow (especially Home)