## Launch Checklist
Launch Checklist
Everything left to ship v1, by phase. 'Type' = Blocker (can't ship without) / Recommended / Optional. Owner: You = account/legal/manual · Claude = in-repo. Statuses reconciled against code/records on 2026-06-26 (a few launch-checklist.md rows were stale — e.g. Firestore rules ARE deployed). Fill the yellow 'Your rank' + 'Decision' columns to set the order we work them. Rows marked 'VERIFY' are doc/memory-derived — confirm in code before relying.
ID | Phase | Item | Owner | Type | Status (2026-06-26) | Your rank | Decision | Notes / next step
L-1 | 1.1 | Swap market data to a LICENSED vendor (Tiingo / EODHD / AlphaVantage / TwelveData) — replace the unlicensed Yahoo endpoint | You→Claude | Blocker | OPEN — the long pole |  |  | You pick a vendor + API key (~$10–50/mo EOD); then a ~1-file PriceProvider swap in marketData.ts. Legal blocker.
L-2 | 1.2 | Deploy Firestore security rules | You | Blocker | DONE 2026-06-17 (checklist doc is STALE) |  |  | Deployed to finwise-app-jj with the privilege-escalation fix + emulator tests. Verify active in console.
L-3 | 1.3 | Cut production build #35 + verify OCR + keychain on a real device | You (EAS) | Blocker | BLOCKED on EAS free quota (~Jul 1); code READY |  |  | 739 tests green, tsc clean, T22 loop fix in. Push-button once quota resets. eas build --local fails (macOS-26 keychain).
L-4 | 2 | App Store screenshots — 6.9in iPhone, on a REAL device (ML Kit blocks the Simulator) | You | Blocker | OPEN (needs a device build) |  |  | 8 frames + captions + per-persona setup spec'd in finwise-appstore-listing.md.
L-5 | 2 | Description / keywords / subtitle / promo text | You | Blocker | DRAFTED — needs entry |  |  | Copy ready in finwise-appstore-listing.md; paste into App Store Connect.
L-6 | 2 | Category (Finance) + Age rating (4+) | You | Blocker | OPEN (trivial) |  |  | Questionnaires in ASC.
L-7 | 2 | Privacy Policy URL + Support URL | You | Blocker | PARTIAL — privacy hosted, needs RE-host of updated copy (see L-11); Support URL TBD |  |  | finwise-legal is live; B-L1 changed the privacy copy so it must be re-hosted.
L-8 | 2.5 | App Privacy 'nutrition label' must MATCH the privacy manifest | You | Blocker | OPEN |  |  | Declare Email, Name, Financial Info, Crash/Diagnostics — all 'app functionality', none 'tracking'. Apple cross-checks.
L-9 | 2.5 | Reviewer demo login (real account + sample data) in the submission notes | You | Blocker | OPEN |  |  | Without it the reviewer can't pass the login screen → auto-reject.
L-10 | 2.5 | Test Delete-account end-to-end on a PRODUCTION build | You | Blocker | OPEN (needs build #35) |  |  | Guideline 5.1.1(v). Confirm it wipes cloud data + auth.
L-11 | 2.6 | B-L1 — Re-host the updated privacy/index.html (AI/privacy claim reconciled in code) | You | Blocker | Code DONE (945f929); RE-HOST pending |  |  | On-device-only tips + ML-Kit OCR; no financial data/receipts leave the device. Live URL must serve the new copy.
L-12 | 2.6 | B-L2 — Verify a Sentry event lands on the next production build | You | Blocker | WIRED (2026-06-23); VERIFY on build |  |  | SDK + DSN + plugin + source-maps all set. Fire the Settings test event and confirm it lands.
L-13 | 2.6 | B-L3 — Disclaimer on every projection / 'on-track' verdict | Claude | Important | DONE (bb68bad) |  |  | Shared <Disclaimer/> on all judgment screens; coverage guard test.
L-14 | 2.6 | B-L4 — Graceful network degradation | Claude | Important | DONE (verified, no code change) |  |  | allSettled + cache fallback; proven by marketData/economicData/store_prices offline tests.
L-15 | 2.6 | A-1 — One income base (take-home) drives every %-of-income spending category | Claude | Accuracy P0 | LIKELY DONE on taxonomy-v1.0.7 — VERIFY |  |  | take_home_agreement.test + number_agreement.test pass. Confirm the % path specifically.
L-16 | 2.6 | A-2 — Cross-screen money-agreement matrix + tests | Claude | Accuracy P0 | DONE — agreement matrix shipped 2026-06-25 |  |  | number_agreement.test.ts green. A wrong number = lost trust (L-7).
L-17 | 2.6 | Verify the bug ledger has no open user-facing money error | Claude | Important | Ongoing — ledger shows 0 open |  |  | Re-confirm before each submit.
L-18 | 2.6 | Run the Maestro flows on a real device (auth-signup, smoke, b21-add-sheet, nw-donut, cashflow) | You | Important | OPEN (needs build) |  |  | Selectors have never executed on-device (ML Kit blocks the simulator).
L-19 | 2.6 | Prep the App Review note (educational planning tool; no money movement / linking / securities advice) | You | Important | DRAFT exists (finwise-app-review-notes.md) |  |  | De-risks the fintech-licensing guideline.
L-20 | 2.6 | Decide: scope the launch US-only | You | Positioning | DECISION — likely already (USD-only, picker removed) |  |  | Confirm; don't market global. GLBA/state-privacy posture assumes US.
L-21 | 2.6 | Decide: track onboarding completion as the #1 launch metric | You | Positioning | DECISION |  |  | Needs basic analytics (see Parked P-73).
L-22 | 4 | Clean onboarding per persona (student / variable-income / professional / retiree) — numbers reconcile | You | Blocker | OPEN (needs build #35) |  |  | Use finwise-user-guide.md as the script.
L-23 | 4 | Confirm prices load from the LICENSED provider (not Yahoo) | You | Blocker | Depends on L-1
L-24 | 4 | Sign up → log out → recover account → log back in | You | Blocker | OPEN
L-25 | 4 | Physical-device test (gestures, keyboard, safe-area, large text) | You | Recommended | OPEN (needs build)
L-26 | 4 | eas submit --platform ios --profile production → TestFlight → submit for review | You | Blocker | Final step |  |  | eas submit is separate from the build quota.

## Parked - Backlog
Parked - Backlog
Every consciously-deferred item, deduplicated across all docs (features, roadmap, qa-plan, ui-compliance, scorecard, microservices, onboarding-matrix, rename-candidates). Status: Open / Partial / Done-verify (doc says open but code/memory says shipped — verify & drop) / Decision. Fill the yellow 'Your rank' + 'Decision' (do-now / next / later / drop) columns. Source = which doc(s) it came from.
ID | Category | Item | Status | Source doc(s) | Your rank | Decision | Why parked / notes
P-1 | Data/Integrations | Plaid / bank & brokerage linking (account aggregation) | Open | features, roadmap, scorecard, microservices |  |  | Auto-pull balances/transactions behind an aggregator interface. XL effort, server-side (Cloud Functions). Biggest stickiness/friction lever.
P-2 | Data/Integrations | Auto-derive dividends from ticker (Yahoo yield/events) | Open | features |  |  | Auto-populate dividends instead of manual entry.
P-3 | Data/Integrations | Ticker autocomplete + price-cache TTL | Open | features |  |  | Perf v2 polish; attribution/allocation/trend already shipped.
P-4 | Data/Integrations | Receipt OCR native rebuild (activate ML Kit) + tune parsing | Open | features, roadmap |  |  | npx expo run:ios native rebuild, then test a real scan. Launch-adjacent — folds into build #35.
P-5 | Data/Integrations | CSV import validation (format / length / dup / row-cap) | Open | qa-plan (QA-T2-009) |  |  | Import has no malformed-row rejection / bounds today. P1.
P-6 | Insights/AI | History-driven insight engine + notifications (richer than today's 9 rules) | Partial | roadmap 1.5, scorecard |  |  | 9-rule ranked engine shipped; the snapshot-history version ('gas +15%, stocks -12%') powering nudges is parked.
P-7 | Insights/AI | AI 'show your work' — consistent tappable explainer everywhere | Open | ui-compliance (G-27) |  |  | Explainability strong inline but not a uniform affordance. P2.
P-8 | Insights/AI | Planning copilot — LLM Q&A over your data ('can I afford a $600k house?') | Open | roadmap Ph4 |  |  | Differentiation.
P-9 | Insights/AI | Life-event scenarios (home, child, job change, sabbatical) side-by-side | Open | roadmap Ph4
P-10 | Retirement/Modeling | Drawdown / decumulation 'will it last?' view for retirees — deeper surfaces | Partial | features, roadmap, microservices |  |  | Accumulation done; a drawdown view shipped for the 50yo review; deeper retiree framing open.
P-11 | Retirement/Modeling | Tax-aware drawdown (withdrawal order, cap-gains harvesting, Roth conversions, healthcare/LTC) | Open | features, roadmap, microservices |  |  | RMDs/order partly shown as transparency; deeper tax-awareness parked (sensitive engine).
P-12 | Retirement/Modeling | Salary-growth assumption (contributions rise with raises) | Open | features, roadmap, microservices
P-13 | Retirement/Modeling | Filing status (married/HoH) + multi-country tax & account-type 'packs' | Open | roadmap, scorecard |  |  | Single-filer US-2026 only today. TaxPack / AccountTypePack abstraction (UK/CA/AU/IN). Tied to global expansion.
P-14 | Retirement/Modeling | Couples / household + shared goals (joint + individual views) | Open | roadmap Ph2.5 |  |  | Partner invite partial. Distinct from the encryption key-sharing item (P-21).
P-15 | Retirement/Modeling | 529 college planning | Open | features |  |  | Life-stage gap.
P-16 | Retirement/Modeling | Life / long-term-care insurance planning | Open | features |  |  | Life-stage gap.
P-17 | Retirement/Modeling | Estate / legacy planning (beneficiaries, estate docs) | Open | features, onboarding-matrix |  |  | Legacy/beneficiary fields deferred from onboarding S7.
P-18 | Retirement/Modeling | Unemployed / transition mode (runway, COBRA, survival budget) | Open | roadmap Ph2.3 |  |  | Overlaps the runway insight (P-34).
P-19 | Retirement/Modeling | Gig / partially-employed mode (variable-income smoothing, 1099 tax set-aside) | Open | roadmap Ph2.4 |  |  | Pay-yourself-a-salary, irregular cadences, tax reserve.
P-20 | Onboarding | 'Sharpen your plan' progressive surface for deferred onboarding fields | Partial | onboarding-matrix, features |  |  | Checklist version shipped; the progressive 'add more to sharpen' surface (retirement COL, travel/medical budget, allocation, employer match, beneficiaries, risk tolerance, per-goal priority…) is spec'd separately.
P-21 | Security/Privacy | Household/partner sharing under zero-knowledge encryption (key-wrapping via invite code) | Open | features |  |  | Two passwords can't share one key today; fails safe (no crash).
P-22 | Security/Privacy | Multi-factor authentication (MFA) | Open | features, qa-plan |  |  | App-lock + inactivity timeout already shipped; MFA is the remaining auth-hardening item.
P-23 | Security/Privacy | Dependency vuln scan (npm audit + Snyk in CI) — triage ~58 advisories | Open | features, qa-plan (T2-005/003) |  |  | Mostly build-time tooling. Add npm audit --audit-level=high + gitleaks to CI.
P-24 | Security/Privacy | SAST / static analysis (SonarQube / Semgrep) in CI | Open | qa-plan (T2-006) |  |  | P1.
P-25 | Security/Privacy | Mobile binary scan (MobSF on the EAS build) | Open | qa-plan (T2-007) |  |  | Insecure-storage/transport scan. P1.
P-26 | Security/Privacy | Transport security hardening (HTTPS-only, cert/timeout handling) | Open | qa-plan (T2-010) |  |  | Enforce HTTPS on Yahoo/BLS/Treasury fetches. P1.
P-27 | Security/Privacy | Slide-to-confirm / biometric on the heaviest actions (per-action) | Open | ui-compliance (G-15) |  |  | App-lock biometric shipped; per-action confirm is the gap. P1.
P-28 | A11y | Screen-reader labels (VoiceOver/TalkBack) on the remaining ~26 screens | Open | features, qa-plan, ui-compliance (G-13) |  |  | Started on shared controls. Single biggest a11y gap. P0.
P-29 | A11y | 44x44 touch targets (grow elements, not just hitSlop) | Open | qa-plan, ui-compliance (G-14) |  |  | Many targets sub-44 via hitSlop. P0.
P-30 | A11y | Dark + high-contrast themes (token swap) | Open | features, qa-plan, ui-compliance (G-21) |  |  | Light-only today. P2.
P-31 | A11y | WCAG AA contrast audit (text + data viz) | Open | qa-plan, ui-compliance (G-32) |  |  | Not formally audited. P1/P2.
P-32 | A11y | Reduce-motion-aware micro-interactions | Open | ui-compliance (G-23) |  |  | P3.
P-33 | UI/UX | Privacy-blur / hide-balances toggle | Done-verify | features, qa-plan, ui-compliance (G-16) |  |  | features.md says a 'hide-balances mask-ALL' shipped in build #34 — VERIFY in code; likely closable.
P-34 | UI/UX | Runway / emergency-fund insight ('cash covers N months') | Open | features, roadmap |  |  | Needs a liquid-cash balance. Overlaps unemployed mode (P-18).
P-35 | UI/UX | Net-worth-over-time card on Home (trend from snapshots) | Open | features |  |  | 'Net worth up $40k over 6 months.'
P-36 | UI/UX | Header + bottom tab-bar redesign | Partial | features |  |  | Greeting/streak/avatar header + nav still older styling.
P-37 | UI/UX | Legacy detail-screen redesigns behind nav (Budget/Transactions, Settings, Tips, Rewards) | Open | features, roadmap, scorecard |  |  | Cockpit tiles route to not-yet-redesigned screens.
P-38 | UI/UX | Single-total vs category-breakdown spend reconciliation (one source of truth) | Open | features |  |  | Avoid double-counting in recaps vs budget.
P-39 | UI/UX | Skeleton loaders + offline/sync state matrix | Open | ui-compliance (G-25) |  |  | No skeletons / stale states. P1.
P-40 | UI/UX | App-wide offline / sync indicator banner | Open | ui-compliance (G-20), qa-plan |  |  | Partial offline handling (tips) but no global status. P2.
P-41 | UI/UX | Undo toasts for reversible deletes ('Deleted · Undo') | Open | ui-compliance (G-11b) |  |  | Destructive actions use blocking dialogs. P1.
P-42 | UI/UX | Reusable 'what's this?' tooltip + searchable glossary module | Partial | ui-compliance (G-17), microservices |  |  | Build-#34 added glossary InfoDots; the reusable tooltip/glossary module + deep-links may still be partial — verify scope. P2.
P-43 | UI/UX | Money/date formatting standard (fix cents drift) | Open | ui-compliance (G-26 / B-46) |  |  | No written standard; cents-vs-whole-dollar drift. P2.
P-44 | UI/UX | User-pinnable / reorderable Home cards | Open | ui-compliance (G-18) |  |  | Home adapts by persona but users can't pin/reorder. P2.
P-45 | UI/UX | Raw-data / table toggle on charts | Open | ui-compliance (G-19) |  |  | Cognitive-load + a11y miss. P2.
P-46 | UI/UX | Notification design system (caps, per-type controls, deep-link) | Open | ui-compliance (G-30) |  |  | Push configured but no frequency caps. P2.
P-47 | UI/UX | Permission priming (camera/notifications) before the OS prompt | Open | ui-compliance (G-29) |  |  | P2.
P-48 | UI/UX | Surface the encryption cue in the UI (lock / 'encrypted' line) | Open | ui-compliance (G-34) |  |  | Encryption real but not shown. P3.
P-49 | UI/UX | Form-validation timing consistency (on-blur / submit) | Open | ui-compliance (G-35) |  |  | P3.
P-50 | UI/UX | Named text styles (Title/Body/Caption) + line-heights | Open | ui-compliance (G-22) |  |  | Applied ad-hoc, no roles. P3.
P-51 | UI/UX | Thumb-zone / Larger-text layout audit | Open | ui-compliance (G-33), qa-plan |  |  | P3.
P-52 | Stickiness/Growth | Push notifications (reminders / nudges) | Open | features |  |  | Plugin configured; reminder logic not built ('near your dining budget').
P-53 | Stickiness/Growth | Savings-goals full UI (waterfall-backed: progress, priority, projections) | Partial | features, roadmap, scorecard |  |  | Goals tab + funding engine exist (B-71); finish the waterfall-backed screen.
P-54 | Stickiness/Growth | Gen-Z motivational framing + app-wide Simple Mode | Open | features, roadmap Ph2.1/2.5 |  |  | Start-now compounding framing; Retirement got only a local plain toggle.
P-55 | Stickiness/Growth | Deeper gamification + education micro-lessons + shareable wins | Open | roadmap Ph2.5 |  |  | Milestones/challenges/streak rewards.
P-56 | Stickiness/Growth | Trends & Year-in-Review + shareable reports + widgets + weekly digest | Open | roadmap Ph4 |  |  | Surface snapshot history as value.
P-57 | Tech-debt/QA | Full string internationalization (translate copy, not just numbers) | Open | features, roadmap, scorecard |  |  | Externalize UI strings (i18next), date/number-by-locale, RTL. USD formatter already shipped.
P-58 | Tech-debt/QA | Currency/locale formatting — on-device verification | Partial | features |  |  | Model + formatter wired on active screens; on-device verify pending.
P-59 | Tech-debt/QA | Sentry full wiring | Done-verify | features, qa-plan |  |  | MEMORY + launch B-L2 say FULLY WIRED 2026-06-23 — VERIFY & drop (only the on-build verify remains, = L-12).
P-60 | Tech-debt/QA | Data export (JSON/CSV) — user data-right + round-trip import | Open | qa-plan, ui-compliance (G-28), roadmap 0.4 |  |  | Delete-all exists; no export. P2.
P-61 | Tech-debt/QA | Schema versioning + migrations on store hydrate | Open | roadmap Ph0.4 |  |  | Safe upgrades as fields keep being added.
P-62 | Tech-debt/QA | Unit tests for untested core calcs (Monte-Carlo, corpus, asset returns, grossFromNet…) | Open | qa-plan (T1-030..036) |  |  | simulate(), capitalNeeded(), solveRetireAge(), blendedReturn, investableValue… lack dedicated tests. P0/P1.
P-63 | Tech-debt/QA | Service-layer error-handling audit (try-catch + typed fallback) | Open | qa-plan (T4-002) |  |  | Verify BLS/Treasury/OCR/Firebase fetches aren't happy-path-only. P0.
P-64 | Tech-debt/QA | Network timeout / retry on all external calls | Open | qa-plan (T4-003) |  |  | No infinite spinner; every call needs a timeout + offline fallback. P1.
P-65 | Tech-debt/QA | Deprecated-API sweep (e.g. Swipeable → ReanimatedSwipeable) | Open | qa-plan (T4-001) |  |  | Migrate deprecated gesture-handler/date/expo APIs. P1.
P-66 | Tech-debt/QA | Complexity-hotspot review (retirement cockpit, income grid) | Open | qa-plan (T4-004) |  |  | Flag deeply nested logic for refactor. P2.
P-67 | Tech-debt/QA | Dead/orphan code + legacy 'debts' array (B-42) cleanup | Open | qa-plan (T4-005), bug-ledger |  |  | Unused exports, @deprecated scaffolding. Remove B-42 post-launch once no legacy data. P2.
P-68 | Tech-debt/QA | Type-safety escapes ('as any' casts, store typing) audit | Open | qa-plan (T4-006) |  |  | P2.
P-69 | Tech-debt/QA | Coverage gate on src/domain (e.g. 80%) in CI | Open | qa-plan §5.2
P-70 | Tech-debt/QA | Adopt the design-review governance gate as a merge check | Open | ui-compliance (G-36) |  |  | Tokens/components centralized; the gate is written but not enforced.
P-71 | Branding | App rename / trademark resolution ('FinWise' may be trademarked) | Open | rename-candidates, README |  |  | REAL legal blocker before public launch. Front-runner 'Hatcho' (hatcho.io/.ai free, clean open-web TM). Next: pick 2-3, run USPTO TESS (classes 9/36/42), register domains, rename across app.
P-72 | Other | Performance / offline-first architecture (cross-cutting) | Open | roadmap
P-73 | Other | Analytics / telemetry (activation funnels, D1/D7/D30 retention) | Open | roadmap Ph0.6 |  |  | Needed to know if we're 'top-3'. Enables launch metric L-21.
P-74 | Other | Device-cloud E2E (Maestro on BrowserStack/Sauce for fragmentation) | Open | qa-plan §5.1 |  |  | Broader device-matrix coverage beyond the launch-checklist Maestro flows (L-18).