## Read me
WHAT THIS IS | Everything you have to answer for Net worth, Cash flow and Performance to be launch-ready — by file, tab and row, which is what you asked for. Every line is ONE thing to answer and says what it blocks.
WHAT "LAUNCH-READY" MEANS HERE, and it is your definition not mine | A figure is not finished because it is coded and tested. Your ladder is RULED → CODED → TESTED → VERIFIED, and only your mark makes a row VERIFIED. A test can prove a figure is what the code gives; it can never prove it is the figure you wanted. So every row of these three modules needs reading.
THE ORDER I WOULD TAKE IT IN | 1. The unanswered questions — they block figures from moving behind their doors. 2. The questions you asked that nobody answered — they are not decisions yet. 3. The decisions recorded in my words — quickest to clear, "as written" is a complete answer. 4. The VERIFIED marks — the longest, and the one nobody can do for you.
WHAT IS NOT ON THIS LIST | Anything I can do myself. I have not put "write the remaining tests" or "fix the classifier" here — those are mine. This is only what needs you.
IT IS REBUILT, NEVER EDITED | Generated by build-launch-answer-list.py from the master file, the decision log and the working plan as they are on disk. Re-run it and it is current; a stale checklist once sent you on a wild-goose chase.

## EVERYTHING
40 things to answer
# | Module | WHAT TO ANSWER | WHERE — file | WHERE — tab | WHERE — row | Which column to type in | What it blocks if you do not | YOUR ANSWER
1 | Net worth | Q17 — "Return on cash + investments" counts money you paid in as a gain. Is the LABEL wrong, or the FORMULA? Fixing the formula means removing deposits and withdrawals before measuring. | moneykeel_calc_master_calculation-master_v01.xlsx | networth | MK-NW-M-002 — Return on cash + investments | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule.
2 | Net worth | Q32 — The trend survives on a new device but the walk behind it does not. Should the trend say so, or show quietly? | moneykeel_calc_master_calculation-master_v01.xlsx | networth | MK-NW-M-003 — the trend line | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule.
3 | Net worth | Q10 — What order of evidence decides an asset's class? Draft: the institution's own class field, then the shape of the identifier (option symbols, nine-character bond numbers, currency codes), then words in the name, then ask you. Q11 — When nothing matches: refuse the line and ask, or park it as unclassified? Parking keeps the totals right and hides a gap; refusing is honest and stops the import. Q12 — Does the person's own answer always win and stick, even when the next sync disagrees? That is today's rule for holdings — confirm it holds for every class. Q13 — Commodities: is a fund that | moneykeel_calc_master_calculation-master_v01.xlsx | networth | MK-NW-M-007 — class rows — by class, institution or type | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule.
4 | Net worth | Q14 — What should a MIXED account be called on screen, when it holds several classes at once? | moneykeel_calc_master_calculation-master_v01.xlsx | networth | MK-NW-M-008 — each account and its balance | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule.
5 | Net worth | Q53 — "Monthly debt payments" on the Net worth screen: the MINIMUM each debt obliges, or what ACTUALLY leaves your account? They part whenever someone pays more than a minimum. On one card — $200 minimum, paid $600 — the minimum reads $200 and the actual reads $600. Both are real figures: the minimum is the obligation a lender can demand (it is what debt-to-income is measured on), the actual is the money that leaves. The screen shows the MINIMUM today, and the label reads like the actual. Which belongs under those words — or should the line say which it is, or show both? | moneykeel_calc_master_calculation-master_v01.xlsx | networth | MK-NW-M-012 — Monthly debt payments | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule.
6 | Net worth | Q15 — An institution word we do not recognise: refuse the line and ask you, or book it as unclassified with no direction? The old sign-guess is what minted the $1.4 million. | moneykeel_calc_master_calculation-master_v01.xlsx | networth | MK-NW-M-019 — Income | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule.
7 | Net worth | Q01 — Is Quantity for a bond the FACE amount (e.g. 227,000) with the price quoted per $100 of face, or the number of bonds? It decides how value and gain are worked out. | moneykeel_calc_master_calculation-master_v01.xlsx | networth | MK-NW-M-023 — Face value | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule.
8 | Net worth | Q04 — "Annual income" on a bond: the last twelve months actually received, or the forward estimate from today\'s coupon? Both are defensible and they differ. | moneykeel_calc_master_calculation-master_v01.xlsx | networth | MK-NW-M-024 — Interest payments | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule.
9 | Net worth | Q05 — Accrued interest: do we work it out ourselves — which needs a day-count rule per bond type — or only show what the institution gives us? | moneykeel_calc_master_calculation-master_v01.xlsx | networth | MK-NW-M-026 — Yield if held to maturity | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule.
10 | Net worth | Q34 — Approve the exact wording for the average-price rule (info dot + column Q): 'Shares with no recorded purchase price are left out of the average. N of your shares are in that position.' — and the refusal: 'Average not available — none of these shares has a recorded price.' | moneykeel_calc_master_calculation-master_v01.xlsx | networth | MK-NW-M-032 — Price paid (average) | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule.
11 | Net worth | Q35 — Approve the exact label and the canon phrase for the twelve-month window. Proposed: 'Dividends received (trailing twelve months)' here, and 'trailing twelve months' in the other four places (spelled out — no initialism). Q36 — Dividends on this card: THIS account only, matching 'Realized from sales' beside it? Recommended: yes. | moneykeel_calc_master_calculation-master_v01.xlsx | networth | MK-NW-M-034 — Dividends received (12 mo) | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule.
12 | Net worth | Q37 — For a connected account: log an 'Opening holding' row per broker lot at first sync (dated the lot's purchase date, at the broker's cost) so every later sale is covered — recommended — or keep 'not counted + say so' for pre-history purchases? | moneykeel_calc_master_calculation-master_v01.xlsx | networth | MK-NW-M-035 — Realized gain from your buys and sells | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule.
13 | Net worth | Q20 — A lot with no recorded purchase price is skipped, so its gain is simply absent. Should the screen SAY so — "gain not counted for N shares, no purchase price on record" — rather than quietly reporting less? | moneykeel_calc_master_calculation-master_v01.xlsx | networth | MK-NW-M-036 — Gain — long-term (held over 1 yr) | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule.
14 | Net worth | Q03 — Certificates of deposit: under Fixed Income, or their own class? They carry a term, a rate and an early-withdrawal penalty that a bond does not. Q38 — Your bond display rule, three specifics before the mock: (1) 'quantity' for a bond = the number of bonds (each of face $1,000), or the total face amount? (2) 'earned interest' = the INTEREST rows recorded in the ledger for this bond — the only source we have — yes? (3) 'current price' = price per $100 of face as brokers quote it, or the dollar value of the position? Then I mock the bond card and screen before any code. | moneykeel_calc_master_calculation-master_v01.xlsx | networth | MK-NW-M-041 — total value of your bonds | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule.
15 | Performance | Q33 — Which index should each asset class be compared against, and should the person be able to change it? Q51 — Home reads "you +3.69% · market +2.83% · ahead by 0.85%". The two sides are not measured the same way: YOUR figure counts the dividends and interest you received (your ruling of 2026-09-25, one meaning of return), while the MARKET figure is the index's PRICE only, because no price feed we have gives an index's dividends. So "ahead by" flatters you by roughly the dividend yield. Three ways out: (a) leave it and say underneath that the market figure is price only; (b) compare price a | moneykeel_calc_master_calculation-master_v01.xlsx | performance | MK-PF-M-008 — market +X% | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule.
16 | Performance | Q52 — MK-PF-F-026 moneyWeightedReturn is a true personal return — it solves for the rate that makes what you paid in, on the days you paid it in, equal what you have now. It is built, correct and reached by NO SCREEN: the card that showed it was removed by the Performance design you approved on 2026-09-25. The Return the screen does show is a different calculation (Modified Dietz) that also calls itself money-weighted. Do we delete the unused one, or does it get a screen? | moneykeel_calc_master_calculation-master_v01.xlsx | multiple_screens | MK-XS-M-004 — ▲ up/▼ down $X (Y%) this month · Return · YOUR RETURN | YOUR ANSWER — use the same number | The figure stays DRAFT, and it is on MORE THAN ONE screen — so the answer settles what every screen showing it says.
17 | Net worth | VERIFY 48 rows — read each row and mark it VERIFIED, or say what is wrong. Only your mark makes a row VERIFIED; my tests can say a figure is what the code gives, never that it is the figure you wanted. | moneykeel_calc_master_calculation-master_v01.xlsx | networth | all 48 unverified rows on this tab | ROW VERIFIED — founder, date and how | The module cannot be called launch-ready: a TESTED row is proved to match the code, not proved to be right.
18 | Performance | VERIFY 11 rows — read each row and mark it VERIFIED, or say what is wrong. Only your mark makes a row VERIFIED; my tests can say a figure is what the code gives, never that it is the figure you wanted. | moneykeel_calc_master_calculation-master_v01.xlsx | performance | all 11 unverified rows on this tab | ROW VERIFIED — founder, date and how | The module cannot be called launch-ready: a TESTED row is proved to match the code, not proved to be right.
19 | Cash flow | VERIFY 53 rows — read each row and mark it VERIFIED, or say what is wrong. Only your mark makes a row VERIFIED; my tests can say a figure is what the code gives, never that it is the figure you wanted. | moneykeel_calc_master_calculation-master_v01.xlsx | cashflow | all 53 unverified rows on this tab | ROW VERIFIED — founder, date and how | The module cannot be called launch-ready: a TESTED row is proved to match the code, not proved to be right.
20 | Net worth | A QUESTION YOU ASKED AND NOBODY ANSWERED: Plain line - means line graph? | moneykeel_log_decisions_v01.xlsx | networth | DEC-0469 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
21 | Net worth | A QUESTION YOU ASKED AND NOBODY ANSWERED: what does screen look like for manual update? | moneykeel_log_decisions_v01.xlsx | networth | DEC-0470 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
22 | Net worth | A QUESTION YOU ASKED AND NOBODY ANSWERED: do we capture only balance or all individual portfolio holding e.g. AMZN 100 stocks …. | moneykeel_log_decisions_v01.xlsx | networth | DEC-0475 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
23 | Net worth | A QUESTION YOU ASKED AND NOBODY ANSWERED: When dividend is captured is it automatically added to income or cash? Similarly, is there a way captical gain is captured and displayed somewhere? | moneykeel_log_decisions_v01.xlsx | networth | DEC-0476 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
24 | Net worth | A QUESTION YOU ASKED AND NOBODY ANSWERED: Is this manual, imported or connected and captured via Plaid? | moneykeel_log_decisions_v01.xlsx | networth | DEC-0478 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
25 | Performance | A QUESTION YOU ASKED AND NOBODY ANSWERED: Total return captures both realized and unrealized gains? Is there any place we display realized P/L, unrealized P/L, total dividend, and total interest separately? | moneykeel_log_decisions_v01.xlsx | performance | DEC-0479 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
26 | Performance | A QUESTION YOU ASKED AND NOBODY ANSWERED: stocks with dividends - will it also show dividends received? | moneykeel_log_decisions_v01.xlsx | performance | DEC-0483 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
27 | Performance | A QUESTION YOU ASKED AND NOBODY ANSWERED: What's the level of details displayed and how?r | moneykeel_log_decisions_v01.xlsx | performance | DEC-0497 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
28 | Performance | A QUESTION YOU ASKED AND NOBODY ANSWERED: Invest: what level of detail, and how? | moneykeel_log_decisions_v01.xlsx | performance | DEC-0510 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
29 | Cash flow | A QUESTION YOU ASKED AND NOBODY ANSWERED: How is income + spending captured, at what frequency, and what about cash / unconnected cards? | moneykeel_log_decisions_v01.xlsx | cashflow | DEC-0503 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
30 | Cash flow | A QUESTION YOU ASKED AND NOBODY ANSWERED: Are the month bars cash flows -- inflow / outflow? | moneykeel_log_decisions_v01.xlsx | cashflow | DEC-0512 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
31 | Net worth | Commit — the branch was 278 files behind on 2026-09-14; committed since: 983805a (catch-up), f0e1d6d (Net worth v08), c4f2679 (the Since crash), 727e22a (Performance v14). Nothing is pushed — the branch taxonomy-v1.0.7 is local only. | moneykeel_calc_plan_workplan_v01.xlsx | Workplan | Commit — the branch was 278 files behind on 2026-09-14; committed sinc | Status / Comments | Founder: say when to PUSH. (Note 2026-09-26: the Xcode licence has not been accepted on this Mac, so the normal git refuses to run — "sudo xcodebuild -license accept" once, then git works everywhere again.)
32 | Net worth | EIGHT live mocks still DRAW words the canon retired (measured 2026-09-26 over the drawn frames, not the commentary): cash-flow this-month v06 ("In (take-home)", "spending") · income end-to-end v07 ("A usual month", "Gross a year") · look-ahead v03 ("/mo") · money-four-tabs v01 ("In (take-home)", "Out (", "/mo", "spending") · account-detail v01 ("Connected ·") · empty-state-pattern v01 ("WHAT YOU O | moneykeel_calc_plan_workplan_v01.xlsx | Workplan | EIGHT live mocks still DRAW words the canon retired (measured 2026-09- | Status / Comments | Founder: say whether each gets a new version on the canon now (old archived), or at its next change. Plan v05 already carries its list inside the file as mark 14 and is fixed when v06 is drawn.
33 | Cash flow | Stand-in ages when the birth year is missing: the Retirement cockpit and Insights assume 45, the cash-flow model and the draw steer assume 68, the onboarding helper 35 (or 65 for the retirement age). Your rule R2 says an unknown input gives no number and a reason. | moneykeel_calc_plan_workplan_v01.xlsx | Workplan | Stand-in ages when the birth year is missing: the Retirement cockpit a | Status / Comments | Founder: say what those screens show when the birth year is missing (ask for it in place? show the door?); then Claude: mock first, then code
34 | Cash flow | Q-CF-2 'how much have I spent this month, against the plan, and what is left' — eight figures DRAFTED on MK-CF-O-003 thisMonth: expected inflow, planned outflow, planned surplus, each planned line, inflow so far, outflow so far, surplus so far, each received line (MK-CF-M-047…054) | moneykeel_calc_plan_workplan_v01.xlsx | Workplan | Q-CF-2 'how much have I spent this month, against the plan, and what i | Status / Comments | Founder: read the eight rows on the master's cashflow tab (Row status says DRAFT) and say yes, or say what changes. Claude: the moment you do, the Cash flow screen, the month detail screen and Home's cell move behind the door and stop working figures out themselves
35 | Net worth | One door, one term: the three ways to add an account read 'Link it (read-only)', 'Add by hand' and 'Import from a file' on every screen, under the heading 'How do you want to add an account?' — Home, Sharpen your plan, the Plan tab, Net worth (first day and the add sheet), the Connect an account screen and Performance | moneykeel_calc_plan_workplan_v01.xlsx | Workplan | One door, one term: the three ways to add an account read 'Link it (re | Status / Comments | Founder: approve the mock MoneyKeel/documents/home-screen/moneykeel_pres_mock_ways-to-add-an-account_v10.html (every affected screen, before and after). Claude: then build all of it the same day, with the tests and the canon row
36 | Net worth | Nothing recorded which design each screen was built from. The Build 53 Net worth and Performance finals (networth-FINAL.html, performance-FINAL.html, the two Net worth PDFs, Net worth screens 01 to 11) were filed under networth-and-performance/archive/ on 2026-09-01, which marks them replaced. They were not replaced. Six hours of mocks then started from the wrong files. CORRECTION 2026-09-14: Buil | moneykeel_calc_plan_workplan_v01.xlsx | Workplan | Nothing recorded which design each screen was built from. The Build 53 | Status / Comments | Claude: done 2026-09-14 — Build 53 files matched by exact content and recorded in MoneyKeel/documents/standards/moneykeel_pres_spec_design-each-screen-was-built-from_v01.md. Founder: (1) confirm Net worth = v5 + square corners; (2) say whether to draw Net worth v6 from the Build 53 code (v5 with squ
37 | Net worth | Net worth v07 — the three ways to add an account on Net worth (first day, the add sheet, the add button), plus every ruling since Build 53 that touches the screen (empty state, Debts, Emergency fund, Stocks / Funds, /month, you entered, expenses, odds to the nearest 5), each marked | moneykeel_calc_plan_workplan_v01.xlsx | Workplan | Net worth v07 — the three ways to add an account on Net worth (first d | Status / Comments | Founder: say yes to v08, or name a mark. Also: today's money for the retirement figures and tax on taxable withdrawals (recommended); whether dark/light bars replace the Plan tab's quiet labels. Claude: once approved, record v08 as the current Net worth design, archive v06, then build marks 1–4 and
38 | Net worth | The retirement sentence (Net worth, Plan, Home) prints future dollars without saying so, and the odds calculation charges no tax on withdrawals from taxable accounts — found checking the founder's question on v07 ($4.1M at 65 is about $2.0M in today's money) | moneykeel_calc_plan_workplan_v01.xlsx | Workplan | The retirement sentence (Net worth, Plan, Home) prints future dollars | Status / Comments | Founder: say whether to show today's money and to tax taxable withdrawals (recommended). Claude: then write both as findings on the master rows (MK-XS-M-002 and the pot/leftover figures) before any code.
39 | Cash flow | Two word collisions found building v08: Cash flow's 'Add by hand' adds an EXPENSE (the same words as the account door), and Settings still says 'Disconnect' beside 'Linked accounts' | moneykeel_calc_plan_workplan_v01.xlsx | Workplan | Two word collisions found building v08: Cash flow's 'Add by hand' adds | Status / Comments | Founder: say whether Cash flow's door should read differently (for example 'Add an expense by hand') and whether Disconnect becomes 'Unlink'.
40 | Net worth | LAUNCH ANSWER LIST — 61 things need you for Net worth, Cash flow and Performance to be launch-ready | moneykeel_calc_plan_workplan_v01.xlsx | Workplan | LAUNCH ANSWER LIST — 61 things need you for Net worth, Cash flow and P | Status / Comments | His ask, 2026-09-29: ‘Give me a list of files, tabs, and rows I need to answer for NW, CF, Performance sections of the app to be complete.’ Open MoneyKeel/documents/other/moneykeel_calc_plan_launch-answer-list_v01.xlsx. Five tabs: Read me, EVERYTHING, and one per module. Every line names its FILE, i

## Net worth
27 things to answer for Net worth
# | Module | WHAT TO ANSWER | WHERE — file | WHERE — tab | WHERE — row | Which column to type in | What it blocks if you do not | YOUR ANSWER
1 | Net worth | Q17 — "Return on cash + investments" counts money you paid in as a gain. Is the LABEL wrong, or the FORMULA? Fixing the formula means removing deposits and withdrawals before measuring. | moneykeel_calc_master_calculation-master_v01.xlsx | networth | MK-NW-M-002 — Return on cash + investments | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule. | Money paid should not be counted as a gain. The formula is incorrect and should be corrected. Formula Time weighted return.
2 | Net worth | Q32 — The trend survives on a new device but the walk behind it does not. Should the trend say so, or show quietly? | moneykeel_calc_master_calculation-master_v01.xlsx | networth | MK-NW-M-003 — the trend line | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule. | Don't understand the question - what trend are your referring to?
3 | Net worth | Q10 — What order of evidence decides an asset's class? Draft: the institution's own class field, then the shape of the identifier (option symbols, nine-character bond numbers, currency codes), then words in the name, then ask you. Q11 — When nothing matches: refuse the line and ask, or park it as unclassified? Parking keeps the totals right and hides a gap; refusing is honest and stops the import. Q12 — Does the person's own answer always win and stick, even when the next sync disagrees? That is today's rule for holdings — confirm it holds for every class. Q13 — Commodities: is a fund that | moneykeel_calc_master_calculation-master_v01.xlsx | networth | MK-NW-M-007 — class rows — by class, institution or type | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule. | Q10: Draft order is correct Q11: Refuse the line and ask Q12: user entry stays even if it is not in the import file. If user modify cost or quantity post import/linked from institution, cost basis should not be overwritten in future sync as quantity, price and market value can change with time but not cost. Q13: incomplete question
4 | Net worth | Q14 — What should a MIXED account be called on screen, when it holds several classes at once? | moneykeel_calc_master_calculation-master_v01.xlsx | networth | MK-NW-M-008 — each account and its balance | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule. | Call an account by it's name - no need to label it unless it is checking or savings account.
5 | Net worth | Q53 — "Monthly debt payments" on the Net worth screen: the MINIMUM each debt obliges, or what ACTUALLY leaves your account? They part whenever someone pays more than a minimum. On one card — $200 minimum, paid $600 — the minimum reads $200 and the actual reads $600. Both are real figures: the minimum is the obligation a lender can demand (it is what debt-to-income is measured on), the actual is the money that leaves. The screen shows the MINIMUM today, and the label reads like the actual. Which belongs under those words — or should the line say which it is, or show both? | moneykeel_calc_master_calculation-master_v01.xlsx | networth | MK-NW-M-012 — Monthly debt payments | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule.
6 | Net worth | Q15 — An institution word we do not recognise: refuse the line and ask you, or book it as unclassified with no direction? The old sign-guess is what minted the $1.4 million. | moneykeel_calc_master_calculation-master_v01.xlsx | networth | MK-NW-M-019 — Income | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule.
7 | Net worth | Q01 — Is Quantity for a bond the FACE amount (e.g. 227,000) with the price quoted per $100 of face, or the number of bonds? It decides how value and gain are worked out. | moneykeel_calc_master_calculation-master_v01.xlsx | networth | MK-NW-M-023 — Face value | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule.
8 | Net worth | Q04 — "Annual income" on a bond: the last twelve months actually received, or the forward estimate from today\'s coupon? Both are defensible and they differ. | moneykeel_calc_master_calculation-master_v01.xlsx | networth | MK-NW-M-024 — Interest payments | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule.
9 | Net worth | Q05 — Accrued interest: do we work it out ourselves — which needs a day-count rule per bond type — or only show what the institution gives us? | moneykeel_calc_master_calculation-master_v01.xlsx | networth | MK-NW-M-026 — Yield if held to maturity | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule.
10 | Net worth | Q34 — Approve the exact wording for the average-price rule (info dot + column Q): 'Shares with no recorded purchase price are left out of the average. N of your shares are in that position.' — and the refusal: 'Average not available — none of these shares has a recorded price.' | moneykeel_calc_master_calculation-master_v01.xlsx | networth | MK-NW-M-032 — Price paid (average) | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule.
11 | Net worth | Q35 — Approve the exact label and the canon phrase for the twelve-month window. Proposed: 'Dividends received (trailing twelve months)' here, and 'trailing twelve months' in the other four places (spelled out — no initialism). Q36 — Dividends on this card: THIS account only, matching 'Realized from sales' beside it? Recommended: yes. | moneykeel_calc_master_calculation-master_v01.xlsx | networth | MK-NW-M-034 — Dividends received (12 mo) | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule.
12 | Net worth | Q37 — For a connected account: log an 'Opening holding' row per broker lot at first sync (dated the lot's purchase date, at the broker's cost) so every later sale is covered — recommended — or keep 'not counted + say so' for pre-history purchases? | moneykeel_calc_master_calculation-master_v01.xlsx | networth | MK-NW-M-035 — Realized gain from your buys and sells | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule.
13 | Net worth | Q20 — A lot with no recorded purchase price is skipped, so its gain is simply absent. Should the screen SAY so — "gain not counted for N shares, no purchase price on record" — rather than quietly reporting less? | moneykeel_calc_master_calculation-master_v01.xlsx | networth | MK-NW-M-036 — Gain — long-term (held over 1 yr) | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule.
14 | Net worth | Q03 — Certificates of deposit: under Fixed Income, or their own class? They carry a term, a rate and an early-withdrawal penalty that a bond does not. Q38 — Your bond display rule, three specifics before the mock: (1) 'quantity' for a bond = the number of bonds (each of face $1,000), or the total face amount? (2) 'earned interest' = the INTEREST rows recorded in the ledger for this bond — the only source we have — yes? (3) 'current price' = price per $100 of face as brokers quote it, or the dollar value of the position? Then I mock the bond card and screen before any code. | moneykeel_calc_master_calculation-master_v01.xlsx | networth | MK-NW-M-041 — total value of your bonds | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule.
17 | Net worth | VERIFY 48 rows — read each row and mark it VERIFIED, or say what is wrong. Only your mark makes a row VERIFIED; my tests can say a figure is what the code gives, never that it is the figure you wanted. | moneykeel_calc_master_calculation-master_v01.xlsx | networth | all 48 unverified rows on this tab | ROW VERIFIED — founder, date and how | The module cannot be called launch-ready: a TESTED row is proved to match the code, not proved to be right.
20 | Net worth | A QUESTION YOU ASKED AND NOBODY ANSWERED: Plain line - means line graph? | moneykeel_log_decisions_v01.xlsx | networth | DEC-0469 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
21 | Net worth | A QUESTION YOU ASKED AND NOBODY ANSWERED: what does screen look like for manual update? | moneykeel_log_decisions_v01.xlsx | networth | DEC-0470 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
22 | Net worth | A QUESTION YOU ASKED AND NOBODY ANSWERED: do we capture only balance or all individual portfolio holding e.g. AMZN 100 stocks …. | moneykeel_log_decisions_v01.xlsx | networth | DEC-0475 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
23 | Net worth | A QUESTION YOU ASKED AND NOBODY ANSWERED: When dividend is captured is it automatically added to income or cash? Similarly, is there a way captical gain is captured and displayed somewhere? | moneykeel_log_decisions_v01.xlsx | networth | DEC-0476 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
24 | Net worth | A QUESTION YOU ASKED AND NOBODY ANSWERED: Is this manual, imported or connected and captured via Plaid? | moneykeel_log_decisions_v01.xlsx | networth | DEC-0478 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
31 | Net worth | Commit — the branch was 278 files behind on 2026-09-14; committed since: 983805a (catch-up), f0e1d6d (Net worth v08), c4f2679 (the Since crash), 727e22a (Performance v14). Nothing is pushed — the branch taxonomy-v1.0.7 is local only. | moneykeel_calc_plan_workplan_v01.xlsx | Workplan | Commit — the branch was 278 files behind on 2026-09-14; committed sinc | Status / Comments | Founder: say when to PUSH. (Note 2026-09-26: the Xcode licence has not been accepted on this Mac, so the normal git refuses to run — "sudo xcodebuild -license accept" once, then git works everywhere again.)
32 | Net worth | EIGHT live mocks still DRAW words the canon retired (measured 2026-09-26 over the drawn frames, not the commentary): cash-flow this-month v06 ("In (take-home)", "spending") · income end-to-end v07 ("A usual month", "Gross a year") · look-ahead v03 ("/mo") · money-four-tabs v01 ("In (take-home)", "Out (", "/mo", "spending") · account-detail v01 ("Connected ·") · empty-state-pattern v01 ("WHAT YOU O | moneykeel_calc_plan_workplan_v01.xlsx | Workplan | EIGHT live mocks still DRAW words the canon retired (measured 2026-09- | Status / Comments | Founder: say whether each gets a new version on the canon now (old archived), or at its next change. Plan v05 already carries its list inside the file as mark 14 and is fixed when v06 is drawn.
35 | Net worth | One door, one term: the three ways to add an account read 'Link it (read-only)', 'Add by hand' and 'Import from a file' on every screen, under the heading 'How do you want to add an account?' — Home, Sharpen your plan, the Plan tab, Net worth (first day and the add sheet), the Connect an account screen and Performance | moneykeel_calc_plan_workplan_v01.xlsx | Workplan | One door, one term: the three ways to add an account read 'Link it (re | Status / Comments | Founder: approve the mock MoneyKeel/documents/home-screen/moneykeel_pres_mock_ways-to-add-an-account_v10.html (every affected screen, before and after). Claude: then build all of it the same day, with the tests and the canon row
36 | Net worth | Nothing recorded which design each screen was built from. The Build 53 Net worth and Performance finals (networth-FINAL.html, performance-FINAL.html, the two Net worth PDFs, Net worth screens 01 to 11) were filed under networth-and-performance/archive/ on 2026-09-01, which marks them replaced. They were not replaced. Six hours of mocks then started from the wrong files. CORRECTION 2026-09-14: Buil | moneykeel_calc_plan_workplan_v01.xlsx | Workplan | Nothing recorded which design each screen was built from. The Build 53 | Status / Comments | Claude: done 2026-09-14 — Build 53 files matched by exact content and recorded in MoneyKeel/documents/standards/moneykeel_pres_spec_design-each-screen-was-built-from_v01.md. Founder: (1) confirm Net worth = v5 + square corners; (2) say whether to draw Net worth v6 from the Build 53 code (v5 with squ
37 | Net worth | Net worth v07 — the three ways to add an account on Net worth (first day, the add sheet, the add button), plus every ruling since Build 53 that touches the screen (empty state, Debts, Emergency fund, Stocks / Funds, /month, you entered, expenses, odds to the nearest 5), each marked | moneykeel_calc_plan_workplan_v01.xlsx | Workplan | Net worth v07 — the three ways to add an account on Net worth (first d | Status / Comments | Founder: say yes to v08, or name a mark. Also: today's money for the retirement figures and tax on taxable withdrawals (recommended); whether dark/light bars replace the Plan tab's quiet labels. Claude: once approved, record v08 as the current Net worth design, archive v06, then build marks 1–4 and
38 | Net worth | The retirement sentence (Net worth, Plan, Home) prints future dollars without saying so, and the odds calculation charges no tax on withdrawals from taxable accounts — found checking the founder's question on v07 ($4.1M at 65 is about $2.0M in today's money) | moneykeel_calc_plan_workplan_v01.xlsx | Workplan | The retirement sentence (Net worth, Plan, Home) prints future dollars | Status / Comments | Founder: say whether to show today's money and to tax taxable withdrawals (recommended). Claude: then write both as findings on the master rows (MK-XS-M-002 and the pot/leftover figures) before any code.
40 | Net worth | LAUNCH ANSWER LIST — 61 things need you for Net worth, Cash flow and Performance to be launch-ready | moneykeel_calc_plan_workplan_v01.xlsx | Workplan | LAUNCH ANSWER LIST — 61 things need you for Net worth, Cash flow and P | Status / Comments | His ask, 2026-09-29: ‘Give me a list of files, tabs, and rows I need to answer for NW, CF, Performance sections of the app to be complete.’ Open MoneyKeel/documents/other/moneykeel_calc_plan_launch-answer-list_v01.xlsx. Five tabs: Read me, EVERYTHING, and one per module. Every line names its FILE, i

## Cash flow
6 things to answer for Cash flow
# | Module | WHAT TO ANSWER | WHERE — file | WHERE — tab | WHERE — row | Which column to type in | What it blocks if you do not | YOUR ANSWER
19 | Cash flow | VERIFY 53 rows — read each row and mark it VERIFIED, or say what is wrong. Only your mark makes a row VERIFIED; my tests can say a figure is what the code gives, never that it is the figure you wanted. | moneykeel_calc_master_calculation-master_v01.xlsx | cashflow | all 53 unverified rows on this tab | ROW VERIFIED — founder, date and how | The module cannot be called launch-ready: a TESTED row is proved to match the code, not proved to be right.
29 | Cash flow | A QUESTION YOU ASKED AND NOBODY ANSWERED: How is income + spending captured, at what frequency, and what about cash / unconnected cards? | moneykeel_log_decisions_v01.xlsx | cashflow | DEC-0503 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
30 | Cash flow | A QUESTION YOU ASKED AND NOBODY ANSWERED: Are the month bars cash flows -- inflow / outflow? | moneykeel_log_decisions_v01.xlsx | cashflow | DEC-0512 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
33 | Cash flow | Stand-in ages when the birth year is missing: the Retirement cockpit and Insights assume 45, the cash-flow model and the draw steer assume 68, the onboarding helper 35 (or 65 for the retirement age). Your rule R2 says an unknown input gives no number and a reason. | moneykeel_calc_plan_workplan_v01.xlsx | Workplan | Stand-in ages when the birth year is missing: the Retirement cockpit a | Status / Comments | Founder: say what those screens show when the birth year is missing (ask for it in place? show the door?); then Claude: mock first, then code
34 | Cash flow | Q-CF-2 'how much have I spent this month, against the plan, and what is left' — eight figures DRAFTED on MK-CF-O-003 thisMonth: expected inflow, planned outflow, planned surplus, each planned line, inflow so far, outflow so far, surplus so far, each received line (MK-CF-M-047…054) | moneykeel_calc_plan_workplan_v01.xlsx | Workplan | Q-CF-2 'how much have I spent this month, against the plan, and what i | Status / Comments | Founder: read the eight rows on the master's cashflow tab (Row status says DRAFT) and say yes, or say what changes. Claude: the moment you do, the Cash flow screen, the month detail screen and Home's cell move behind the door and stop working figures out themselves
39 | Cash flow | Two word collisions found building v08: Cash flow's 'Add by hand' adds an EXPENSE (the same words as the account door), and Settings still says 'Disconnect' beside 'Linked accounts' | moneykeel_calc_plan_workplan_v01.xlsx | Workplan | Two word collisions found building v08: Cash flow's 'Add by hand' adds | Status / Comments | Founder: say whether Cash flow's door should read differently (for example 'Add an expense by hand') and whether Disconnect becomes 'Unlink'.

## Performance
7 things to answer for Performance
# | Module | WHAT TO ANSWER | WHERE — file | WHERE — tab | WHERE — row | Which column to type in | What it blocks if you do not | YOUR ANSWER
15 | Performance | Q33 — Which index should each asset class be compared against, and should the person be able to change it? Q51 — Home reads "you +3.69% · market +2.83% · ahead by 0.85%". The two sides are not measured the same way: YOUR figure counts the dividends and interest you received (your ruling of 2026-09-25, one meaning of return), while the MARKET figure is the index's PRICE only, because no price feed we have gives an index's dividends. So "ahead by" flatters you by roughly the dividend yield. Three ways out: (a) leave it and say underneath that the market figure is price only; (b) compare price a | moneykeel_calc_master_calculation-master_v01.xlsx | performance | MK-PF-M-008 — market +X% | YOUR ANSWER — use the same number | The figure stays DRAFT: it is declared and printed, and nothing moves behind its door until you rule.
16 | Performance | Q52 — MK-PF-F-026 moneyWeightedReturn is a true personal return — it solves for the rate that makes what you paid in, on the days you paid it in, equal what you have now. It is built, correct and reached by NO SCREEN: the card that showed it was removed by the Performance design you approved on 2026-09-25. The Return the screen does show is a different calculation (Modified Dietz) that also calls itself money-weighted. Do we delete the unused one, or does it get a screen? | moneykeel_calc_master_calculation-master_v01.xlsx | multiple_screens | MK-XS-M-004 — ▲ up/▼ down $X (Y%) this month · Return · YOUR RETURN | YOUR ANSWER — use the same number | The figure stays DRAFT, and it is on MORE THAN ONE screen — so the answer settles what every screen showing it says.
18 | Performance | VERIFY 11 rows — read each row and mark it VERIFIED, or say what is wrong. Only your mark makes a row VERIFIED; my tests can say a figure is what the code gives, never that it is the figure you wanted. | moneykeel_calc_master_calculation-master_v01.xlsx | performance | all 11 unverified rows on this tab | ROW VERIFIED — founder, date and how | The module cannot be called launch-ready: a TESTED row is proved to match the code, not proved to be right.
25 | Performance | A QUESTION YOU ASKED AND NOBODY ANSWERED: Total return captures both realized and unrealized gains? Is there any place we display realized P/L, unrealized P/L, total dividend, and total interest separately? | moneykeel_log_decisions_v01.xlsx | performance | DEC-0479 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
26 | Performance | A QUESTION YOU ASKED AND NOBODY ANSWERED: stocks with dividends - will it also show dividends received? | moneykeel_log_decisions_v01.xlsx | performance | DEC-0483 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
27 | Performance | A QUESTION YOU ASKED AND NOBODY ANSWERED: What's the level of details displayed and how?r | moneykeel_log_decisions_v01.xlsx | performance | DEC-0497 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.
28 | Performance | A QUESTION YOU ASKED AND NOBODY ANSWERED: Invest: what level of detail, and how? | moneykeel_log_decisions_v01.xlsx | performance | DEC-0510 | Open question on this decision — for him | It is not a decision until it is answered, so nothing can be built or tested against it.