## Open gaps vs mock
# | Found by | Screen | Gap | Class of defect | Status
1 | Founder | NW main | E*TRADE CD still shows under Cash | DATA REALITY — the cash-only rule was applied to NEW data only; existing/synced accounts were never re-classified | OPEN
2 | Founder | NW main | VMFXX (money-market fund) still under Cash | same class as #1 — needs a one-time migration over existing accounts | OPEN
3 | Founder | NW main | Inside the Cash group there is a SECOND "Cash" sub-heading with the items under it | NESTING — group bar and class sub-band duplicate each other | OPEN
4 | Founder | NW main | Group totals sit slightly LEFT of the row numbers | ALIGNMENT — band value inset differs from row value inset | OPEN
5 | Founder | NW main | "By category / By institution" pills sit BELOW What you owe; the mock puts them above the lists | ORDER | OPEN
6 | Claude | NW main | Hero band reads "YOUR NET WORTH"; mock reads "YOUR NET WORTH · AUG 4, 2026 info-dot" | TEXT DIFF | OPEN
7 | Claude | NW main | Retirement card still uses the OLD "path ahead ... by 92" wording, unbanded; mock has the banded card with the approved sentence | TEXT DIFF + approved-words decision not applied here | OPEN
8 | Claude | NW main | Under the change: code shows "as of Aug 10"; mock shows "since Aug 3, 2026" | TEXT DIFF — different meaning | OPEN
9 | Claude | NW main | Emergency cushion card differs between the with-data screen and the mock | TEXT/STRUCTURE | OPEN

## Method that must be used
1. Extract every visible string from the approved mock, in order — that list is the spec.
2. Render the screen with real-shaped data; dump every visible string, in order.
3. Diff the two lists. Every different/missing/extra line is a defect. Report N of N identical.
4. Check order, nesting, alignment, data reality (rule changes must re-classify EXISTING accounts).
5. State what was NOT verified — appearance is never proven by these tests.