## Launch (v1)
Launch (v1)
Everything targeted for the NEXT launch (v1): the must-do steps to ship, PLUS the v1 work lifted up from the backlog. Type: 'Blocker' = can't ship without it · 'v1 feature' = wanted in the launch but not blocking the submission · 'Important'/'Decision'/'Recommended' as labelled. Stage = where it is (Plan→Design→Build→Test→Refine→Ready, or Done). The top block (L-#) is the ship process in critical-path order; below it are the v1 features. Yellow columns are yours to fill (J Rank / J Notes / Decision); 'Your rank' is my suggested order. Heads-up: the must-ship-to-submit set is the Blockers near the top — the v1 features can't all make a launch that's days away.
ID | Area | Item | Owner | Type | Stage | Status / what's left | Your rank | J Rank | J Notes | Decision (when) | Notes / next step
L-1 | Data | Switch to a paid, properly-licensed source for stock & fund prices (the free Yahoo feed isn't legal for a paid app). | You→Claude | Blocker | Plan | Open — the long pole | 1 | 4 |  | NOW | You pick a provider (Tiingo is cheapest, ~$10–50/mo) and get a key; then I do a small swap. This is a legal must-fix.
L-15 | Accuracy | Make a spending category entered as a percentage turn into the SAME dollar amount everywhere it's used. | Claude | Accuracy | Test | Likely done — I'm verifying | 2 | done | Test | NOW — verify | Automatic checks pass; I'll confirm the percentage path specifically.
L-16 | Accuracy | Make every screen show the SAME number for the same thing (take-home pay can't differ screen to screen). | Claude | Accuracy | Done | Done 2026-06-25 | 3 | done | Test | DONE | Locked in by an automatic check. A wrong number = lost trust.
L-17 | Accuracy | Confirm no money figure shown anywhere is wrong. | Claude | Important | Test | Ongoing — none currently open | 4 |  |  | NOW — verify | Re-check before each submission.
L-2 | Security | Lock down the cloud database so each person can only read their own data. | You | Blocker | Done | Done 2026-06-17 (the old checklist was stale) | 5 | done |  | DONE — confirm console | Already deployed; just confirm it's active in the console.
L-19 | Compliance | Write the note to Apple's reviewer explaining the app is an educational planner (no money movement). | You | Important | Refine | Draft exists | 6 | 5 |  | NOW | Reduces the risk of rejection under finance-app rules.
L-5 | Listing | Enter the App Store description, keywords, subtitle, and promo text. | You | Blocker | Refine | Drafted — needs entering | 7 | 6 |  | NOW | The wording is written; paste it into App Store Connect.
L-8 | Compliance | Fill in Apple's privacy questionnaire so it matches what the app actually collects. | You | Blocker | Plan | Open | 8 | 7 |  | NOW | Declare email, name, financial info, crash data — all to run the app, none for tracking. Apple cross-checks.
L-6 | Listing | Set the app's category (Finance) and age rating (4+). | You | Blocker | Plan | Open (quick) | 9 | 8 |  | NOW | Short questionnaires in App Store Connect.
L-9 | Compliance | Create a test login with sample data for Apple's reviewer and include it in the submission. | You | Blocker | Plan | Open | 10 | 9 |  | NOW | Without it the reviewer can't get past sign-in and will reject.
L-7 | Listing | Publish a live Privacy Policy page and a Support page, and link them. | You | Blocker | Build | Part done — privacy page needs the new wording re-published; support page not made yet | 11 | 1 |  | NOW | The privacy page is live but its text changed (see L-11).
L-11 | Compliance | Re-publish the privacy page with the new wording: financial data and receipts never leave your device. | You | Blocker | Refine | Wording done in the app; the public page isn't re-published | 12 | 2 |  | NOW | The promise is already true in the app; the public page must say the same.
L-20 | Positioning | Decide to launch in the US only for now. | You | Decision | Plan | Likely already (US-dollars only) | 13 | 3 | Have Claude confirm | NOW — decide | Confirm; don't market it globally yet.
L-21 | Positioning | Decide to track 'how many people finish setup' as the #1 success measure. | You | Decision | Plan | Decision needed | 14 |  |  | NOW — decide | Needs basic usage tracking (see the analytics item below).
L-13 | Compliance | Show a 'this is an estimate, not advice' note on every forecast or 'on-track' verdict. | Claude | Important | Done | Done | 15 | done | Test | DONE | Added everywhere; a guard test stops it being removed.
L-14 | Reliability | Make sure the app handles no-internet gracefully instead of crashing. | Claude | Important | Done | Done (verified) | 16 | done | Test | DONE | Already safe; proven by offline tests.
L-3 | Build | Build the real app installer (build #35) and check receipt-scanning + secure storage on a real phone. | You (EAS) | Blocker | Build | Blocked on the free build allowance (~Jul 1); the code is ready | 17 | done | Test | AT BUILD #35 | Everything's in and tested; push-button once the allowance resets.
L-23 | Data | Confirm prices load from the new paid source (not Yahoo). | You | Blocker | Plan | Waiting on the vendor swap (L-1) | 18 |  |  | AT BUILD #35
L-12 | Reliability | Confirm a crash report actually reaches the dashboard on the new build. | You | Blocker | Test | Wired; verify on the build | 19 | done | Test | AT BUILD #35 | Press the test button in Settings and check it lands.
L-10 | Compliance | Test that 'delete my account' fully wipes your data on a real build. | You | Blocker | Test | Open (needs build #35) | 20 | done | Test | AT BUILD #35 | Apple requires this; confirm it removes cloud data and login.
L-22 | Testing | Walk through setup as each user type (student, variable income, professional, retiree) and check the numbers add up. | You | Blocker | Test | Open (needs build #35) | 21 | done | Test | AT BUILD #35 | Use the user guide as the script.
L-24 | Testing | Test sign up → log out → recover account → log back in. | You | Blocker | Test | Open | 22 | done | Test | AT BUILD #35
L-18 | Testing | Run the automated tap-through tests on a real phone (sign-up, basic screens, add-sheet, net-worth, cash-flow). | You | Important | Test | Open (needs build) | 23 |  | ?? | AT BUILD #35 | These scripts have never run on a real device, so some may need small fixes the first time.
L-25 | Testing | Hands-on test on a real phone: gestures, keyboard, screen edges, large text. | You | Recommended | Test | Open (needs build) | 24 | done | Test | AT BUILD #35
L-4 | Listing | Take the App Store screenshots on a real iPhone. | You | Blocker | Build | Open (needs a device build) | 25 | 10 |  | AT BUILD #35 | 8 framed shots with captions are already planned out.
L-26 | Submit | Submit the build to TestFlight and then to App Review. | You | Blocker | Plan | Final step | 26 |  |  | SUBMIT (last) | Submitting doesn't use the build allowance.
P-71 | Branding | Pick and trademark a final app name, since 'FinWise' may already be taken. | You→Claude | Blocker | Plan | Not started |  |  |  | Before submit — legal | A real legal blocker before public launch; 'Hatcho' is the front-runner.
P-23 | Security | Scan the app's building blocks for known security holes and fix the risky ones. | Claude | Important | Plan | Not started |  |  |  | Before submit | A high-priority safety check before launch.
P-29 | Accessibility | Make buttons big enough to tap reliably for everyone. | Claude | Important | Plan | Not started |  |  |  | Before submit | An accessibility basic (for users with disabilities); high priority.
P-63 | Quality | Review that every data fetch handles errors gracefully, not just the happy path. | Claude | Important | Plan | Not started |  |  |  | Before submit | Prevents crashes and blank screens; high priority.
P-64 | Quality | Add timeouts and retries so the app never hangs waiting on data. | Claude | Important | Plan | Not started |  |  |  | Before submit | Stops endless loading spinners; medium priority.
P-73 | Other | Add usage tracking to see how many people finish setup and keep coming back. | Claude | Important | Plan | Not started |  |  |  | Before submit (enables L-21) | Needed to measure success and the top launch metric.
P-4 | Data | Turn on snap-a-photo receipt scanning and improve how it reads the totals. | Claude | v1 feature | Plan | Not started |  |  |  | v1 feature | Nearly ready; needs a real device build to switch on and test.
P-5 | Data | Catch bad rows when you import a spreadsheet so imports don't break things. | Claude | v1 feature | Plan | Not started |  |  |  | v1 feature | Protects against messy files corrupting your data.
P-6 | Insights | Turn your saved history into smart nudges like 'gas spending up 15% this month'. | Claude | v1 feature | Build | A basic 9-rule version works; the richer history-driven version isn't built. |  |  |  | v1 feature | Makes the app feel personal and proactive.
P-7 | Insights | Put a consistent tap-to-explain button on every AI suggestion so you see the reasoning. | Claude | v1 feature | Plan | Not started |  |  |  | v1 feature | Builds trust; explanations exist but aren't uniform yet.
P-8 | Insights | Ask the app plain questions like 'can I afford a $600k house?' and get an answer. | Claude | v1 feature | Plan | Not started |  |  |  | v1 feature | A standout feature that sets the app apart.
P-10 | Retire | Show retirees whether their money will last as they spend it down. | Claude | v1 feature | Build | A basic spend-down view exists; deeper retiree-focused views aren't built. |  |  |  | v1 feature | Answers the top question retirees have.
P-11 | Retire | Plan smart, tax-savvy withdrawals in retirement to keep more of your money. | Claude | v1 feature | Plan | Not started |  |  |  | v1 feature | Valuable but sensitive; needs careful, accurate tax handling.
P-14 | Retire | Let couples and households share goals while keeping personal views too. | Claude | v1 feature | Plan | Partner invites are partly built. |  |  |  | v1 feature | Needed for shared finances.
P-15 | Retire | Add saving-for-college planning. | Claude | v1 feature | Plan | Not started |  |  |  | v1 feature | Fills a gap for families with kids.
P-16 | Retire | Add life and long-term-care insurance planning. | Claude | v1 feature | Plan | Not started |  |  |  | v1 feature | Fills a life-stage gap many users hit.
P-19 | Retire | Add a mode for gig and freelance income that smooths uneven pay and sets aside taxes. | Claude | v1 feature | Plan | Not started |  |  |  | v1 feature | Serves the growing self-employed audience.
P-20 | Onboarding | Let users add more details later to sharpen their plan, prompted step by step. | Claude | v1 feature | Build | A simple checklist exists; the guided 'add more to sharpen' flow isn't built. |  |  |  | v1 feature | Improves plan accuracy without overwhelming people upfront.
P-21 | Security | Let partners securely share one encrypted account through an invite code. | Claude | v1 feature | Plan | Not started |  |  |  | v1 feature | Today two logins can't share the same encrypted data; needed for couples.
P-27 | Security | Require a fingerprint or face check to confirm the most important actions. | Claude | v1 feature | Plan | Not started |  |  |  | v1 feature | App unlock already uses biometrics; this adds per-action confirmation.
P-33 | UI/UX | Add a tap to hide or blur your balances for privacy. | Claude | v1 feature | Done | Done — verify |  |  |  | v1 feature | Lets you check the app in public without showing your money.
P-34 | UI/UX | Show how many months your cash savings could cover if income stopped. | Claude | v1 feature | Plan | Not started |  |  |  | v1 feature | A reassuring 'safety cushion' number; overlaps the job-loss mode.
P-35 | UI/UX | Add a Home card showing how your net worth has grown over time. | Claude | v1 feature | Plan | Not started |  |  |  | v1 feature | A motivating progress view like 'net worth up $40k in 6 months'.
P-36 | UI/UX | Redesign the top bar and bottom menu to match the newer look. | Claude | v1 feature | Build | The newer style exists elsewhere; the header and menu still use older styling. |  |  |  | v1 feature | Visual consistency across the app.
P-38 | UI/UX | Make total spending and the category breakdown always add up to the same number. | Claude | v1 feature | Plan | Not started |  |  |  | v1 feature | Prevents confusing double-counting between summaries and budget.
P-39 | UI/UX | Add loading placeholders and clear offline / syncing states. | Claude | v1 feature | Plan | Not started |  |  |  | v1 feature | Makes the app feel smoother while data loads; medium priority.
P-41 | UI/UX | Add an 'undo' option after deleting something by mistake. | Claude | v1 feature | Plan | Not started |  |  |  | v1 feature | Friendlier than a blocking confirmation pop-up; medium priority.
P-42 | UI/UX | Add a reusable 'what's this?' tooltip and a searchable plain-language glossary. | Claude | v1 feature | Build | Simple explainer dots were added; the full tooltip and glossary module may be unfinished. |  |  |  | v1 feature | Helps users understand finance terms; lower priority.
P-43 | UI/UX | Set one consistent rule for showing money and dates so cents don't drift. | Claude | v1 feature | Plan | Not started |  |  |  | v1 feature | Keeps numbers looking correct and uniform; lower priority.
P-45 | UI/UX | Let users switch any chart to a plain data table. | Claude | v1 feature | Plan | Not started |  |  |  | v1 feature | Easier to read for some users; lower priority.

## Future backlog
Future backlog
Everything NOT in the next launch — future work, grouped by area. Version: 'v1.x (soon)' = a soon-after-launch point release · 'v2 (future)' = a later bigger release. Stage shows how far along each is; 'What's left' spells out what's unfinished for the part-done ones. Yellow columns are yours (Version / Your notes). Note: I lifted every v1 item up to the Launch tab, and removed the crash-reporting row here because it's the same work as a launch item (L-12).
ID | Category | Item | Stage | What's left | Version (v1.x soon / v2 future) | Your notes | Why it matters
P-1 | Data | Connect the app to your bank and brokerage so balances and transactions pull in automatically. | Plan |  | v2 (future) |  | Biggest convenience and stickiness win, but a large build needing a secure server.
P-2 | Data | Automatically figure out dividends from a stock ticker instead of you typing them in. | Plan |  | v2 (future) |  | Saves manual entry for people who hold dividend-paying stocks.
P-3 | Data | Suggest stock tickers as you type and cache prices so they load faster. | Plan |  | v2 (future) |  | Nice polish; the core performance views already work.
P-9 | Insights | Compare life choices like buying a home, having a child, or a job change side by side. | Plan |  | v2 (future) |  | Helps users weigh big decisions.
P-12 | Retire | Assume your savings grow as your pay rises over the years. | Plan |  | v2 (future) |  | Makes retirement projections more realistic.
P-13 | Retire | Support married filers and other countries' tax and account rules. | Plan |  | v2 (future) |  | Today it only handles single US filers; needed to expand abroad.
P-17 | Retire | Add estate planning like naming who inherits and tracking key documents. | Plan |  | v2 (future) |  | Rounds out planning for later life stages.
P-18 | Retire | Add a job-loss mode showing how long your cash lasts and a survival budget. | Plan |  | v2 (future) |  | Helps people through a stressful transition.
P-22 | Security | Add two-step login for stronger account security. | Plan |  | v2 (future) |  | App lock already exists; this is the next security layer.
P-24 | Security | Add automated code scanning that flags security flaws as code is written. | Plan |  | v2 (future) |  | Catches problems early; lower priority.
P-25 | Security | Scan the finished app file for insecure storage or data-transfer issues. | Plan |  | v2 (future) |  | Extra security check; lower priority.
P-26 | Security | Make sure all data fetches use secure, encrypted connections. | Plan |  | v2 (future) |  | Protects data in transit; lower priority.
P-28 | Accessibility | Make every screen work with the screen reader for blind and low-vision users. | Plan |  | v2 (future) |  | The single biggest accessibility gap (for users with disabilities).
P-30 | Accessibility | Add dark mode and a high-contrast theme. | Plan |  | v2 (future) |  | A comfort and readability option; lower priority.
P-31 | Accessibility | Check that all text and charts have enough color contrast to be readable. | Plan |  | v2 (future) |  | An accessibility review (for users with disabilities); medium priority.
P-32 | Accessibility | Tone down animations for users who prefer less motion. | Plan |  | v2 (future) |  | A small comfort improvement; low priority.
P-37 | UI/UX | Refresh the older detail screens like budget, transactions, settings, and rewards. | Plan |  | v2 (future) |  | The new home tiles still open older-looking screens.
P-40 | UI/UX | Add an app-wide banner showing when you're offline or syncing. | Plan |  | v2 (future) |  | Keeps users informed about connection status; lower priority.
P-44 | UI/UX | Let users pin and rearrange the cards on their Home screen. | Plan |  | v2 (future) |  | Personalizes the home view; lower priority.
P-46 | UI/UX | Build a notification system with frequency limits and per-type controls. | Plan |  | v2 (future) |  | Prevents notification overload; lower priority.
P-47 | UI/UX | Explain why the app needs camera or notification access before the system asks. | Plan |  | v2 (future) |  | Increases the chance users say yes; lower priority.
P-48 | UI/UX | Show a visible 'your data is encrypted' cue in the app. | Plan |  | v2 (future) |  | Reassures users their data is protected; low priority.
P-49 | UI/UX | Make form error messages appear at consistent moments across the app. | Plan |  | v2 (future) |  | Small polish for a smoother experience; low priority.
P-50 | UI/UX | Define standard text styles for titles, body, and captions. | Plan |  | v2 (future) |  | Keeps typography consistent; low priority.
P-51 | UI/UX | Check that layouts work for one-handed use and large text sizes. | Plan |  | v2 (future) |  | A comfort and accessibility review (for users with disabilities); low priority.
P-52 | Growth | Send reminder nudges like 'you're near your dining budget'. | Plan | The plumbing exists; the reminder logic isn't built. | v2 (future) |  | Drives people back into the app.
P-53 | Growth | Finish the full savings-goals screen with progress, priority, and projections. | Build | The goals tab and funding logic exist; the full visual screen isn't finished. | v1.x (soon) |  | Helps people set and track goals; a stickiness feature.
P-54 | Growth | Add younger, motivational framing and a simpler app-wide mode. | Plan |  | v2 (future) |  | Makes the app approachable; only one screen has a plain toggle today.
P-55 | Growth | Add more game-like rewards, mini lessons, and shareable wins. | Plan |  | v2 (future) |  | Boosts engagement through milestones and streaks.
P-56 | Growth | Add trends, a year-in-review, shareable reports, widgets, and a weekly summary. | Plan |  | v2 (future) |  | Turns saved history into ongoing value for users.
P-57 | Quality | Translate the app's wording into other languages, not just the numbers. | Plan |  | v2 (future) |  | Needed to reach non-English users; currency formatting already done.
P-58 | Quality | Confirm money and date formats display correctly on a real device. | Build | The formatting logic is wired; it just needs checking on an actual phone. | v1.x (soon) |  | Ensures numbers look right everywhere.
P-60 | Quality | Let users export their data to a file and import it back. | Plan |  | v1.x (soon) |  | Gives users control of their data; medium priority.
P-61 | Quality | Safely upgrade saved data as new fields are added over time. | Plan |  | v2 (future) |  | Prevents data problems when the app updates.
P-62 | Quality | Add tests for the core retirement and investment math. | Plan |  | v1.x (soon) |  | Protects accuracy of the most important calculations; high priority.
P-65 | Quality | Replace outdated app components with their current versions. | Plan |  | v2 (future) |  | Keeps the app maintainable and future-proof; medium priority.
P-66 | Quality | Simplify the most tangled parts of the code, like the retirement and income screens. | Plan |  | v2 (future) |  | Makes future changes safer and easier; lower priority.
P-67 | Quality | Remove unused and leftover old code. | Plan |  | v2 (future) |  | Tidies up the app after launch; lower priority.
P-68 | Quality | Tighten up loose data typing to catch more bugs automatically. | Plan |  | v2 (future) |  | Reduces hidden errors; lower priority.
P-69 | Quality | Require core calculations to stay well-tested before any code change ships. | Plan |  | v2 (future) |  | Guards the most important math automatically.
P-70 | Quality | Make design consistency a required check before new code is merged. | Plan |  | v2 (future) |  | The rules are written but not yet enforced.
P-72 | Other | Improve overall speed and make the app work well offline. | Plan |  | v2 (future) |  | A broad, behind-the-scenes quality improvement.
P-74 | Other | Test the app across many real phone models in the cloud to catch device-specific bugs. | Plan |  | v2 (future) |  | Ensures it works on the wide range of phones people own.